## Instructions
1. Use summary sheet tab to track concrete poured each month and each structure.
2. Use concrete pour summary sheet tab to track concrete pours as well as compressive strength breaks from testing company based on days. If you have not input a testing report by the break date the cell for that report in the "Sample 1" Column will turn red to alert you that the report is overdue.
3. Use pump truck tab to track pump truck rentals. Make sure to note pump truck size ordered vs. pump truck size delivered. Should only pay for the rate for the size ordered even if a larger truck is sent.
4. Use concrete credits tab to track credits owed by concrete supplier (i.e. truck not meeting slump requirements, a truck that timed out).
5. Copy concrete estimate into Estimate tab. Use as a reference for total CY of concrete on project and CYs required for each structure.

## Summary Sheet
JOB # AND NAME | 0673 OWP AWWTF
JOB START DATE | 2026-04-01
| Total Est CY | TBD
Month | Yards Poured | % Completed Monthly | Structure | Est. Yds | JTD Yds | Diff. | Est. Cost | JTD Cost | Diff. | Est. Rate | Actual Rate
2026-04-01 | 13 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-05-01 | 3 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-06-01 | 109 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-07-01 | 45 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-08-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-09-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-10-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-11-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2026-12-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-01-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-02-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-03-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-04-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-05-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-06-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-07-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-08-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-09-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-10-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-11-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2027-12-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-01-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-02-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-03-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-04-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-05-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-06-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
2028-07-01 | 0 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
JTD | 170 | #VALUE! |  |  | 0 | 0 |  | 0 | 0 | - | -
Formulas:
Month = DATE(YEAR([Month, row above]),MONTH([Month, row above])+1,DAY([Month, row above]))

## Concrete Pour Summary
0673 OWP AWWTF |  | CIP 10301 | DATE | 2026-08-05 | [9 empty] | Report Overdue
|  |  | Total Est CY | 13006
|  |  | Total CY Placed | 170
Concrete Log | [13 empty] | Sample #1 |  | Sample #2 |  | Sample #3 |  | Sample #4 |  | Sample Averages |  | Sample Avg. 7-Day Entered | Sample Avg. 28-Day Entered
[14 empty] | Compressive Strength |  | Compressive Strength |  | Compressive Strength |  | Compressive Strength |  | Compressive Strength
Month | Pour Date | Pour Location | Structure | Mix # | Design Strength | Yds. Required | Yds. Delivered | Yds. Installed | Yield /Waste | Poured By | Invoice # | Invoice Total | Notes / Arehna Report # | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG
Apr | 2026-04-09 | Temporary Switchboard Pad and Parking Lot Post | Temporary | 1602011 | 4500 | 4 | 4 | 4 | 0% | Garney |  |  | No Samples Taken | NA | NA
Apr | 2026-04-30 | Warehouse Posts | Warehouse | 1602011 | 4500 | 9 | 9 | 9 | 0% | Garney |  |  | AC13445 | 2330 | 4628 | [8 empty] | 2026-06-03
May | 2026-05-14 | Miscellaneous | N/A | 1588170 | 4500 | 3 | 3 | 3 | 0% | Garney |  |  | No Samples Taken | NA | NA
June | 2026-06-04 | Warehouse Posts | Warehouse | 1602011 | 4500 | 3 | 3 | 3 | 0% | Garney | 9453642653 | 655.71 | AC13697 | 2400 | 4372 | [8 empty] | 2026-06-19 | 2026-07-06
June | 2026-06-19 | Cogburn - Control Box Slabs | Site-wide | 1588170 | 4500 | 6 | 6 | 6 | -6% | Garney |  |  | AC13808 | 4150 | 4648 | [8 empty] | 2026-06-29 | 2026-07-20
June | 2026-06-23 | Warehouse Slab | Warehouse | 1602011 | 4500 | 100 | 100 | 100 | 0% | Garney |  |  | AC13825, AC13826 | 3000 | 4177 | 3140 | 5169 | [6 empty] | 2026-06-30
Jul | 2026-07-01 | 30" ML - Trains 1 & 2 Encasements - First 2 trucks | BNR | 1637366 | 4500 | 18 | 18 | 18 | -18% | Garney |  |  | AC13872 | 4780
Jul | 2026-07-01 | 30" ML - Trains 1 & 2 Encasements - Remaining trucks | BNR | 1588170 | 4500 | 6 | 6 | 6 | -21% | Garney |  |  | AC13873 | 2570
Jul | 2026-07-06 | 30" ML - Trains 1 & 2 Encasements - Vertical Tops | BNR | 1588170 | 4500 | 16 | 16 | 16 | 0% | Garney
Jul | 2026-07-09 | 30" ML - Trains 3 & 4 - Mud Mats | BNR | 1519217 | 2500 | 5 | 5 | 5 | 0% | Garney |  |  |  | NA
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Concrete Pour Summary - Subs
0673 OWP AWWTF |  | CIP 10301 | DATE | 2026-08-05 | [7 empty] | Report Overdue
|  |  | Total Est CY | 13006
|  |  | Total CY Placed | 5009.5
Concrete Log | [11 empty] | Sample #1 |  | Sample #2 |  | Sample #3 |  | Sample #4 |  | Sample Averages |  | Sample Avg. 7-Day Entered | Sample Avg. 28-Day Entered
[12 empty] | Compressive Strength |  | Compressive Strength |  | Compressive Strength |  | Compressive Strength |  | Compressive Strength
Month | Pour Date | Pour Location | Structure | Mix # | Design Strength | Yds. Required | Yds. Delivered | Yds. Installed | Yield /Waste | Poured By | Notes / Arehna Report # | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG | 7 - Day AVG | 28 - Day AVG
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13427 | 4113 | 6416.5 | [6 empty] | 4113 | 6416.5 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13428 | 4411 | 6428 | [6 empty] | 4411 | 6428 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13429 | 4676.5 | 6649.5 | [6 empty] | 4676.5 | 6649.5 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13430 | 4886.5 | 6698.5 | [6 empty] | 4886.5 | 6698.5 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13431 | 4593 | 6893.5 | [6 empty] | 4593 | 6893.5 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13432 | 4568 | 7117 | [6 empty] | 4568 | 7117 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13433 | 4032 | 6541.5 | [6 empty] | 4032 | 6541.5 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P356F0480910 | 3500 |  |  |  | 0% | Menard | AC13434 | 4424 | 6604 | [6 empty] | 4424 | 6604 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35GF0450810 | 3500 |  |  |  | 0% | Menard | AC13435 | 4577 | 7705 | [6 empty] | 4577 | 7705 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35GF0450810 | 3500 |  |  |  | 0% | Menard | AC13436 | 5071 | 7783.5 | [6 empty] | 5071 | 7783.5 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35GF0450810 | 3500 |  |  |  | 0% | Menard | AC13437 | 5462 | 8036 | [6 empty] | 5462 | 8036 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35GF0450810 | 3500 |  |  |  | 0% | Menard | AC13438 | 5419 | 7455 | [6 empty] | 5419 | 7455 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35G90500810 | 3500 |  |  |  | 0% | Menard | AC13439 | 4742 | 7611 | [6 empty] | 4742 | 7611 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35G90500810 | 3500 |  |  |  | 0% | Menard | AC13440 | 4712 | 8266 | [6 empty] | 4712 | 8266 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35G90500810 | 3500 |  |  |  | 0% | Menard | AC13441 | 4535 | 5985 | [6 empty] | 4535 | 5985 | 2026-06-19 | 2026-06-19 | 1
Apr | 2026-04-28 | Grout Mix Design Test |  | P35G90500810 | 3500 |  |  |  | 0% | Menard | AC13442 | 4122 | 5367 | [6 empty] | 4122 | 5367 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-08 | CMC Grout | BNR | P35G90500810 | 3500 | 70 |  |  | -70% | Menard | AC13509, AC13510 | 5643 | 8191 | 5359 | 7672 |  |  |  |  | 5501 | 7931.5 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-11 | CMC Grout | BNR | P35G90500810 | 3500 | 90 | 51 | 51 | -39% | Menard | AC13516 | 4783.5 | 7808 | [6 empty] | 4783.5 | 7808 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-11 | Temp Ductbank #1 | Ductbank | SW5A5R10 | 3000 | 20 | 20 | 20 | 0% | Cogburn | AC13521 | 4750 | 5812 | [6 empty] | 4750 | 5812 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-12 | CMC Grout | BNR | P35G90500810 | 3500 | 94.5 | 73.5 | 73.5 | -21% | Menard | AC13522 | 4335 | 7093 | [6 empty] | 4335 | 7093 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-13 | CMC Grout | BNR | P35G90500810 | 3500 | 136.5 | 115.5 | 115.5 | -21% | Menard | AC13544, AC13551 | 4749.5 | 7061 | 4934 | 8441 |  |  |  |  | 4841.75 | 7751 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-14 | CMC Grout | BNR | P35G90500810 | 3500 | 126 | 42 | 42 | -84% | Menard | AC13552 | 5709 | 7629 | [6 empty] | 5709 | 7629 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-15 | CMC Grout | BNR | P35G90500810 | 3500 | 52.5 | 52.5 | 52.5 | 0% | Menard | AC13549, AC13550 | 5275 | 8666 | 5275 | 8228 |  |  |  |  | 5275 | 8447 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-18 | CMC Grout | BNR | P35G90500810 | 3500 | 105 | 73.5 | 73.5 | -31.5% | Menard | AC13557 | 5647 | 8425 | [6 empty] | 5647 | 8425 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-19 | CMC Grout | BNR | P35G90500810 | 3500 | 105 | 105 | 105 | 0% | Menard | AC13569, AC13570 | 5197 | 5978 | 5794 | 7059 |  |  |  |  | 5495.5 | 6518.5 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-19 | Ductbank | Ductbank | SW5A5R10 | 3000 |  |  | 50 | 50% | Cogburn | AC13598 | 3757.5 | 5205 | [6 empty] | 3757.5 | 5205 | 2026-06-19 | 2026-06-19 | 1
May | 2026-05-20 | CMC Grout | BNR | P35G90500810 | 3500 | 105 | 73.5 | 73.5 | -31.5% | Menard | AC13585 | 4853 | 7575 | [6 empty] | 4853 | 7575 | 2026-06-19 | 2026-06-24 | 1
May | 2026-05-21 | CMC Grout | BNR | P35G90500810 | 3500 | 147 | 147 | 147 | 0% | Menard | AC13586, AC13587 | 5556 | 9362 | 5537 | 10006 |  |  |  |  | 5546.5 | 9684 | 2026-06-19 | 2026-06-24 | 1
May | 2026-05-21 | Ductbank | Ductbank | SW5AR10 | 3000 | 40 | 40 | 40 | 0% | Cogburn | AC13599 | 4430 | 5567 | [6 empty] | 4430 | 5567 | 2026-06-19 | 2026-06-25 | 1
May | 2026-05-26 | CMC Grout | BNR | P35G90500810 | 3500 | 115.5 | 115.5 | 115.5 | 0% | Menard | AC13620, AC13621 | 4681 | 7368 | 4773 | 8420 |  |  |  |  | 4727 | 7894 | 2026-06-12 | 2026-06-25 | 1
May | 2026-05-27 | CMC Grout | BNR | P35G90500810 | 3500 | 136.5 | 136.5 | 136.5 | 0% | Menard | AC13626, AC13627 | 4869 | 7724 | 5037 | 9090 |  |  |  |  | 4953 | 8407 | 2026-06-12 | 2026-06-25 | 1
May | 2026-05-28 | CMC Grout | BNR | P35G90500810 | 3500 | 178.8 | 157.5 | 157.5 | -21.3% | Menard | AC13634, AC13635, AC13636 | 3678 | 6515 | 4659 | 8280 | 4652 | 7223 |  |  | 4329.6667 | 7339.3333 | 2026-06-23 | 2026-06-29 | 1
May | 2026-05-29 | CMC Grout | BNR | P35G90500810 | 3500 | 73.5 | 10.5 | 62 | -11.5% | Menard | AC13658 | 4625 | 7512 | [6 empty] | 4625 | 7512 | 2026-06-12 | 2026-06-29 | 1
May | 2026-05-29 | Ductbank | Ductbank | SW5AR10 | 3000 | 29 | 29 | 29 | 0% | Cogburn | AC13668 | 4540 | 5613 | [6 empty] | 4540 | 5613 | 2026-06-19 | 2026-06-29
June | 2026-06-01 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 94.5 | 94.5% | Menard | AC13664 | 4719 | 7227 | [6 empty] | 4719 | 7227 | 2026-06-12 | 2026-07-01
June | 2026-06-02 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 157.5 | 157.5% | Menard | AC13675, AC13676 | 4999 | 7626 | 4472 | 7884 |  |  |  |  | 4735.5 | 7755 | 2026-06-12 | 2026-07-01
June | 2026-06-03 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 168 | 168% | Menard | AC13683, AC13684 | 4739 | 8039 | 4896 | 8018 |  |  |  |  | 4817.5 | 8028.5 | 2026-06-12 | 2026-07-02
June | 2026-06-04 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 178.5 | 178.5% | Menard | AC13695, AC13696 | 5791 | 7735 | 4986 | 8536 |  |  |  |  | 5388.5 | 8135.5 | 2026-06-29 | 2026-07-06
June | 2026-06-05 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 63 | 63% | Menard | AC13717, AC13718 | 5964 | 7463 | 7121 | 9180 |  |  |  |  | 6542.5 | 8321.5 | 2026-06-19 | 2026-07-06
June | 2026-06-08 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 168 | 168% | Menard | AC13715, AC13716 | 5091 | 7918 | 5719 | 8338 |  |  |  |  | 5405 | 8128 | 2026-06-19 | 2026-07-08
June | 2026-06-09 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 168 | 168% | Menard | AC13720, AC13721 | 5142 | 8013 | 4733 | 7398 |  |  |  |  | 4937.5 | 7705.5 | 2026-06-19 | 2026-07-08
June | 2026-06-10 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 136.5 | 136.5% | Menard | AC13730, AC13731 | 5056 | 7272 | 4963 | 7049 |  |  |  |  | 5009.5 | 7160.5 | 2026-06-19 | 2026-07-10
June | 2026-06-11 | Ductbank DB-18 | Ductbank | SW5AR10 | 3000 |  |  | 35.5 | 35.5% | Cogburn | AC13767 | 4650 | 5659 | [6 empty] | 4650 | 5659 | 2026-06-29 | 2026-07-15
June | 2026-06-11 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 126 | 126% | Menard | AC13741, AC13742, AC13743 | 5597 | 8765 | 4621 | 7571 | 5479 | 7589 |  |  | 5232.3333 | 7975 | 2026-06-23 | 2026-07-15
June | 2026-06-12 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 126 | 126% | Menard | AC13753, AC13754 | 6712 | 7541 | 5000 | 6202 |  |  |  |  | 5856 | 6871.5 | 2026-06-23 | 2026-07-15
June | 2026-06-15 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 157.5 | 157.5% | Menard | AC13762, AC13763 | 5779 | 8056 | 5166 | 7665 |  |  |  |  | 5472.5 | 7860.5 | 2026-06-23 | 2026-07-15
June | 2026-06-17 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 157.5 | 157.5% | Menard | AC13779, AC13780 | 5868 | 8173 | 5008 | 6973 |  |  |  |  | 5438 | 7573 | 2026-06-29 | 2026-07-20
June | 2026-06-18 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 126.5 | 126.5% | Menard | AC13803, AC13804 | 5705 | 7233 | 4221 | 6951 |  |  |  |  | 4963 | 7092 | 2026-06-29 | 2026-07-20
June | 2026-06-19 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 105 | 105% | Menard | AC13809, AC13810 | 5984 | 8362 | 6502 | 8264 |  |  |  |  | 6243 | 8313 | 2026-06-29 | 2026-07-20
June | 2026-06-22 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 168 | 168% | Menard | AC13817, AC13818 | 5602 |  | 5052 | [5 empty] | 5327 |  | 2026-07-01
June | 2026-06-24 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 147 | 147% | Menard | AC13833, AC13834 | 4890 |  | 5573 | [5 empty] | 5231.5 |  | 2026-07-01
June | 2026-06-25 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 84 | 84% | Menard | AC13843 | 6071 | [7 empty] | 6071 |  | 2026-07-06
June | 2026-06-26 | Ductbank DB-15 | Ductbank | SW5A5R10 | 3000 |  |  | 6 | 35.5% | Cogburn | AC13857 | 4320 | [7 empty] | 4320 |  | 2026-07-06
June | 2026-06-26 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 147 | 147% | Menard | AC13858, AC13859 | 5031 |  | 5115 | [5 empty] | 5073 |  | 2026-07-06
June | 2026-06-29 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 84 | 84% | Menard | AC13866 | 5160 | [7 empty] | 5160 |  | 2026-07-08
June | 2026-06-30 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 84 | 84% | Menard | AC13868 | 5637 | [7 empty] | 5637 |  | 2026-07-08
June | 2026-06-30 | Ductbank DB-18 | Ductbank | SW5A5R10 | 3000 |  |  |  | 35.5% | Cogburn | AC13869 | 3890 | [7 empty] | 3890 |  | 2026-07-20
July | 2026-07-01 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 157.5 | 157.5% | Menard | AC13870, AC13871 | 4678 |  | 3900 | [5 empty] | 4289 |  | 2026-07-10
July | 2026-07-02 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 96.5 | 96.5% | Menard | AC13883 | 5265 | [7 empty] | 5265 |  | 2026-07-15
July | 2026-07-06 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 126 | 126% | Menard | AC13888, AC13889 | 5458 |  | 4625 | [5 empty] | 5041.5 |  | 2026-07-15
July | 2026-07-07 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 168 | 168% | Menard | AC13898, AC13899 | 4108 |  | 4758 | [7 empty] | 2026-07-15
July | 2026-07-08 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 120 | 120% | Menard | AC13909, AC13910 | 4767 |  | 3920 | [7 empty] | 2026-07-20
July | 2026-07-09 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 115.5 | 115.5% | Menard | AC13920, AC13921 | 3408 |  | 4705 | [7 empty] | 2026-07-20
July | 2026-07-10 | CMC Grout | BNR | P35G90500810 | 3500 |  |  | 147 | 147% | Menard | AC13942, AC13943 | 4318 |  | 4278 | [7 empty] | 2026-07-20
July | 2026-07-10 | Ductbank 11 & 16 | Ductbank | SW5A5R10 | 3000 |  |  | 45 | 45% | Cogburn | AC13926 | 4070 | [7 empty] | 4070 |  | 2026-07-20
July | 2026-07-10 | South Tower Crane Pedestals | BNR | 50JNX72 | 5000 |  |  | 2 | 2% | Baker | AC13927 | 5680 | [7 empty] | 5680 |  | 2026-07-20
July | 2026-07-13 | CMC Grout | BNR | P35G90500810 | 3500 |  |  |  | 0% | Menard | AC13944, AC13945 | 4005 |  | 4797 | [5 empty] | 4401 |  | 2026-07-23
July | 2026-07-14 | CMC Grout | BNR | P35G90500810 | 3500 |  |  |  | 0% | Menard | AC13954 | 4546 | [7 empty] | 4546 |  | 2026-07-23
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Note on B58: Annlera Forsythe: Date was originally 6/23. No production report for that day, only 6/24.

## Weekly Report
helper
0673 OWP AWWTF |  |  | CIP 10301 |  | Week Ending (Friday) | 2026-08-07 | 28-Day Pass | 28-Day Fail |  | 7-Day Results
Weekly Concrete Cylinder Break Report |  |  |  |  | Report Period | 08/01 - 08/07/2026 | 0 | 0 |  | 0
Enter or adjust the Friday date above (H2) to run the report for any week. Showing results entered in the 7 days ending on that date.
7-Day Compressive Strength Results — Entered This Week
Pour Date | Structure | Mix # | Design Strength | Notes / Arehna Report # | 7-Day Result (psi)
28-Day Compressive Strength Results — Entered This Week
Pour Date | Structure | Mix # | Design Strength | Notes / Arehna Report # | 28-Day Result (psi) | Result
Helper — This Week 28-Day Pass/Fail
[11 empty] | Status | Count
[11 empty] | Pass | 0
[11 empty] | Fail | 0
Helper — This Week Avg Strength
[11 empty] | Test Age | Avg Result (psi)
[11 empty] | 7-Day | -
[11 empty] | 28-Day | -

## Trends
0673 OWP AWWTF |  |  | CIP 10301 |  | As of | 2026-08-05
Concrete Break Trends — One Water Campus AWWTF
Total Breaks Logged |  |  | 28-Day Pass Rate |  |  | Avg Margin Above Design |  | 28-Day Fails
41 |  |  | 100% |  |  | 3843.1545 |  | 0
Helper — 28-Day Pass/Fail (Overall)
Status | Count
Pass | 41
Fail | 0
Helper — 28-Day Pass/Fail by Structure
Structure | Pass | Fail
BNR | 21 | 0
Ductbank | 4 | 0
DB-18 | 0 | 0
Mix Design Test | 16 | 0
Helper — 28-Day Strength by Structure (actual structure pours only)
BNR Date | BNR 28-Day (psi) | Ductbank Date | Ductbank 28-Day (psi) | DB-18 Date | DB-18 28-Day (psi) | Design Strength Date | Design Strength (psi)
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
#N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
2026-05-08 | 7931.5 | #N/A | #N/A | #N/A | #N/A | 2026-05-08 | 3500
2026-05-11 | 7808 | #N/A | #N/A | #N/A | #N/A | 2026-05-11 | 3500
#N/A | #N/A | 2026-05-11 | 5812 | #N/A | #N/A | 2026-05-11 | 3000
46154 | 7093 | #N/A | #N/A | #N/A | #N/A | 2026-05-12 | 3500
46155 | 7751 | #N/A | #N/A | #N/A | #N/A | 2026-05-13 | 3500
46156 | 7629 | #N/A | #N/A | #N/A | #N/A | 2026-05-14 | 3500
46157 | 8447 | #N/A | #N/A | #N/A | #N/A | 2026-05-15 | 3500
46160 | 8425 | #N/A | #N/A | #N/A | #N/A | 2026-05-18 | 3500
46161 | 6518.5 | #N/A | #N/A | #N/A | #N/A | 2026-05-19 | 3500
#N/A | #N/A | 46161 | 5205 | #N/A | #N/A | 2026-05-19 | 3000
46162 | 7575 | #N/A | #N/A | #N/A | #N/A | 2026-05-20 | 3500
46163 | 9684 | #N/A | #N/A | #N/A | #N/A | 2026-05-21 | 3500
#N/A | #N/A | 46163 | 5567 | #N/A | #N/A | 2026-05-21 | 3000
46168 | 7894 | #N/A | #N/A | #N/A | #N/A | 2026-05-26 | 3500
46169 | 8407 | #N/A | #N/A | #N/A | #N/A | 2026-05-27 | 3500
46170 | 7339.3333 | #N/A | #N/A | #N/A | #N/A | 2026-05-28 | 3500
46171 | 7512 | #N/A | #N/A | #N/A | #N/A | 2026-05-29 | 3500
#N/A | #N/A | 46171 | 5613 | #N/A | #N/A | 2026-05-29 | 3000
46174 | 7227 | #N/A | #N/A | #N/A | #N/A | 2026-06-01 | 3500
46175 | 7755 | #N/A | #N/A | #N/A | #N/A | 2026-06-02 | 3500
46176 | 8028.5 | #N/A | #N/A | #N/A | #N/A | 2026-06-03 | 3500
46177 | 8135.5 | #N/A | #N/A | #N/A | #N/A | 2026-06-04 | 3500
46178 | 8321.5 | #N/A | #N/A | #N/A | #N/A | 2026-06-05 | 3500
46181 | 8128 | #N/A | #N/A | #N/A | #N/A | 46181 | 3500
46182 | 7705.5 | #N/A | #N/A | #N/A | #N/A | 2026-06-09 | 3500
Helper — Avg Margin Above Design Strength by Structure (psi)
Structure | Avg Margin (psi)
BNR | 4372.1587
Ductbank | 2549.25
-
Helper — Avg 28-Day Strength by Mix #
Mix # | Avg 28-Day (psi) | Design Strength (psi)
P35G90500810 | 7701.7733 | 3500
P35GF0450810 | 7744.875 | 3500
P356F0480910 | 6668.5625 | 3500
SW5A5R10 | 5508.5 | 3000
SW5AR10 | 5590 | 3000

## Pump Truck
Pump Truck Tracking
Date | Pour Location | Truck Size Requested | Truck Size Sent | Hours | Invoice # | Amount | Cubic Yards | $/CY | Date Approved | Notes
2026-04-30 | Warehouse | 28M | 37M | 1.5 |  |  | 9 | 0
2026-06-23 | Warehouse |  |  | 5 |  |  | 100 | 0 |  | 5" boom is checked off (unsure of truck size)
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
[5 empty] | Total $ | 0
[5 empty] | Total CY | 109 | Avg Based on totals: |  | 0

## Concrete Credits
Concrete Credits
Date Received | Amount | Date Approved | Notes

## Mix Designs
Garney - CEMEX
Concrete Class | A | B | D | E | F
Mix Type | Regular | Thick Section | Pea Gravel | Sitework | Lean Concrete
Mix # | 1637295 | 1637294 | 1637366 | 1588170 | 1519217
Type of Work | Roof, Floor Slabs, Walls, Pavements, and other Concrete Items not listed elsewhere | 12-inch and thicker Walls, Slabs on Grade, Mats, Pavements, and Footings | Use where large quantities of structural grout is required - At the Progressive Design-Builder’s option, superplastic Regular Mix may be substituted for the first lift quantities of structural grout is required | Curbs, Gutters, Sidewalks, Catch Basins, Fence embedments, Encasements, and duct banks | Thrist Blocks, Pipe Trench Cut-off Blocks, and Cradles
Compressive Strength, Min 28 Day (PSI) | 4500 psi | 4500 psi | 4500 psi | 4500 psi | 2500 psi
Slump | 6.00 - 9.00 in. | 6.00 - 9.00 in. | 6.00 - 9.00 in. | 6.00 - 9.00 in. | 3.00 - 5.00 in.
Air Allowed | 3.50 - 6.50 % | 3.50 - 6.50 % | 3.50 - 6.50 % | Entrapped | Entrapped
Baker - Quickcrete
Concrete Class | B | B | B | B | C | D
Mix Type |  |  |  |  | 3" Pump Line
Mix # | 45CAG350 | 45CAG350H | 45CAG292A | 45CAG292AH | 50JAG493H | 50SAG406H | 50JNX72
Type of Work | WALLS/FOUNDATIONS | WALLS/FOUNDATIONS | FOUNDATION ALT | FOUNDATION ALT | CONGESTED SECTION |  | TOWER CRANE FND
Compressive Strength, Min 28 Day (PSI) | 4500 psi | 4500 psi | 4500 psi | 4500 psi | 5000 psi | 5000 psi | 5000 psi
Slump | 2.00 - 4.00 in. | 6.00 - 9.00 in. | 2.00 - 4.00 in. | 6.00 - 9.00 in. | 6.00 - 9.00 in. | 6.00 - 9.00 in. | 6.00 - 9.00 in.
Air Allowed | 3.50 - 6.50 % | 3.50 - 6.50 % | 3.50 - 6.50 % | 3.50 - 6.50 % | 3.50 - 6.50 % | 3.50 - 6.50 % | 1.00 - 3.00 %
Menard - Maschmeyer Cocnrete
Concrete Class
Mix Type
Mix # | P35GF0450810 | P35G90500810 | P356F0480910 | P35690520910
Type of Work | - | - | This mix is not recommended for flatwork applications or any structure that is subject to drying shrinkage requirements. | This mix is not recommended for flatwork applications or any structure that is subject to drying shrinkage requirements.
Compressive Strength, Min 28 Day (PSI) | 3500 psi | 3500 psi | 3500 psi | 3500 psi
Slump | 7.00 - 10.00 in. | 7.00 - 10.00 in. | 8.00 - 11.00 in. | 8.00 - 11.00 in.
Air Allowed | 1.50 - 3.00 % | 1.50 - 3.00 % | 1.50 - 3.00 % | 1.50 - 3.00 %
Cogburn - Titan American
Concrete Class
Mix Type
Mix # | SW5A5R10
Type of Work | Cocnrete Duct Bank
Compressive Strength, Min 28 Day (PSI) | 3000 psi
Slump | 4.00 - 6.00 in
Air Allowed | 0 - 6.00 %

## Estimate
Copy and Paste Your Concrete Estimate in this sheet

## Estimate ex
| Estimate for Apopka CMAR - 90% Estimates | [6 empty] | 6 | Form Crew |  | 20 | TOTAL BID | 62912000 |  | TOTAL FEE |  | 6291200 |  | Bid Date: | 2016-10-26
| Division #3 | [6 empty] | 7 | Placing Crew |  | 20 | GC's % | 6.62% | FEE % | 10% | FEE PER MANHOUR |  | 26.779 | Bid Time: | 9:00
| Prepared by: | [6 empty] | 8 | Finish Crew |  | 20 | [8 empty] | BID SUMMARY | BID DETAIL
| Addenda Noted: 0 | [6 empty] | 18 | Rebar |  | 20
[5 empty] | Worksheet Totals | 32720.8 |  |  | 83616.1199 |  |  | 1672112.398 |  | 3163348.667 |  | 911242.55 |  | 319696.5685 |  | 169130 | 6235530.1835 | 7006954.9039
[5 empty] | Filtered Totals | 32720.8 |  |  | 83616.1199 |  |  | 1672112.398 |  | 3163348.667 |  | 911242.55 |  | 319696.5685 |  | 169130 | 6235530.1835 | Package | Structure
Row | Comments | [7 empty] | Total |  | Labor |  | Materials |  | Subcontract |  | Equipment |  | Other |  | Total | Bid Item | Bid Item
# | (Spec/Dwg) |  |  |  | Description | Quantity | Unit | Crew | MH | MH/U | Unit | Total | Unit | Total | Unit | Total | Unit | Total | Unit | Total | Cost | #1 | #2
Division #3
6
6
|  | 034133 - Hollow Core Slabs | [5 empty] | 6
|  |  | West Plant Operations Building |  |  |  |  | 6
|  |  |  | Control and Mechanical Rooms |  |  |  | 6
[5 empty] | 6" Thick Hollow Core Slabs | 827 | SF | 6 | 0 |  | 0 | 0 |  | 0 | 23.35 | 19310.45 |  | 0 |  | 0 | 19310.45 | 4 | 15
[5 empty] | ** THIS SHOULD BE $15/SF BASED ON LAKELAND QUOTE FROM 10/10/16 |  |  | 6
6
|  | 032100 - REINFORCING STEEL (PURCHASE AND INSTALL) | [5 empty] | 6
[5 empty] | ** 2010 we had 1,263 tons @ $727/ton MAT and $222/ton SUB (0.098 tn/cy) |  |  | 6
[5 empty] | ** 11,500 CY AT 30%, USING $850/$450 TN PLUGS |  |  | 6
[5 empty] | ** 12,047 CY AT 60%, USING $700/$550 TN PLUGS |  |  | 6
[5 empty] | ** 12,733 CY AT 90%, USING $700/$550 TN PLUGS |  |  | 6
[5 empty] | 90% TONNAGE BASED ON J.KERR SPREADSHEET |  |  | 6 |  |  |  |  | 743.05
6
[5 empty] | (20-W) ANOXIC BASIN | 129 | TN | 6 | 0 |  | 0 | 0 | 700 | 90300 |  | 0 |  | 0 |  | 0 | 90300
[5 empty] | (20-E) AERATION / ANOXIC TANK | 652 | TN | 6 | 0 |  | 0 | 0 | 700 | 456400 |  | 0 |  | 0 |  | 0 | 456400
[5 empty] | (40-E) CLARIVIER NO. 3 & 4 | 143.5 | TN | 6 | 0 |  | 0 | 0 | 700 | 100450 |  | 0 |  | 0 |  | 0 | 100450
[5 empty] | (50-E) FILTERS / RAPID MIX BASIN | 77 | TN | 6 | 0 |  | 0 | 0 | 700 | 53900 |  | 0 |  | 0 |  | 0 | 53900
[5 empty] | (60-E) C.C TANK / EFF TRANS PUMP STATION | 94 | TN | 6 | 0 |  | 0 | 0 | 700 | 65800 |  | 0 |  | 0 |  | 0 | 65800
[5 empty] | (110-E) AEROBIC DIGESTERS | 250.5 | TN | 6 | 0 |  | 0 | 0 | 700 | 175350 |  | 0 |  | 0 |  | 0 | 175350
[5 empty] | BUILDING PACKAGE "BUILDINGS" | 105.4 | TN | 6 | 0 |  | 0 | 0 | 700 | 73780 |  | 0 |  | 0 |  | 0 | 73780
[5 empty] | EVERYTHING ELSE NOT LISTED ABOVE | 155.3 | TN | 6 | 0 |  | 0 | 0 | 700 | 108710 |  | 0 |  | 0 |  | 0 | 108710
[6 empty] | 1606.7 | TN
6
[5 empty] | CHAIRS & STANDEES @ WALLS & DECKS | 1 | LS | 6 | 0 |  | 0 | 0 | 33000 | 33000 |  | 0 |  | 0 |  | 0 | 33000
6
[5 empty] | (20-W) ANOXIC BASIN | 129 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 70950 |  | 0 |  | 0 | 70950
[5 empty] | (20-E) AERATION / ANOXIC TANK | 652 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 358600 |  | 0 |  | 0 | 358600
[5 empty] | (40-E) CLARIVIER NO. 3 & 4 | 143.5 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 78925 |  | 0 |  | 0 | 78925
[5 empty] | (50-E) FILTERS / RAPID MIX BASIN | 77 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 42350 |  | 0 |  | 0 | 42350
[5 empty] | (60-E) C.C TANK / EFF TRANS PUMP STATION | 94 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 51700 |  | 0 |  | 0 | 51700
[5 empty] | (110-E) AEROBIC DIGESTERS | 250.5 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 137775 |  | 0 |  | 0 | 137775
[5 empty] | BUILDING PACKAGE "BUILDINGS" | 105.4 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 57970 |  | 0 |  | 0 | 57970
[5 empty] | EVERYTHING ELSE NOT LISTED ABOVE | 155.3 | TN | 6 | 0 |  | 0 | 0 |  | 0 | 550 | 85415 |  | 0 |  | 0 | 85415
[6 empty] | 1606.7 | TN
6
6
|  | 033500 - CONCRETE PUMPING | [5 empty] | 6
[5 empty] | **2010, 11,000 CY @ $5/CY PUMPED |  |  | 6
[5 empty] | ** 11,500 CY AT 30%, USING $13/CY |  |  | 6
[5 empty] | ** 12,047 CY AT 60%, USING $13/CY |  |  | 6
[5 empty] | ** 12,733 CY AT 90%, USING $13/CY |  |  | 6
6
[5 empty] | (20-W) ANOXIC BASIN | 1060 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 13780 | 13780
[5 empty] | (20-E) AERATION / ANOXIC TANK | 5090 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 66170 | 66170
[5 empty] | (40-E) CLARIVIER NO. 3 & 4 | 1220 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 15860 | 15860
[5 empty] | (50-E) FILTERS / RAPID MIX BASIN | 451 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 5863 | 5863
[5 empty] | (60-E) C.C TANK / EFF TRANS PUMP STATION | 558 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 7254 | 7254
[5 empty] | (110-E) AEROBIC DIGESTERS | 1747 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 22711 | 22711
[5 empty] | BUILDING PACKAGE "BUILDINGS" | 1054 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 13702 | 13702
[5 empty] | EVERYTHING ELSE NOT LISTED ABOVE | 1553 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 13 | 20189 | 20189
[6 empty] | 12733 | CY
6
6
|  | BID FORM ITEM 5 | [5 empty] | 6
|  |  | CRACK REPAIR AT EQUALIZATION TANK |  |  |  |  | 6
|  |  |  | Less than 0.1-inch (50 LF) |  |  |  | 6
[5 empty] | ROUGH/CLEAN CRACK | 50 | LF | 6 | 2.5 | 0.05 | 1 | 50 | 1 | 50 |  | 0 | 0.1 | 5 |  | 0 | 105 |  | 5
[5 empty] | SET INJECTION PORTS @ 12" | 50 | EA | 6 | 6 | 0.12 | 2.4 | 120 | 0.5 | 25 |  | 0 |  | 0 |  | 0 | 145 |  | 5
[5 empty] | APPLY CRACK SEALANT | 50 | LF | 6 | 2.5 | 0.05 | 1 | 50 | 1 | 50 |  | 0 |  | 0 |  | 0 | 100 |  | 5
[5 empty] | PRESSURE INJECT EPOXY | 50 | LF | 6 | 5 | 0.1 | 2 | 100 | 5.12 | 256 |  | 0 | 0.1 | 5 |  | 0 | 361 |  | 5
[5 empty] | REMOVE/PATCH INJECTION PORTS | 50 | EA | 6 | 1.25 | 0.025 | 0.5 | 25 | 0.01 | 0.5 |  | 0 |  | 0 |  | 0 | 25.5 |  | 5
[5 empty] | SMOOTH SURFACE OF CRACK | 50 | LF | 6 | 2.5 | 0.05 | 1 | 50 |  | 0 |  | 0 | 0.1 | 5 |  | 0 | 55 |  | 5
[8 empty] | 6 | [14 empty] | 5
|  |  |  | Greater than 0.1-inch (50 LF) |  |  |  | 6 | [14 empty] | 5
[5 empty] | SAW/CHIP/CLEAN | 50 | LF | 6 | 5 | 0.1 | 2 | 100 | 0.01 | 0.5 |  | 0 | 0.25 | 12.5 |  | 0 | 113 |  | 5
[5 empty] | EPOXY BOND CONCRETE | 50 | LF | 6 | 5 | 0.1 | 2 | 100 | 0.85 | 42.5 |  | 0 |  | 0 |  | 0 | 142.5 |  | 5
[5 empty] | APPLY POLYURETHANE JOINT SEALANT | 50 | LF | 6 | 5 | 0.1 | 2 | 100 |  | 0 | 5 | 250 |  | 0 |  | 0 | 350 |  | 5
5
|  |  |  | Spall Repair - 4" Deep (20 CY) |  |  |  | 6 | [14 empty] | 5
[5 empty] | SAW/CHIP/CLEAN | 20 | CY | 6 | 405 | 20.25 | 405 | 8100 | 0.27 | 5.4 |  | 0 | 6.75 | 135 |  | 0 | 8240.4 |  | 5
[5 empty] | EPOXY BOND CONCRETE | 1625 | SF | 6 | 81.25 | 0.05 | 1 | 1625 | 0.85 | 1381.25 |  | 0 |  | 0 |  | 0 | 3006.25 |  | 5
[5 empty] | PATCH/REPAIR CONCRETE | 20 | CY | 6 | 540 | 27 | 540 | 10800 | 3942 | 78840 |  | 0 |  | 0 |  | 0 | 89640 |  | 5
[5 empty] | TROWEL FINISH REPAIR | 1625 | SF | 6 | 325 | 0.2 | 4 | 6500 | 0.02 | 32.5 |  | 0 |  | 0 |  | 0 | 6532.5 |  | 5
5
|  | BID FORM ITEM 6 | [5 empty] | 6
|  |  | CRACK REPAIR AT WEST PLANT PROCESS BASINS |  |  |  |  | 6
|  |  |  | Less than 0.1-inch (50 LF) |  |  |  | 6 | [14 empty] | 8
[5 empty] | ROUGH/CLEAN CRACK | 50 | LF | 6 | 2.5 | 0.05 | 1 | 50 | 1 | 50 |  | 0 | 0.1 | 5 |  | 0 | 105 |  | 8
[5 empty] | SET INJECTION PORTS @ 12" | 50 | EA | 6 | 6 | 0.12 | 2.4 | 120 | 0.5 | 25 |  | 0 |  | 0 |  | 0 | 145 |  | 8
[5 empty] | APPLY CRACK SEALANT | 50 | LF | 6 | 2.5 | 0.05 | 1 | 50 | 1 | 50 |  | 0 |  | 0 |  | 0 | 100 |  | 8
[5 empty] | PRESSURE INJECT EPOXY | 50 | LF | 6 | 5 | 0.1 | 2 | 100 | 5.12 | 256 |  | 0 | 0.1 | 5 |  | 0 | 361 |  | 8
[5 empty] | REMOVE/PATCH INJECTION PORTS | 50 | EA | 6 | 1.25 | 0.025 | 0.5 | 25 | 0.01 | 0.5 |  | 0 |  | 0 |  | 0 | 25.5 |  | 8
[5 empty] | SMOOTH SURFACE OF CRACK | 50 | LF | 6 | 2.5 | 0.05 | 1 | 50 |  | 0 |  | 0 | 0.1 | 5 |  | 0 | 55 |  | 8
[8 empty] | 6 | [14 empty] | 8
|  |  |  | Greater than 0.1-inch (50 LF) |  |  |  | 6 | [14 empty] | 8
[5 empty] | SAW/CHIP/CLEAN | 50 | LF | 6 | 5 | 0.1 | 2 | 100 | 0.01 | 0.5 |  | 0 | 0.25 | 12.5 |  | 0 | 113 |  | 8
[5 empty] | EPOXY BOND CONCRETE | 50 | LF | 6 | 5 | 0.1 | 2 | 100 | 0.85 | 42.5 |  | 0 |  | 0 |  | 0 | 142.5 |  | 8
[5 empty] | APPLY POLYURETHANE JOINT SEALANT | 50 | LF | 6 | 5 | 0.1 | 2 | 100 |  | 0 | 5 | 250 |  | 0 |  | 0 | 350 |  | 8
8
|  |  |  | Spall Repair - 4" Deep (20 CY) |  |  |  | 6 | [14 empty] | 8
[5 empty] | SAW/CHIP/CLEAN | 20 | CY | 6 | 405 | 20.25 | 405 | 8100 | 0.27 | 5.4 |  | 0 | 6.75 | 135 |  | 0 | 8240.4 |  | 8
[5 empty] | EPOXY BOND CONCRETE | 1625 | SF | 6 | 81.25 | 0.05 | 1 | 1625 | 0.85 | 1381.25 |  | 0 |  | 0 |  | 0 | 3006.25 |  | 8
[5 empty] | PATCH/REPAIR CONCRETE | 20 | CY | 6 | 540 | 27 | 540 | 10800 | 3942 | 78840 |  | 0 |  | 0 |  | 0 | 89640 |  | 8
[5 empty] | TROWEL FINISH REPAIR | 1625 | SF | 6 | 325 | 0.2 | 4 | 6500 | 0.02 | 32.5 |  | 0 |  | 0 |  | 0 | 6532.5 |  | 8
8
2513 - CONCRETE PAVING
Conc Paving is now shown as 3000 psi
|  |  | West Plant |  |  |  |  | 6
|  |  |  | Paving |  |  |  | 6 | [13 empty] | 1
[5 empty] | HAND PREP SUBGRADE-BUILDING | 2539 | SF | 6 | 40.624 | 0.016 | 0.32 | 812.48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 812.48 | 1 | 2
[5 empty] | POINT & PATCH | 177 | SF | 8 | 5.31 | 0.03 | 0.6 | 106.2 | 0.01 | 1.77 | 0 | 0 | 0 | 0 |  | 0 | 107.97 | 1 | 2
[5 empty] | FINISH CONCRETE | 2539 | SF | 6 | 35.546 | 0.014 | 0.28 | 710.92 | 0.02 | 50.78 | 0 | 0 | 0 | 0 |  | 0 | 761.7 | 1 | 2
[5 empty] | SLAB EDGEFORM | 263 | SF | 6 | 63.12 | 0.24 | 4.8 | 1262.4 | 0.7 | 184.1 | 0 | 0 | 1 | 263 |  | 0 | 1709.5 | 1 | 2
[5 empty] | 1/2" EXPANSION JOINT | 166 | SF | 6 | 14.11 | 0.085 | 1.7 | 282.2 | 1.5 | 249 | 0 | 0 | 0 | 0 |  | 0 | 531.2 | 1 | 2
[5 empty] | 1/2" JOINT SEALANT | 248 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 620 |  | 0 | 620 | 1 | 2
[5 empty] | 8" TYPE 1 CONC PAVING CONTRACTION JT | 135 | LF | 6 | 56.7 | 0.42 | 8.4 | 1134 | 2.87 | 387.45 | 0 | 0 | 0 | 0 |  | 0 | 1521.45 | 1 | 2
[5 empty] | RESTEEL DOBIE SUPPORTS | 2539 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 126.95 | 0 | 0 | 0 | 0 |  | 0 | 126.95 | 1 | 2
[5 empty] | PLACE SLAB ON GRADE | 63 | CY | 6 | 37.8 | 0.6 | 12 | 756 | 0 | 0 |  | 0 |  | 0 |  | 0 | 756 | 1 | 2
[5 empty] | PURCHASE: 4000 PSI CONCRETE @ PAVING | 63 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6930 | 0 | 0 | 0 | 0 |  | 0 | 6930 | 1 | 2
[5 empty] | CONCRETE PUMPING | 63 | CY | 6 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 13 | 819 | 819 | 1 | 2
[5 empty] | PURCHASE / INSTALL REINFORCING STEEL | 3.15 | TN | 6 | 0 | 0 | 0 | 0 | 800 | 2520 | 550 | 1732.5 | 0 | 0 |  | 0 | 4252.5 | 1 | 2
1
|  |  | East Plant |  |  |  |  | 6 | [13 empty] | 1 | 2
|  |  |  | Paving |  |  |  | 6 | [13 empty] | 1 | 2
[5 empty] | HAND PREP SUBGRADE-BUILDING | 8621 | SF | 6 | 137.936 | 0.016 | 0.32 | 2758.72 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2758.72 | 1 | 2
[5 empty] | POINT & PATCH | 650.79 | SF | 8 | 19.5237 | 0.03 | 0.6 | 390.474 | 0.01 | 6.5079 | 0 | 0 | 0 | 0 |  | 0 | 396.9819 | 1 | 2
[5 empty] | FINISH CONCRETE | 8621 | SF | 6 | 120.694 | 0.014 | 0.28 | 2413.88 | 0.02 | 172.42 | 0 | 0 | 0 | 0 |  | 0 | 2586.3 | 1 | 2
[5 empty] | SLAB EDGEFORM | 971.33 | SF | 6 | 233.1192 | 0.24 | 4.8 | 4662.384 | 0.7 | 679.931 | 0 | 0 | 1 | 971.33 |  | 0 | 6313.645 | 1 | 2
[5 empty] | 1/2" EXPANSION JOINT | 450.75 | SF | 6 | 38.3138 | 0.085 | 1.7 | 766.275 | 1.5 | 676.125 | 0 | 0 | 0 | 0 |  | 0 | 1442.4 | 1 | 2
[5 empty] | 1/2" JOINT SEALANT | 671.83 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1679.575 |  | 0 | 1679.575 | 1 | 2
[5 empty] | 8" TYPE 1 CONC PAVING CONTRACTION JT | 872 | LF | 6 | 366.24 | 0.42 | 8.4 | 7324.8 | 2.87 | 2502.64 | 0 | 0 | 0 | 0 |  | 0 | 9827.44 | 1 | 2
[5 empty] | RESTEEL DOBIE SUPPORTS | 8621 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 431.05 | 0 | 0 | 0 | 0 |  | 0 | 431.05 | 1 | 2
[5 empty] | PLACE SLAB ON GRADE | 214 | CY | 6 | 128.4 | 0.6 | 12 | 2568 | 0 | 0 |  | 0 |  | 0 |  | 0 | 2568 | 1 | 2
[5 empty] | PURCHASE: 4000 PSI CONCRETE @ PAVING | 214 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 23540 | 0 | 0 | 0 | 0 |  | 0 | 23540 | 1 | 2
[5 empty] | CONCRETE PUMPING | 214 | CY | 6 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 13 | 2782 | 2782 | 1 | 2
[5 empty] | PURCHASE / INSTALL REINFORCING STEEL | 10.7 | TN | 6 | 0 | 0 | 0 | 0 | 800 | 8560 | 550 | 5885 | 0 | 0 |  | 0 | 14445 | 1 | 2
1
1
|  | 2525 - CONCRETE SIDEWALK (NORMALLY AROUND $5.50 / SF NO BASE) | [5 empty] | 6 | [13 empty] | 1 | 2
[5 empty] | Sidewalk thickness was changed from 6" to 4" in 90pct. CY of concrete has been modified to reflect this change. Sidewalks are now shown as 3000 psi | [16 empty] | 1
|  |  | West Plant |  |  |  |  | 6 | [13 empty] | 1 | 2
|  |  |  | Sidewalk |  | OK |  | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 | 2
[5 empty] | HAND PREP SUBGRADE-SIDEWALKS | 5406.57 | SF | 6 | 108.1314 | 0.02 | 0.4 | 2162.628 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2162.628 | 1 | 2
[5 empty] | FINISH CONCRETE | 5406.57 | SF | 6 | 75.692 | 0.014 | 0.28 | 1513.8396 | 0.02 | 108.1314 | 0 | 0 | 0 | 0 |  | 0 | 1621.971 | 1 | 2
[5 empty] | SIDEWALK EDGEFORM | 1637.17 | SF | 6 | 261.9472 | 0.16 | 3.2 | 5238.944 | 0.716 | 1172.2137 | 0 | 0 | 0 | 0 |  | 0 | 6411.1577 | 1 | 2
[5 empty] | INSTALL EXP JOINT/ SIDEWALK | 342.5 | SF | 6 | 13.7 | 0.04 | 0.8 | 274 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 274 | 1 | 2
[5 empty] | SAW CUT CONCRETE | 1485 | LF | 6 | 178.2 | 0.12 | 2.4 | 3564 | 0.18 | 267.3 | 0 | 0 | 0.75 | 1113.75 |  | 0 | 4945.05 | 1 | 2
[5 empty] | JOINT SEALANT | 685 | LF | 6 | 54.8 | 0.08 | 1.6 | 1096 | 1.5 | 1027.5 | 0 | 0 | 0 | 0 |  | 0 | 2123.5 | 1 | 2
[5 empty] | PURCHASE: 1/2" FIBER EXP JOINT | 342.5 | SF | 6 | 0 | 0 | 0 | 0 | 1 | 342.5 | 0 | 0 | 0 | 0 |  | 0 | 342.5 | 1 | 2
[5 empty] | 6X6-10/10 MESH 21# W1.4XW1.4 | 63.64 | SQS | 6 | 38.184 | 0.6 | 12 | 763.68 | 18 | 1145.52 | 0 | 0 | 0 | 0 |  | 0 | 1909.2 | 1 | 2
[5 empty] | PLACE SIDEWALKS | 67 | CY | 6 | 40.2 | 0.6 | 12 | 804 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 804 | 1 | 2
[5 empty] | PURCHASE: 4000 PSI CONCRETE @ SIDEWALK | 67 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 7370 | 0 | 0 | 0 | 0 |  | 0 | 7370 | 1 | 2
[5 empty] | NO PUMPING ANTICIPATED | [16 empty] | 1
1
|  |  | East Plant |  |  |  |  | 6 | [13 empty] | 1 | 2
|  |  |  | Sidewalk |  | OK |  | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1 | 2
[5 empty] | DETECTABLE WARNING | 6 | EA | 6 | 12 | 2 | 40 | 240 | 150 | 900 | 0 | 0 | 0 | 0 |  | 0 | 1140 | 1 | 2
[5 empty] | HAND PREP SUBGRADE-SIDEWALKS | 4548.7 | SF | 6 | 90.974 | 0.02 | 0.4 | 1819.48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1819.48 | 1 | 2
[5 empty] | FINISH CONCRETE | 4548.7 | SF | 6 | 63.6818 | 0.014 | 0.28 | 1273.636 | 0.02 | 90.974 | 0 | 0 | 0 | 0 |  | 0 | 1364.61 | 1 | 2
[5 empty] | SIDEWALK EDGEFORM | 1383.84 | SF | 6 | 221.4144 | 0.16 | 3.2 | 4428.288 | 0.716 | 990.8294 | 0 | 0 | 0 | 0 |  | 0 | 5419.1174 | 1 | 2
[5 empty] | INSTALL EXP JOINT/ SIDEWALK | 347 | SF | 6 | 13.88 | 0.04 | 0.8 | 277.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 277.6 | 1 | 2
[5 empty] | SAW CUT CONCRETE | 1085 | LF | 6 | 130.2 | 0.12 | 2.4 | 2604 | 0.18 | 195.3 | 0 | 0 | 0.75 | 813.75 |  | 0 | 3613.05 | 1 | 2
[5 empty] | JOINT SEALANT | 694 | LF | 6 | 55.52 | 0.08 | 1.6 | 1110.4 | 1.5 | 1041 | 0 | 0 | 0 | 0 |  | 0 | 2151.4 | 1 | 2
[5 empty] | PURCHASE: 1/2" FIBER EXP JOINT | 347 | SF | 6 | 0 | 0 | 0 | 0 | 1 | 347 | 0 | 0 | 0 | 0 |  | 0 | 347 | 1 | 2
[5 empty] | 6X6-10/10 MESH 21# W1.4XW1.4 | 53.54 | SQS | 6 | 32.124 | 0.6 | 12 | 642.48 | 18 | 963.72 | 0 | 0 | 0 | 0 |  | 0 | 1606.2 | 1 | 2
[5 empty] | PLACE SIDEWALKS | 57 | CY | 6 | 34.2 | 0.6 | 12 | 684 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 684 | 1 | 2
[5 empty] | PURCHASE: 4000 PSI CONCRETE @ SIDEWALK | 57 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6270 | 0 | 0 | 0 | 0 |  | 0 | 6270 | 1 | 2
[5 empty] | NO PUMPING ANTICIPATED | [16 empty] | 1
1
1
|  | 2778 - CURB AND GUTTER | [5 empty] | 6 | [13 empty] | 1 | 2
|  |  | Entire Site |  |  |  |  | 6 | [13 empty] | 1 | 2
|  |  |  | Curb and Gutter - HAVE A QUOTE FOR $67K FOR THIS AMOUNT OF WORK |  |  |  | 6 | [13 empty] | 1 | 2
[5 empty] | * LENGTH OF CURB/GUTTER * | 4486 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 2
[5 empty] | CURB / CURB & GUTTER FINISH | 8972 | SF | 6 | 358.88 | 0.04 | 0.8 | 7177.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7177.6 | 1 | 2
[5 empty] | CURB & GUTTER FORMWORK | 8972 | LF | 6 | 448.6 | 0.05 | 1 | 8972 | 1 | 8972 | 0 | 0 | 0 | 0 |  | 0 | 17944 | 1 | 2
[5 empty] | INSTALL EXP JOINT/ CURB | 2618 | SF | 6 | 104.72 | 0.04 | 0.8 | 2094.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2094.4 | 1 | 2
[5 empty] | SAW CUT CONCRETE | 853 | LF | 6 | 102.36 | 0.12 | 2.4 | 2047.2 | 0.18 | 153.54 | 0 | 0 | 0.75 | 639.75 |  | 0 | 2840.49 | 1 | 2
[5 empty] | JOINT SEALANT | 4188 | LF | 6 | 209.4 | 0.05 | 1 | 4188 | 1.5 | 6282 | 0 | 0 | 0 | 0 |  | 0 | 10470 | 1 | 2
[5 empty] | PURCHASE: 1/2" FIBER EXP JOINT | 2618 | SF | 6 | 0 | 0 | 0 | 0 | 1 | 2618 | 0 | 0 | 0 | 0 |  | 0 | 2618 | 1 | 2
[5 empty] | PLACE CURB / CURB & GUTTER | 247 | CY | 6 | 148.2 | 0.6 | 12 | 2964 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2964 | 1 | 2
[5 empty] | PURCHASE: 3000 PSI CONCRETE @ C&G | 247 | CY | 6 | 0 | 0 | 0 | 0 | 105 | 25935 | 0 | 0 | 0 | 0 |  | 0 | 25935 | 1 | 2
NO REBAR / NO PUMPING REQUIRED
|  | 3300 - CAST-IN-PLACE CONCRETE | [5 empty] | 6
|  |  | CONCRETE MATERIAL (EXLUDING GROUT) |  |  |  |  | 6
[5 empty] | QUANTITY OF CONCRETE | 12338 | CY | 6 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
[5 empty] | CONCRETE WASTE - 3% | 371 | CY | 6 | 0 |  | 0 | 0 | 110 | 40810 |  | 0 |  | 0 |  | 0 | 40810
|  |  | (05-W) Pretreatment No. 1 |  |  |  |  | 6
|  |  |  | Repair Concrete - 2" Deep |  |  |  | 6
[5 empty] | SAW CUT - IN DEMO ESTIMATE | 1 | EA | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 3
[5 empty] | CHIP/CLEAN @ REPAIR | 100 | SF | 6 | 75 | 0.75 | 15 | 1500 | 0.1 | 10 | 0 | 0 | 1 | 100 |  | 0 | 1610 |  | 3
[5 empty] | EPOXY BOND CONCRETE | 100 | SF | 6 | 5 | 0.05 | 1 | 100 | 0.85 | 85 | 0 | 0 | 0 | 0 |  | 0 | 185 |  | 3
[5 empty] | PATCH/REPAIR CONCRETE | 16.7 | CF | 6 | 16.7 | 1 | 20 | 334 | 140 | 2338 | 0 | 0 | 0 | 0 |  | 0 | 2672 |  | 3
[5 empty] | TROWEL FINISH REPAIR | 100 | SF | 6 | 19.6 | 0.196 | 3.92 | 392 | 0.02 | 2 | 0 | 0 | 0 | 0 |  | 0 | 394 |  | 3
|  |  | (10-W) Pretreatment No. 2 |  |  |  |  | 6
|  |  |  | Footings @ EL 102.08 thru 106.58 |  |  |  | 6
[5 empty] | HAND EXCAV COLUMN FTG | 9.9 | CY | 6 | 19.8 | 2 | 40 | 396 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 396 |  | 4
[5 empty] | FINISH TOP FTG/PILE CAP | 809.66 | SF | 8 | 22.6705 | 0.028 | 0.56 | 453.4096 | 0.02 | 16.1932 | 0 | 0 | 0 | 0 |  | 0 | 469.6028 |  | 4
[5 empty] | COLUMN FTG EDGEFORM | 603 | SF | 6 | 144.72 | 0.24 | 4.8 | 2894.4 | 0.45 | 271.35 | 0 | 0 | 1 | 603 |  | 0 | 3768.75 |  | 4
[5 empty] | 12" TYPE 1 FOOTING WALL BASE JT | 19 | LF | 6 | 8.93 | 0.47 | 9.4 | 178.6 | 2.96 | 56.24 | 0 | 0 | 0 | 0 |  | 0 | 234.84 |  | 4
[5 empty] | WALL STARTER FORMS/ FTG | 21.5 | LF | 6 | 8.6 | 0.4 | 8 | 172 | 3 | 64.5 | 0 | 0 | 0 | 0 |  | 0 | 236.5 |  | 4
[5 empty] | KEYWAY/ COLUMN FOOTING | 21.5 | LF | 6 | 1.9995 | 0.093 | 1.86 | 39.99 | 0.375 | 8.0625 | 0 | 0 | 0 | 0 |  | 0 | 48.0525 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 809.66 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 40.483 | 0 | 0 | 0 | 0 |  | 0 | 40.483 |  | 4
[5 empty] | PLACE COLUMN FOOTING | 45 | CY | 7 | 31.5 | 0.7 | 14 | 630 | 0 | 0 |  | 0 |  | 0 |  | 0 | 630 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 45 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4950 | 0 | 0 | 0 | 0 |  | 0 | 4950 |  | 4
|  |  |  | Columns |  |  |  | 6
[5 empty] | POINT & PATCH | 1113.12 | SF | 8 | 33.3936 | 0.03 | 0.6 | 667.872 | 0.01 | 11.1312 | 0 | 0 | 0 | 0 |  | 0 | 679.0032 |  | 4
[5 empty] | RUB CONC COLUMN/PIER | 1113.12 | SF | 6 | 111.312 | 0.1 | 2 | 2226.24 | 0.03 | 33.3936 | 0 | 0 | 0 | 0 |  | 0 | 2259.6336 |  | 4
[5 empty] | COLUMN FORM: 0'-4' PERIM | 150 | SF | 6 | 34.05 | 0.227 | 4.54 | 681 | 0.773 | 115.95 | 0 | 0 | 1 | 150 |  | 0 | 946.95 |  | 4
[5 empty] | COLUMN FORM: 4'-6' PERIM | 963.12 | SF | 6 | 185.8822 | 0.193 | 3.86 | 3717.6432 | 0.773 | 744.4918 | 0 | 0 | 1 | 963.12 |  | 0 | 5425.255 |  | 4
[5 empty] | PLACE COLUMNS | 15 | CY | 6 | 12 | 0.8 | 16 | 240 | 0 | 0 |  | 0 |  | 0 |  | 0 | 240 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 15 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1650 | 0 | 0 | 0 | 0 |  | 0 | 1650 |  | 4
|  |  |  | Foundation Straight Walls |  |  |  | 6
[5 empty] | POINT & PATCH | 1598.61 | SF | 8 | 47.9583 | 0.03 | 0.6 | 959.166 | 0.01 | 15.9861 | 0 | 0 | 0 | 0 |  | 0 | 975.1521 |  | 4
[5 empty] | STANDARD RUB WALLS | 1246 | SF | 6 | 93.45 | 0.075 | 1.5 | 1869 | 0.03 | 37.38 | 0 | 0 | 0 | 0 |  | 0 | 1906.38 |  | 4
[5 empty] | GANG WALLFORM: 12 - 16' | 233.85 | SF | 6 | 25.7235 | 0.11 | 2.2 | 514.47 | 0.55 | 128.6175 | 0 | 0 | 1 | 233.85 |  | 0 | 876.9375 |  | 4
[5 empty] | GANG WALLFORM: 16 - 20' | 397 | SF | 6 | 47.64 | 0.12 | 2.4 | 952.8 | 0.55 | 218.35 | 0 | 0 | 1 | 397 |  | 0 | 1568.15 |  | 4
[5 empty] | GANG WALLFORM: 20+' | 718.76 | SF | 6 | 93.4388 | 0.13 | 2.6 | 1868.776 | 0.55 | 395.318 | 0 | 0 | 1 | 718.76 |  | 0 | 2982.854 |  | 4
[5 empty] | GANG WALL END FORMS | 85.34 | SF | 6 | 24.4926 | 0.287 | 5.74 | 489.8516 | 1.091 | 93.1059 | 0 | 0 | 0 | 0 |  | 0 | 582.9575 |  | 4
[5 empty] | PLACE WALLS | 26 | CY | 6 | 18.2 | 0.7 | 14 | 364 | 0 | 0 |  | 0 |  | 0 |  | 0 | 364 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 26 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2860 | 0 | 0 | 0 | 0 |  | 0 | 2860 |  | 4
|  |  |  | Circular Walls Grit Chamber Foundation Walls - 19' |  |  |  | 6
[5 empty] | POINT & PATCH | 716.28 | SF | 8 | 21.4884 | 0.03 | 0.6 | 429.768 | 0.01 | 7.1628 | 0 | 0 | 0 | 0 |  | 0 | 436.9308 |  | 4
[5 empty] | STANDARD RUB WALLS | 263.89 | SF | 6 | 19.7917 | 0.075 | 1.5 | 395.835 | 0.03 | 7.9167 | 0 | 0 | 0 | 0 |  | 0 | 403.7517 |  | 4
[5 empty] | CIRC GANGFORM: 0 - 10' DIA | 716.28 | SF | 6 | 358.14 | 0.5 | 10 | 7162.8 | 0.55 | 393.954 | 0 | 0 | 2 | 1432.56 |  | 0 | 8989.314 |  | 4
[5 empty] | 12" TYPE 2 CIRC GANG CONST JT | 19 | LF | 6 | 5.51 | 0.29 | 5.8 | 110.2 | 2.76 | 52.44 | 0 | 0 | 0 | 0 |  | 0 | 162.64 |  | 4
[5 empty] | CIR GANG-PIPE PENET 0-12" DIA | 2 | EA | 6 | 2 | 1 | 20 | 40 | 7.5 | 15 | 0 | 0 | 0 | 0 |  | 0 | 55 |  | 4
[5 empty] | PLACE WALLS | 14 | CY | 6 | 9.8 | 0.7 | 14 | 196 | 0 | 0 |  | 0 |  | 0 |  | 0 | 196 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 14 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1540 | 0 | 0 | 0 | 0 |  | 0 | 1540 |  | 4
|  |  |  | Pipe Encasements - 4 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 5.7 | CY | 6 | 11.4 | 2 | 40 | 228 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 228 |  | 4
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 904 | SF | 6 | 108.48 | 0.12 | 2.4 | 2169.6 | 1 | 904 | 0 | 0 | 1 | 904 |  | 0 | 3977.6 |  | 4
[5 empty] | PIPE ENCASE FORMWK - VERT 12' | 80.16 | SF | 6 | 19.2384 | 0.24 | 4.8 | 384.768 | 1 | 80.16 | 0 | 0 | 1 | 80.16 |  | 0 | 545.088 |  | 4
[5 empty] | PIPE ENCASE FORMWK - VERT 2 ' | 36 | SF | 6 | 8.64 | 0.24 | 4.8 | 172.8 | 1 | 36 | 0 | 0 | 1 | 36 |  | 0 | 244.8 |  | 4
[5 empty] | PIPE ENCASE FORMWK - VERT 4.33 | 69.28 | SF | 6 | 16.6272 | 0.24 | 4.8 | 332.544 | 1 | 69.28 | 0 | 0 | 1 | 69.28 |  | 0 | 471.104 |  | 4
[5 empty] | PIPE ENCASE FORMWK - VERT 6 ' | 108 | SF | 6 | 25.92 | 0.24 | 4.8 | 518.4 | 1 | 108 | 0 | 0 | 1 | 108 |  | 0 | 734.4 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 452 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 22.6 | 0 | 0 | 0 | 0 |  | 0 | 22.6 |  | 4
[5 empty] | PLACE PIPE ENCASEMENT | 58 | CY | 6 | 34.8 | 0.6 | 12 | 696 | 0 | 0 |  | 0 |  | 0 |  | 0 | 696 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 58 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6380 | 0 | 0 | 0 | 0 |  | 0 | 6380 |  | 4
|  |  |  | Slab on Grade @ EL 111.25 |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1380 | SF | 6 | 22.08 | 0.016 | 0.32 | 441.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 441.6 |  | 4
[5 empty] | POINT & PATCH | 179 | SF | 8 | 5.37 | 0.03 | 0.6 | 107.4 | 0.01 | 1.79 | 0 | 0 | 0 | 0 |  | 0 | 109.19 |  | 4
[5 empty] | FINISH CONCRETE | 1380 | SF | 6 | 19.32 | 0.014 | 0.28 | 386.4 | 0.02 | 27.6 | 0 | 0 | 0 | 0 |  | 0 | 414 |  | 4
[5 empty] | SLAB EDGEFORM | 179 | SF | 6 | 42.96 | 0.24 | 4.8 | 859.2 | 0.7 | 125.3 | 0 | 0 | 1 | 179 |  | 0 | 1163.5 |  | 4
[5 empty] | 1/2" EXPANSION JOINT | 64 | SF | 6 | 5.44 | 0.085 | 1.7 | 108.8 | 1.5 | 96 | 0 | 0 | 0 | 0 |  | 0 | 204.8 |  | 4
[5 empty] | 1/2" JOINT SEALANT | 95.5 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 238.75 |  | 0 | 238.75 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 1380 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 69 | 0 | 0 | 0 | 0 |  | 0 | 69 |  | 4
[5 empty] | PLACE SLAB ON GRADE | 38 | CY | 6 | 22.8 | 0.6 | 12 | 456 | 0 | 0 |  | 0 |  | 0 |  | 0 | 456 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 38 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4180 | 0 | 0 | 0 | 0 |  | 0 | 4180 |  | 4
|  |  |  | Equipment Pads - 2 EA |  |  |  | 6
[5 empty] | POINT & PATCH CONC PAD | 23 | SF | 8 | 2.001 | 0.087 | 1.74 | 40.02 | 0.01 | 0.23 | 0 | 0 | 0 | 0 |  | 0 | 40.25 |  | 4
[5 empty] | TROWEL FINISH PADS | 14 | SF | 6 | 2.002 | 0.143 | 2.86 | 40.04 | 0.02 | 0.28 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 4
[5 empty] | RUB CONC PAD | 23 | SF | 6 | 2.3 | 0.1 | 2 | 46 | 0.03 | 0.69 | 0 | 0 | 0 | 0 |  | 0 | 46.69 |  | 4
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 14 | SF | 6 | 2.002 | 0.143 | 2.86 | 40.04 | 0.01 | 0.14 | 0 | 0 | 0 | 0 |  | 0 | 40.18 |  | 4
[5 empty] | PAD EDGEFORM | 23 | SF | 6 | 5.52 | 0.24 | 4.8 | 110.4 | 1 | 23 | 0 | 0 | 0 | 0 |  | 0 | 133.4 |  | 4
[5 empty] | SET ANCHOR BOLTS/ PAD | 8 | EA | 6 | 4.8 | 0.6 | 12 | 96 | 1.5 | 12 | 0 | 0 | 0 | 0 |  | 0 | 108 |  | 4
[5 empty] | PLACE PADS | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 4
|  |  |  | Curb @ EL 111.50 |  |  |  | 6
[5 empty] | * LENGTH OF CURB/GUTTER * | 45 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 4
[5 empty] | CURB / CURB & GUTTER FINISH | 30.15 | SF | 6 | 3.5276 | 0.117 | 2.34 | 70.551 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 70.551 |  | 4
[5 empty] | CURB FORMWORK | 90 | LF | 6 | 12.96 | 0.144 | 2.88 | 259.2 | 0.795 | 71.55 | 0 | 0 | 0 | 0 |  | 0 | 330.75 |  | 4
[5 empty] | SAW CUT CONCRETE | 4 | LF | 6 | 2 | 0.5 | 10 | 40 | 0.18 | 0.72 | 0 | 0 | 0.75 | 3 |  | 0 | 43.72 |  | 4
[5 empty] | PLACE CURB / CURB & GUTTER | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 4
[5 empty] | PURCHASE: 3000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 100 | 200 | 0 | 0 | 0 | 0 |  | 0 | 200 |  | 4
|  |  |  | Circular Grit Chamber Elevated Slab @ 125.08 |  |  |  | 6
[5 empty] | POINT & PATCH | 44 | SF | 8 | 1.98 | 0.045 | 0.9 | 39.6 | 0.01 | 0.44 | 0 | 0 | 0 | 0 |  | 0 | 40.04 |  | 4
[5 empty] | FINISH CONCRETE | 154 | SF | 6 | 2.156 | 0.014 | 0.28 | 43.12 | 0.02 | 3.08 | 0 | 0 | 0 | 0 |  | 0 | 46.2 |  | 4
[5 empty] | RUB CONC SUPP SLAB EDGES | 44 | SF | 6 | 4.4 | 0.1 | 2 | 88 | 0.03 | 1.32 | 0 | 0 | 0 | 0 |  | 0 | 89.32 |  | 4
[5 empty] | RUB CONC UNDERSIDE OF SLAB | 154 | SF | 6 | 6.776 | 0.044 | 0.88 | 135.52 | 0.03 | 4.62 | 0 | 0 | 0 | 0 |  | 0 | 140.14 |  | 4
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 154 | SF | 6 | 2.002 | 0.013 | 0.26 | 40.04 | 0.02 | 3.08 | 0 | 0 | 0 | 0 |  | 0 | 43.12 |  | 4
[5 empty] | SUSPENDED SOFFIT FORM: 12- 16' | 154 | SF | 6 | 78.848 | 0.512 | 10.24 | 1576.96 | 1.75 | 269.5 | 0 | 0 | 0.99 | 152.46 |  | 0 | 1998.92 |  | 4
[5 empty] | SUSPENDED SLAB EDGE FORM | 44 | SF | 6 | 9.68 | 0.22 | 4.4 | 193.6 | 1.575 | 69.3 | 0 | 0 | 0 | 0 |  | 0 | 262.9 |  | 4
[5 empty] | 12" TYPE 1 SUSPND SLB WL BS JT | 41 | LF | 6 | 19.27 | 0.47 | 9.4 | 385.4 | 2.96 | 121.36 | 0 | 0 | 0 | 0 |  | 0 | 506.76 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 154 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 7.7 | 0 | 0 | 0 | 0 |  | 0 | 7.7 |  | 4
[5 empty] | PLACE SUSPEND SLAB | 6 | CY | 6 | 6 | 1 | 20 | 120 | 0 | 0 |  | 0 |  | 0 |  | 0 | 120 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 6 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 660 | 0 | 0 | 0 | 0 |  | 0 | 660 |  | 4
|  |  |  | Circular Grit Chamber Walls @ EL 134.08 |  |  |  | 6
[5 empty] | POINT & PATCH | 585.39 | SF | 8 | 17.5617 | 0.03 | 0.6 | 351.234 | 0.01 | 5.8539 | 0 | 0 | 0 | 0 |  | 0 | 357.0879 |  | 4
[5 empty] | STANDARD RUB WALLS | 270 | SF | 6 | 20.25 | 0.075 | 1.5 | 405 | 0.03 | 8.1 | 0 | 0 | 0 | 0 |  | 0 | 413.1 |  | 4
[5 empty] | CIRC WALLFORM: 0 - 4' | 45.39 | SF | 6 | 22.695 | 0.5 | 10 | 453.9 | 0.7 | 31.773 | 0 | 0 | 1 | 45.39 |  | 0 | 531.063 |  | 4
[5 empty] | CIRC WALLFORM: 8 - 12' | 540 | SF | 6 | 270 | 0.5 | 10 | 5400 | 0.7 | 378 | 0 | 0 | 1 | 540 |  | 0 | 6318 |  | 4
[5 empty] | CIRCULAR WALL END FORMS | 18 | SF | 6 | 5.166 | 0.287 | 5.74 | 103.32 | 1.091 | 19.638 | 0 | 0 | 0 | 0 |  | 0 | 122.958 |  | 4
[5 empty] | 12" TYPE 2 CIRC GANG CONST JT | 8.5 | LF | 6 | 2.465 | 0.29 | 5.8 | 49.3 | 2.76 | 23.46 | 0 | 0 | 0 | 0 |  | 0 | 72.76 |  | 4
[5 empty] | SET EMBED ANGLE/ CIRCULAR WALL | 30 | LF | 6 | 6 | 0.2 | 4 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 120 |  | 4
[5 empty] | PLACE WALLS | 11 | CY | 6 | 7.7 | 0.7 | 14 | 154 | 0 | 0 |  | 0 |  | 0 |  | 0 | 154 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 11 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1210 | 0 | 0 | 0 | 0 |  | 0 | 1210 |  | 4
|  |  |  | 12" Circular Grit Chamber Suspended Slab @ 134.08 |  |  |  | 6
[5 empty] | POINT & PATCH | 24 | SF | 8 | 1.992 | 0.083 | 1.66 | 39.84 | 0.01 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 40.08 |  | 4
[5 empty] | FINISH CONCRETE | 36 | SF | 6 | 2.016 | 0.056 | 1.12 | 40.32 | 0.02 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 41.04 |  | 4
[5 empty] | RUB CONC SUPP SLAB EDGES | 24 | SF | 6 | 2.4 | 0.1 | 2 | 48 | 0.03 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 48.72 |  | 4
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 36 | SF | 6 | 2.016 | 0.056 | 1.12 | 40.32 | 0.02 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 41.04 |  | 4
[5 empty] | SUSPENDED SOFFIT FORM: 4 - 8' | 36 | SF | 6 | 6.12 | 0.17 | 3.4 | 122.4 | 1.75 | 63 | 0 | 0 | 0.63 | 22.68 |  | 0 | 208.08 |  | 4
[5 empty] | SUSPENDED SLAB EDGE FORM | 24 | SF | 6 | 5.28 | 0.22 | 4.4 | 105.6 | 1.575 | 37.8 | 0 | 0 | 0 | 0 |  | 0 | 143.4 |  | 4
[5 empty] | SET EMBED ANGLE/ SUSPEND SLAB | 24 | LF | 6 | 4.8 | 0.2 | 4 | 96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 96 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 36 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 1.8 | 0 | 0 | 0 | 0 |  | 0 | 1.8 |  | 4
[5 empty] | PLACE SUSPEND SLAB | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 4
|  |  |  | Intermediate Shored Slab @ EL 120.08 |  |  |  | 6
[5 empty] | POINT & PATCH | 71 | SF | 8 | 2.13 | 0.03 | 0.6 | 42.6 | 0.01 | 0.71 | 0 | 0 | 0 | 0 |  | 0 | 43.31 |  | 4
[5 empty] | FINISH CONCRETE | 355 | SF | 6 | 4.97 | 0.014 | 0.28 | 99.4 | 0.02 | 7.1 | 0 | 0 | 0 | 0 |  | 0 | 106.5 |  | 4
[5 empty] | RUB CONC SUPP SLAB EDGES | 71 | SF | 6 | 7.1 | 0.1 | 2 | 142 | 0.03 | 2.13 | 0 | 0 | 0 | 0 |  | 0 | 144.13 |  | 4
[5 empty] | RUB CONC UNDERSIDE OF SLAB | 355 | SF | 6 | 15.62 | 0.044 | 0.88 | 312.4 | 0.03 | 10.65 | 0 | 0 | 0 | 0 |  | 0 | 323.05 |  | 4
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 355 | SF | 6 | 3.905 | 0.011 | 0.22 | 78.1 | 0.02 | 7.1 | 0 | 0 | 0 | 0 |  | 0 | 85.2 |  | 4
[5 empty] | SHORED SOFFIT FORM: 8 - 12' | 355 | SF | 6 | 177.5 | 0.5 | 10 | 3550 | 2 | 710 | 0 | 0 | 1.125 | 399.375 |  | 0 | 4659.375 |  | 4
[5 empty] | SHORED SLAB EDGE FORM | 71 | SF | 6 | 15.62 | 0.22 | 4.4 | 312.4 | 1.8 | 127.8 | 0 | 0 | 0 | 0 |  | 0 | 440.2 |  | 4
[5 empty] | 12" TYPE 1 SUSPND SLB WL BS JT | 112 | LF | 6 | 52.64 | 0.47 | 9.4 | 1052.8 | 2.96 | 331.52 | 0 | 0 | 0 | 0 |  | 0 | 1384.32 |  | 4
[5 empty] | SHRD SLB-PIPE PENET 13-36" DIA | 3 | EA | 6 | 3 | 1 | 20 | 60 | 22.5 | 67.5 | 0 | 0 | 0 | 0 |  | 0 | 127.5 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 355 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 17.75 | 0 | 0 | 0 | 0 |  | 0 | 17.75 |  | 4
[5 empty] | PLACE SHORED SLAB/BEAM | 14 | CY | 6 | 14 | 1 | 20 | 280 | 0 | 0 |  | 0 |  | 0 |  | 0 | 280 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 14 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1540 | 0 | 0 | 0 | 0 |  | 0 | 1540 |  | 4
|  |  |  | Weir Box Walls |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH | 2833.46 | SF | 8 | 85.0038 | 0.03 | 0.6 | 1700.076 | 0.01 | 28.3346 | 0 | 0 | 0 | 0 |  | 0 | 1728.4106 |  | 4
[5 empty] | STANDARD RUB WALLS | 816 | SF | 6 | 61.2 | 0.075 | 1.5 | 1224 | 0.03 | 24.48 | 0 | 0 | 0 | 0 |  | 0 | 1248.48 |  | 4
[5 empty] | RUB CONC BEAMS | 32 | SF | 6 | 3.2 | 0.1 | 2 | 64 | 0.03 | 0.96 | 0 | 0 | 0 | 0 |  | 0 | 64.96 |  | 4
[5 empty] | FINISH & CURE TOP OF BEAM | 16 | SF | 6 | 2 | 0.125 | 2.5 | 40 | 0.04 | 0.64 | 0 | 0 | 0 | 0 |  | 0 | 40.64 |  | 4
[5 empty] | WALLFORM: 4 - 8' | 547.46 | SF | 6 | 65.6952 | 0.12 | 2.4 | 1313.904 | 0.7 | 383.222 | 0 | 0 | 1 | 547.46 |  | 0 | 2244.586 |  | 4
[5 empty] | WALLFORM: 12 - 16' | 2254 | SF | 6 | 293.02 | 0.13 | 2.6 | 5860.4 | 0.7 | 1577.8 | 0 | 0 | 1 | 2254 |  | 0 | 9692.2 |  | 4
[5 empty] | STRAIGHT WALL END FORMS | 43.67 | SF | 6 | 12.5333 | 0.287 | 5.74 | 250.6658 | 1.091 | 47.644 | 0 | 0 | 0 | 0 |  | 0 | 298.3098 |  | 4
[5 empty] | ISOLATED BEAM SOFFIT: 12 - 16' | 16 | SF | 6 | 12 | 0.75 | 15 | 240 | 2 | 32 | 0 | 0 | 2.6 | 41.6 |  | 0 | 313.6 |  | 4
[5 empty] | ISOLATED BEAM SIDES | 32 | SF | 6 | 9.6 | 0.3 | 6 | 192 | 1.5 | 48 | 0 | 0 | 0 | 0 |  | 0 | 240 |  | 4
[5 empty] | 12" TYPE 2 STRAIT GANG CONST JT | 18 | LF | 6 | 5.22 | 0.29 | 5.8 | 104.4 | 2.76 | 49.68 | 0 | 0 | 0 | 0 |  | 0 | 154.08 |  | 4
[5 empty] | 6"X6" CHAMFER / STR WALL | 16 | LF | 6 | 2 | 0.125 | 2.5 | 40 | 2.25 | 36 | 0 | 0 | 0 | 0 |  | 0 | 76 |  | 4
[5 empty] | SET EMBED ANGLE/ STRAIGHT WALL | 100 | LF | 6 | 20 | 0.2 | 4 | 400 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 400 |  | 4
[5 empty] | SET EMBED ANGLE/ BEAM | 16 | LF | 6 | 3.2 | 0.2 | 4 | 64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 64 |  | 4
[5 empty] | STR WALL-PIPE PENET 13-36" DIA | 1 | EA | 6 | 2 | 2 | 40 | 40 | 22.5 | 22.5 | 0 | 0 | 0 | 0 |  | 0 | 62.5 |  | 4
[5 empty] | PLACE WALLS | 52 | CY | 6 | 36.4 | 0.7 | 14 | 728 | 0 | 0 |  | 0 |  | 0 |  | 0 | 728 |  | 4
[5 empty] | PLACE ISOLATED BEAM | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 53 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 5830 | 0 | 0 | 0 | 0 |  | 0 | 5830 |  | 4
|  |  |  | Intermediate Shored Slab @ EL 128.75 |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH | 126 | SF | 8 | 3.78 | 0.03 | 0.6 | 75.6 | 0.01 | 1.26 | 0 | 0 | 0 | 0 |  | 0 | 76.86 |  | 4
[5 empty] | FINISH CONCRETE | 598 | SF | 6 | 8.372 | 0.014 | 0.28 | 167.44 | 0.02 | 11.96 | 0 | 0 | 0 | 0 |  | 0 | 179.4 |  | 4
[5 empty] | RUB CONC SUPP SLAB EDGES | 126 | SF | 6 | 12.6 | 0.1 | 2 | 252 | 0.03 | 3.78 | 0 | 0 | 0 | 0 |  | 0 | 255.78 |  | 4
[5 empty] | RUB CONC UNDERSIDE OF SLAB | 598 | SF | 6 | 26.312 | 0.044 | 0.88 | 526.24 | 0.03 | 17.94 | 0 | 0 | 0 | 0 |  | 0 | 544.18 |  | 4
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 598 | SF | 6 | 6.578 | 0.011 | 0.22 | 131.56 | 0.02 | 11.96 | 0 | 0 | 0 | 0 |  | 0 | 143.52 |  | 4
[5 empty] | SHORED SOFFIT FORM: 16 - 20' | 598 | SF | 6 | 288.834 | 0.483 | 9.66 | 5776.68 | 2 | 1196 | 0 | 0 | 1.625 | 971.75 |  | 0 | 7944.43 |  | 4
[5 empty] | SHORED SLAB EDGE FORM | 126 | SF | 6 | 27.72 | 0.22 | 4.4 | 554.4 | 1.8 | 226.8 | 0 | 0 | 0 | 0 |  | 0 | 781.2 |  | 4
[5 empty] | FORM GATE BOXOUT/SOG | 20 | LF | 6 | 9 | 0.45 | 9 | 180 | 2.25 | 45 |  | 0 |  | 0 |  | 0 | 225 |  | 4
[5 empty] | 12" TYPE 1 SUSPND SLB WL BS JT | 158 | LF | 6 | 74.26 | 0.47 | 9.4 | 1485.2 | 2.96 | 467.68 | 0 | 0 | 0 | 0 |  | 0 | 1952.88 |  | 4
[5 empty] | 24" TYPE 1 SUSPND SLB WL BS JT | 20 | LF | 6 | 15.6 | 0.78 | 15.6 | 312 | 2.97 | 59.4 | 0 | 0 | 0 | 0 |  | 0 | 371.4 |  | 4
[5 empty] | SHRD SLB-PIPE PENET 13-36" DIA | 4 | EA | 6 | 4 | 1 | 20 | 80 | 22.5 | 90 | 0 | 0 | 0 | 0 |  | 0 | 170 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 598 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 29.9 | 0 | 0 | 0 | 0 |  | 0 | 29.9 |  | 4
[5 empty] | PLACE SHORED SLAB/BEAM | 23 | CY | 6 | 16.1 | 0.7 | 14 | 322 | 0 | 0 |  | 0 |  | 0 |  | 0 | 322 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 23 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2530 | 0 | 0 | 0 | 0 |  | 0 | 2530 |  | 4
|  |  |  | Outer Screen Channel Walls |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH | 1133.07 | SF | 8 | 33.9921 | 0.03 | 0.6 | 679.842 | 0.01 | 11.3307 | 0 | 0 | 0 | 0 |  | 0 | 691.1727 |  | 4
[5 empty] | STANDARD RUB WALLS | 566.54 | SF | 6 | 42.4905 | 0.075 | 1.5 | 849.81 | 0.03 | 16.9962 | 0 | 0 | 0 | 0 |  | 0 | 866.8062 |  | 4
[5 empty] | WALLFORM: 4 - 8' | 1133.07 | SF | 6 | 135.9684 | 0.12 | 2.4 | 2719.368 | 0.7 | 793.149 | 0 | 0 | 1 | 1133.07 |  | 0 | 4645.587 |  | 4
[5 empty] | STRAIGHT WALL END FORMS | 13.33 | SF | 6 | 3.8257 | 0.287 | 5.74 | 76.5142 | 1.091 | 14.543 | 0 | 0 | 0 | 0 |  | 0 | 91.0572 |  | 4
[5 empty] | FORM GATE BOXOUT/GANG | 45 | LF | 6 | 20.25 | 0.45 | 9 | 405 | 2.25 | 101.25 |  | 0 |  | 0 |  | 0 | 506.25 |  | 4
[5 empty] | SET EMBED ANGLE/ STRAIGHT WALL | 74 | LF | 6 | 14.8 | 0.2 | 4 | 296 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 296 |  | 4
[5 empty] | PLACE WALLS | 23 | CY | 6 | 16.1 | 0.7 | 14 | 322 | 0 | 0 |  | 0 |  | 0 |  | 0 | 322 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 23 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2530 | 0 | 0 | 0 | 0 |  | 0 | 2530 |  | 4
|  |  |  | Interior Screen Channel Walls |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH | 511.5 | SF | 8 | 15.345 | 0.03 | 0.6 | 306.9 | 0.01 | 5.115 | 0 | 0 | 0 | 0 |  | 0 | 312.015 |  | 4
[5 empty] | WALLFORM: 0 - 4' | 30 | SF | 6 | 6.6 | 0.22 | 4.4 | 132 | 0.7 | 21 | 0 | 0 | 1 | 30 |  | 0 | 183 |  | 4
[5 empty] | WALLFORM: 4 - 8' | 481.5 | SF | 6 | 57.78 | 0.12 | 2.4 | 1155.6 | 0.7 | 337.05 | 0 | 0 | 1 | 481.5 |  | 0 | 1974.15 |  | 4
[5 empty] | FORM GATE BOXOUT/GANG | 22 | LF | 6 | 9.9 | 0.45 | 9 | 198 | 2.25 | 49.5 |  | 0 |  | 0 |  | 0 | 247.5 |  | 4
[5 empty] | STRAIGHT WALL END FORMS | 18 | SF | 6 | 5.166 | 0.287 | 5.74 | 103.32 | 1.091 | 19.638 | 0 | 0 | 0 | 0 |  | 0 | 122.958 |  | 4
[5 empty] | PLACE WALLS | 12 | CY | 6 | 8.4 | 0.7 | 14 | 168 | 0 | 0 |  | 0 |  | 0 |  | 0 | 168 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 12 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1320 | 0 | 0 | 0 | 0 |  | 0 | 1320 |  | 4
|  |  |  | 10" Shored Slab On Channel Walls @ EL 134.08 |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH | 4.15 | SF | 8 | 2.0003 | 0.482 | 9.64 | 40.006 | 0.01 | 0.0415 | 0 | 0 | 0 | 0 |  | 0 | 40.0475 |  | 4
[5 empty] | FINISH CONCRETE | 226 | SF | 6 | 3.164 | 0.014 | 0.28 | 63.28 | 0.02 | 4.52 | 0 | 0 | 0 | 0 |  | 0 | 67.8 |  | 4
[5 empty] | RUB CONC SUPP SLAB EDGES | 64 | SF | 6 | 6.4 | 0.1 | 2 | 128 | 0.03 | 1.92 | 0 | 0 | 0 | 0 |  | 0 | 129.92 |  | 4
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 226 | SF | 6 | 2.486 | 0.011 | 0.22 | 49.72 | 0.02 | 4.52 | 0 | 0 | 0 | 0 |  | 0 | 54.24 |  | 4
[5 empty] | SHORED SOFFIT FORM: 4 - 8' | 216 | SF | 6 | 94.176 | 0.436 | 8.72 | 1883.52 | 2 | 432 | 0 | 0 | 0.875 | 189 |  | 0 | 2504.52 |  | 4
[5 empty] | SUSPENDED SOFFIT FORM: 4 - 8' | 10 | SF | 6 | 2 | 0.2 | 4 | 40 | 1.75 | 17.5 | 0 | 0 | 0.63 | 6.3 |  | 0 | 63.8 |  | 4
[5 empty] | SUSPENDED SLAB EDGE FORM | 5 | SF | 6 | 2 | 0.4 | 8 | 40 | 1.575 | 7.875 | 0 | 0 | 0 | 0 |  | 0 | 47.875 |  | 4
[5 empty] | SET EMBED ANGLE/ SHORED SLAB | 65 | LF | 6 | 13 | 0.2 | 4 | 260 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 260 |  | 4
[5 empty] | SET EMBED ANGLE/ SUSPEND SLAB | 2.5 | LF | 6 | 2 | 0.8 | 16 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 226 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 11.3 | 0 | 0 | 0 | 0 |  | 0 | 11.3 |  | 4
[5 empty] | PLACE SHORED SLAB/BEAM | 7 | CY | 6 | 7 | 1 | 20 | 140 | 0 | 0 |  | 0 |  | 0 |  | 0 | 140 |  | 4
[5 empty] | PLACE SUSPEND SLAB | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 8 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 880 | 0 | 0 | 0 | 0 |  | 0 | 880 |  | 4
|  |  |  | 10" Northern Shored Slab Suppored by Columns @ EL 134.08 |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH | 109.56 | SF | 8 | 3.2868 | 0.03 | 0.6 | 65.736 | 0.01 | 1.0956 | 0 | 0 | 0 | 0 |  | 0 | 66.8316 |  | 4
[5 empty] | FINISH CONCRETE | 602 | SF | 6 | 8.428 | 0.014 | 0.28 | 168.56 | 0.02 | 12.04 | 0 | 0 | 0 | 0 |  | 0 | 180.6 |  | 4
[5 empty] | RUB CONC SUPP SLAB EDGES | 132 | SF | 6 | 13.2 | 0.1 | 2 | 264 | 0.03 | 3.96 | 0 | 0 | 0 | 0 |  | 0 | 267.96 |  | 4
[5 empty] | RUB CONC UNDERSIDE OF SLAB | 602 | SF | 6 | 26.488 | 0.044 | 0.88 | 529.76 | 0.03 | 18.06 | 0 | 0 | 0 | 0 |  | 0 | 547.82 |  | 4
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 602 | SF | 6 | 6.622 | 0.011 | 0.22 | 132.44 | 0.02 | 12.04 | 0 | 0 | 0 | 0 |  | 0 | 144.48 |  | 4
[5 empty] | SHORED SOFFIT FORM: 20 - +' | 602 | SF | 6 | 382.872 | 0.636 | 12.72 | 7657.44 | 2 | 1204 | 0 | 0 | 1.875 | 1128.75 |  | 0 | 9990.19 |  | 4
[5 empty] | SHORED SLAB EDGE FORM | 132 | SF | 6 | 29.04 | 0.22 | 4.4 | 580.8 | 1.8 | 237.6 | 0 | 0 | 0 | 0 |  | 0 | 818.4 |  | 4
[5 empty] | SET EMBED ANGLE/ SHORED SLAB | 49.5 | LF | 6 | 9.9 | 0.2 | 4 | 198 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 198 |  | 4
[5 empty] | RESTEEL DOBIE SUPPORTS | 602 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 30.1 | 0 | 0 | 0 | 0 |  | 0 | 30.1 |  | 4
[5 empty] | PLACE SHORED SLAB/BEAM | 19 | CY | 6 | 13.3 | 0.7 | 14 | 266 | 0 | 0 |  | 0 |  | 0 |  | 0 | 266 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 19 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2090 | 0 | 0 | 0 | 0 |  | 0 | 2090 |  | 4
|  |  |  | Stair Landings - 1 EA |  |  |  | 6 | [14 empty] | 4
[5 empty] | POINT & PATCH SUPPORTED STAIRS | 19 | SF | 8 | 2.09 | 0.11 | 2.2 | 41.8 | 0.01 | 0.19 | 0 | 0 | 0 | 0 |  | 0 | 41.99 |  | 4
[5 empty] | BROOM FINISH SUPPORTED STAIRS | 21.7 | SF | 6 | 2.17 | 0.1 | 2 | 43.4 | 0.02 | 0.434 | 0 | 0 | 0 | 0 |  | 0 | 43.834 |  | 4
[5 empty] | RUB CONC SUPPORTED STAIRS | 19 | SF | 6 | 2.09 | 0.11 | 2.2 | 41.8 | 0.03 | 0.57 | 0 | 0 | 0 | 0 |  | 0 | 42.37 |  | 4
[5 empty] | SUPPORTED LANDING EDGEFORM | 19 | SF | 6 | 4.56 | 0.24 | 4.8 | 91.2 | 2 | 38 | 0 | 0 | 0 | 0 |  | 0 | 129.2 |  | 4
[5 empty] | PLACE SUPPRTED STAIRS/LANDINGS | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 4
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 4
|  |  |  | Grout |  |  |  | 6 | [14 empty] | 4
[5 empty] | FINISH GROUT - SUMPS/PITS | 125 | SF | 6 | 2 | 0.016 | 0.32 | 40 | 0.02 | 2.5 | 0 | 0 | 0 | 0 |  | 0 | 42.5 |  | 4
[5 empty] | ROUGH/CLEAN NEW CONC | 125 | SF | 6 | 2 | 0.016 | 0.32 | 40 | 0.01 | 1.25 | 0 | 0 | 0 | 0 |  | 0 | 41.25 |  | 4
[5 empty] | PLACE GROUT - SUMPS/PITS | 13 | CY | 6 | 10.4 | 0.8 | 16 | 208 | 0 | 0 |  | 0 |  | 0 |  | 0 | 208 |  | 4
[5 empty] | PURCHASE: 2500 PSI GROUT | 13 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 1495 | 0 | 0 | 0 | 0 |  | 0 | 1495 |  | 4
|  |  | (15-W) Equalization Basin |  |  |  |  | 6
|  |  |  | Pipe Encasements - 2 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 1.22 | CY | 6 | 2.44 | 2 | 40 | 48.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 48.8 |  | 5
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 320 | SF | 6 | 38.4 | 0.12 | 2.4 | 768 | 1 | 320 | 0 | 0 | 1 | 320 |  | 0 | 1408 |  | 5
[5 empty] | RESTEEL DOBIE SUPPORTS | 100 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 5 | 0 | 0 | 0 | 0 |  | 0 | 5 |  | 5
[5 empty] | PLACE PIPE ENCASEMENT | 26 | CY | 6 | 15.6 | 0.6 | 12 | 312 | 0 | 0 |  | 0 |  | 0 |  | 0 | 312 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 26 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2860 | 0 | 0 | 0 | 0 |  | 0 | 2860 |  | 5
5
|  |  |  | Column Pedestals - 9 EA |  |  |  | 6 | [14 empty] | 5
[5 empty] | POINT & PATCH CONC PAD | 144 | SF | 8 | 3.168 | 0.022 | 0.44 | 63.36 | 0.01 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 64.8 |  | 5
[5 empty] | TROWEL FINISH PADS | 144 | SF | 6 | 9.936 | 0.069 | 1.38 | 198.72 | 0.02 | 2.88 | 0 | 0 | 0 | 0 |  | 0 | 201.6 |  | 5
[5 empty] | RUB CONC PAD | 144 | SF | 6 | 14.4 | 0.1 | 2 | 288 | 0.03 | 4.32 | 0 | 0 | 0 | 0 |  | 0 | 292.32 |  | 5
[5 empty] | CLEAN EXIST CONC FOR BOND-PAD | 144 | SF | 6 | 11.952 | 0.083 | 1.66 | 239.04 | 0.075 | 10.8 | 0 | 0 | 0 | 0 |  | 0 | 249.84 |  | 5
[5 empty] | PAD EDGEFORM | 144 | SF | 6 | 34.56 | 0.24 | 4.8 | 691.2 | 1 | 144 | 0 | 0 | 0 | 0 |  | 0 | 835.2 |  | 5
[5 empty] | SET ANCHOR BOLTS/ PAD | 36 | EA | 6 | 21.6 | 0.6 | 12 | 432 | 1.5 | 54 | 0 | 0 | 0 | 0 |  | 0 | 486 |  | 5
[5 empty] | EPOXY BOND CONCRETE - PADS | 144 | SF | 6 | 2.016 | 0.014 | 0.28 | 40.32 | 0.85 | 122.4 | 0 | 0 | 0 | 0 |  | 0 | 162.72 |  | 5
[5 empty] | DRILL/GROUT DOWELS PADS | 36 | EA | 6 | 9 | 0.25 | 5 | 180 | 1.25 | 45 | 0 | 0 | 1.75 | 63 |  | 0 | 288 |  | 5
[5 empty] | PLACE PADS | 6 | CY | 6 | 3.6 | 0.6 | 12 | 72 | 0 | 0 |  | 0 |  | 0 |  | 0 | 72 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 6 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 660 | 0 | 0 | 0 | 0 |  | 0 | 660 |  | 5
5
|  |  |  | Grout Repaired Concrete |  |  |  | 6 | [14 empty] | 5
[5 empty] | FINISH GROUT - TANK BOTTOMS | 5675 | SF | 6 | 170.25 | 0.03 | 0.6 | 3405 | 0.02 | 113.5 | 0 | 0 | 0 | 0 |  | 0 | 3518.5 |  | 5
[5 empty] | CLEAN EXIST CONC FOR BONDING | 5675 | SF | 6 | 96.475 | 0.017 | 0.34 | 1929.5 | 0.08 | 454 | 0 | 0 | 0 | 0 |  | 0 | 2383.5 |  | 5
[5 empty] | PLACE GROUT - TANK BOTTOMS | 42 | CY | 6 | 25.2 | 0.6 | 12 | 504 | 0 | 0 |  | 0 |  | 0 |  | 0 | 504 |  | 5
[5 empty] | PURCHASE: 2500 PSI GROUT | 42 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 4830 | 0 | 0 | 0 | 0 |  | 0 | 4830 |  | 5
5
|  |  |  | Blower Pads - 3 EA |  |  |  | 6 | [14 empty] | 5
[5 empty] | POINT & PATCH CONC PAD | 105.3 | SF | 8 | 2.3166 | 0.022 | 0.44 | 46.332 | 0.01 | 1.053 | 0 | 0 | 0 | 0 |  | 0 | 47.385 |  | 5
[5 empty] | TROWEL FINISH PADS | 150 | SF | 6 | 10.35 | 0.069 | 1.38 | 207 | 0.02 | 3 | 0 | 0 | 0 | 0 |  | 0 | 210 |  | 5
[5 empty] | RUB CONC PAD | 105.3 | SF | 6 | 10.53 | 0.1 | 2 | 210.6 | 0.03 | 3.159 | 0 | 0 | 0 | 0 |  | 0 | 213.759 |  | 5
[5 empty] | PAD EDGEFORM | 105.3 | SF | 6 | 25.272 | 0.24 | 4.8 | 505.44 | 1 | 105.3 | 0 | 0 | 0 | 0 |  | 0 | 610.74 |  | 5
[5 empty] | SET ANCHOR BOLTS/ PAD | 24 | EA | 6 | 14.4 | 0.6 | 12 | 288 | 1.5 | 36 | 0 | 0 | 0 | 0 |  | 0 | 324 |  | 5
[5 empty] | PLACE PADS | 7 | CY | 6 | 4.2 | 0.6 | 12 | 84 | 0 | 0 |  | 0 |  | 0 |  | 0 | 84 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 7 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 770 | 0 | 0 | 0 | 0 |  | 0 | 770 |  | 5
5
|  |  |  | Sump Box Slab |  |  |  | 6 | [14 empty] | 5
[5 empty] | HAND PREP SUBGRADE-BUILDING | 6.25 | SF | 6 | 2 | 0.32 | 6.4 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40 |  | 5
[5 empty] | POINT & PATCH | 10 | SF | 8 | 2 | 0.2 | 4 | 40 | 0.01 | 0.1 | 0 | 0 | 0 | 0 |  | 0 | 40.1 |  | 5
[5 empty] | FINISH CONCRETE | 6.25 | SF | 6 | 2 | 0.32 | 6.4 | 40 | 0.02 | 0.125 | 0 | 0 | 0 | 0 |  | 0 | 40.125 |  | 5
[5 empty] | SLAB EDGEFORM | 10 | SF | 6 | 2.4 | 0.24 | 4.8 | 48 | 0.7 | 7 | 0 | 0 | 1 | 10 |  | 0 | 65 |  | 5
[5 empty] | RESTEEL DOBIE SUPPORTS | 6.25 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 0.3125 | 0 | 0 | 0 | 0 |  | 0 | 0.3125 |  | 5
[5 empty] | PLACE SLAB ON GRADE | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 5
5
|  |  |  | Sump Box Walls |  |  |  | 6 | [14 empty] | 5
[5 empty] | POINT & PATCH | 60 | SF | 8 | 2.28 | 0.038 | 0.76 | 45.6 | 0.01 | 0.6 | 0 | 0 | 0 | 0 |  | 0 | 46.2 |  | 5
[5 empty] | WALLFORM: 0 - 4' | 60 | SF | 6 | 9.6 | 0.16 | 3.2 | 192 | 0.7 | 42 | 0 | 0 | 1 | 60 |  | 0 | 294 |  | 5
[5 empty] | PLACE WALLS | 2 | CY | 6 | 2 | 1 | 20 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 5
5
|  |  |  | 8" Slab on Grade |  |  |  | 6 | [14 empty] | 5
[5 empty] | HAND PREP SUBGRADE-BUILDING | 2398 | SF | 6 | 38.368 | 0.016 | 0.32 | 767.36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 767.36 |  | 5
[5 empty] | POINT & PATCH | 308 | SF | 8 | 9.24 | 0.03 | 0.6 | 184.8 | 0.01 | 3.08 | 0 | 0 | 0 | 0 |  | 0 | 187.88 |  | 5
[5 empty] | FINISH CONCRETE | 2398 | SF | 6 | 33.572 | 0.014 | 0.28 | 671.44 | 0.02 | 47.96 | 0 | 0 | 0 | 0 |  | 0 | 719.4 |  | 5
[5 empty] | SLAB EDGEFORM | 308 | SF | 6 | 73.92 | 0.24 | 4.8 | 1478.4 | 0.7 | 215.6 | 0 | 0 | 1 | 308 |  | 0 | 2002 |  | 5
[5 empty] | FORM SUMP BOXOUT/ S.O.G. | 6.25 | SF | 6 | 3.125 | 0.5 | 10 | 62.5 | 2.25 | 14.0625 | 0 | 0 | 0 | 0 |  | 0 | 76.5625 |  | 5
[5 empty] | RESTEEL DOBIE SUPPORTS | 2398 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 119.9 | 0 | 0 | 0 | 0 |  | 0 | 119.9 |  | 5
[5 empty] | PLACE SLAB ON GRADE | 66 | CY | 6 | 39.6 | 0.6 | 12 | 792 | 0 | 0 |  | 0 |  | 0 |  | 0 | 792 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 66 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 7260 | 0 | 0 | 0 | 0 |  | 0 | 7260 |  | 5
5
|  |  |  | EQ Pump Pads - 6 EA |  |  |  | 6 | [14 empty] | 5
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 144 | SF | 8 | 3.168 | 0.022 | 0.44 | 63.36 | 0.01 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 64.8 |  | 5
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 12 | SF | 6 | 2.004 | 0.167 | 3.34 | 40.08 | 0.02 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 5
[5 empty] | RUB CONC PIPE SUPPORT | 144 | SF | 6 | 14.4 | 0.1 | 2 | 288 | 0.03 | 4.32 | 0 | 0 | 0 | 0 |  | 0 | 292.32 |  | 5
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 12 | SF | 6 | 2.004 | 0.167 | 3.34 | 40.08 | 0.01 | 0.12 | 0 | 0 | 0 | 0 |  | 0 | 40.2 |  | 5
[5 empty] | PIPE SUPPORT FORMWORK | 144 | SF | 6 | 40.32 | 0.28 | 5.6 | 806.4 | 1 | 144 | 0 | 0 | 0 | 0 |  | 0 | 950.4 |  | 5
[5 empty] | SET ANCHOR BOLTS/ PIPE SUPPORT | 18 | EA | 6 | 10.8 | 0.6 | 12 | 216 | 1.5 | 27 | 0 | 0 | 0 | 0 |  | 0 | 243 |  | 5
[5 empty] | PLACE PIPE SUPPORT | 2 | CY | 6 | 2 | 1 | 20 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 5
5
|  |  |  | Pipe Supports - 17 EA |  |  |  | 6 | [14 empty] | 5
[5 empty] | POINT & PATCH | 15.96 | SF | 8 | 1.995 | 0.125 | 2.5 | 39.9 | 0.01 | 0.1596 | 0 | 0 | 0 | 0 |  | 0 | 40.0596 |  | 5
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 224.33 | SF | 8 | 4.9353 | 0.022 | 0.44 | 98.7052 | 0.01 | 2.2433 | 0 | 0 | 0 | 0 |  | 0 | 100.9485 |  | 5
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 24.86 | SF | 6 | 3.0826 | 0.124 | 2.48 | 61.6528 | 0.02 | 0.4972 | 0 | 0 | 0 | 0 |  | 0 | 62.15 |  | 5
[5 empty] | RUB CONC COLUMN/PIER | 15.96 | SF | 6 | 1.995 | 0.125 | 2.5 | 39.9 | 0.03 | 0.4788 | 0 | 0 | 0 | 0 |  | 0 | 40.3788 |  | 5
[5 empty] | RUB CONC PIPE SUPPORT | 224.33 | SF | 6 | 22.433 | 0.1 | 2 | 448.66 | 0.03 | 6.7299 | 0 | 0 | 0 | 0 |  | 0 | 455.3899 |  | 5
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 24.86 | SF | 6 | 1.9888 | 0.08 | 1.6 | 39.776 | 0.01 | 0.2486 | 0 | 0 | 0 | 0 |  | 0 | 40.0246 |  | 5
[5 empty] | PIER FORM: 4'-6' PERIM | 15.96 | SF | 6 | 4.1975 | 0.263 | 5.26 | 83.9496 | 0.818 | 13.0553 | 0 | 0 | 1 | 15.96 |  | 0 | 112.9649 |  | 5
[5 empty] | PIPE SUPPORT FORMWORK | 224.33 | SF | 6 | 62.8124 | 0.28 | 5.6 | 1256.248 | 1 | 224.33 | 0 | 0 | 0 | 0 |  | 0 | 1480.578 |  | 5
[5 empty] | FORM SMALL PIPE SADDLE 1' DIA | 12 | EA | 6 | 12 | 1 | 20 | 240 | 7.5 | 90 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 5
[5 empty] | FORM MEDIUM PIPE SADDLE 2' DIA | 2 | EA | 6 | 4 | 2 | 40 | 80 | 15 | 30 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 5
[5 empty] | SET ANCHOR BOLTS/ PIER | 12 | EA | 6 | 7.2 | 0.6 | 12 | 144 | 1.5 | 18 | 0 | 0 | 0 | 0 |  | 0 | 162 |  | 5
[5 empty] | GROUT BASE PL NON-SHRINK GROUT | 3 | EA | 6 | 3 | 1 | 20 | 60 | 25 | 75 | 0 | 0 | 0 | 0 |  | 0 | 135 |  | 5
[5 empty] | PLACE PIERS | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 5
[5 empty] | PLACE PIPE SUPPORT | 3 | CY | 6 | 2.001 | 0.667 | 13.34 | 40.02 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40.02 |  | 5
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 5
|  |  | (16-W) Blower Station |  |  |  |  | 6
|  |  |  | Repair Concrete - 2" Deep |  |  |  | 6
[5 empty] | CHIP/CLEAN @ REPAIR | 132 | SF | 6 | 99 | 0.75 | 15 | 1980 | 0.1 | 13.2 | 0 | 0 | 1 | 132 |  | 0 | 2125.2 |  | 6
[5 empty] | SAW CUT - IN DEMO ESTIMATE | 1 | EA | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 6
[5 empty] | EPOXY BOND CONCRETE | 132 | SF | 6 | 6.6 | 0.05 | 1 | 132 | 0.85 | 112.2 | 0 | 0 | 0 | 0 |  | 0 | 244.2 |  | 6
[5 empty] | PATCH/REPAIR CONCRETE | 22 | CF | 6 | 22 | 1 | 20 | 440 | 140 | 3080 | 0 | 0 | 0 | 0 |  | 0 | 3520 |  | 6
[5 empty] | TROWEL FINISH REPAIR | 132 | SF | 6 | 25.872 | 0.196 | 3.92 | 517.44 | 0.02 | 2.64 | 0 | 0 | 0 | 0 |  | 0 | 520.08 |  | 6
|  |  | (18-W) Odor Control No. 1 & 2 |  |  |  |  | 6
|  |  |  | 10" Slab on Grade |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1448.06 | SF | 6 | 23.169 | 0.016 | 0.32 | 463.3792 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 463.3792 |  | 7
[5 empty] | POINT & PATCH | 159.23 | SF | 8 | 4.7769 | 0.03 | 0.6 | 95.538 | 0.01 | 1.5923 | 0 | 0 | 0 | 0 |  | 0 | 97.1303 |  | 7
[5 empty] | FINISH CONCRETE | 1448.06 | SF | 6 | 20.2728 | 0.014 | 0.28 | 405.4568 | 0.02 | 28.9612 | 0 | 0 | 0 | 0 |  | 0 | 434.418 |  | 7
[5 empty] | SLAB EDGEFORM | 191.84 | SF | 6 | 46.0416 | 0.24 | 4.8 | 920.832 | 0.7 | 134.288 | 0 | 0 | 1 | 191.84 |  | 0 | 1246.96 |  | 7
[5 empty] | 1/2" EXPANSION JOINT | 28.17 | SF | 6 | 2.3945 | 0.085 | 1.7 | 47.889 | 1.5 | 42.255 |  | 0 |  | 0 |  | 0 | 90.144 |  | 7
[5 empty] | 1/2" JOINT SEALANT | 28.17 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 70.425 |  | 0 |  | 0 | 70.425 |  | 7
[5 empty] | RESTEEL DOBIE SUPPORTS | 1448.06 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 72.403 | 0 | 0 | 0 | 0 |  | 0 | 72.403 |  | 7
[5 empty] | PLACE SLAB ON GRADE | 45 | CY | 6 | 36 | 0.8 | 16 | 720 | 0 | 0 |  | 0 |  | 0 |  | 0 | 720 |  | 7
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 45 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4950 | 0 | 0 | 0 | 0 |  | 0 | 4950 |  | 7
|  |  |  | Equipment Pads - 2 EA |  |  |  | 6 | [14 empty] | 7
[5 empty] | POINT & PATCH CONC PAD | 144.51 | SF | 8 | 26.7343 | 0.185 | 3.7 | 534.687 | 0.01 | 1.4451 | 0 | 0 | 0 | 0 |  | 0 | 536.1321 |  | 7
[5 empty] | TROWEL FINISH PADS | 416.95 | SF | 6 | 43.3628 | 0.104 | 2.08 | 867.256 | 0.02 | 8.339 | 0 | 0 | 0 | 0 |  | 0 | 875.595 |  | 7
[5 empty] | RUB CONC PAD | 144.51 | SF | 6 | 26.7343 | 0.185 | 3.7 | 534.687 | 0.03 | 4.3353 | 0 | 0 | 0 | 0 |  | 0 | 539.0223 |  | 7
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 416.95 | SF | 6 | 43.3628 | 0.104 | 2.08 | 867.256 | 0.01 | 4.1695 | 0 | 0 | 0 | 0 |  | 0 | 871.4255 |  | 7
[5 empty] | PAD EDGEFORM | 205.77 | SF | 6 | 49.3848 | 0.24 | 4.8 | 987.696 | 1 | 205.77 | 0 | 0 | 0 | 0 |  | 0 | 1193.466 |  | 7
[5 empty] | SET ANCHOR BOLTS/ PAD | 20 | EA | 6 | 12 | 0.6 | 12 | 240 | 1.5 | 30 | 0 | 0 | 0 | 0 |  | 0 | 270 |  | 7
[5 empty] | PLACE PADS | 10 | CY | 6 | 20 | 2 | 40 | 400 | 0 | 0 |  | 0 |  | 0 |  | 0 | 400 |  | 7
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 10 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1100 | 0 | 0 | 0 | 0 |  | 0 | 1100 |  | 7
|  |  | (20-W) Anoxic Basin |  |  |  |  | 6
|  |  |  | Pipe Encasements - 2 EA |  |  |  | 6 | [14 empty] | 8
[5 empty] | HAND EXCAV PIPE ENCASE | 0.22 | CY | 6 | 1.9672 | 8.942 | 178.84 | 39.3448 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39.3448 |  | 8
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 36.6 | SF | 6 | 4.392 | 0.12 | 2.4 | 87.84 | 1 | 36.6 | 0 | 0 | 1 | 36.6 |  | 0 | 161.04 |  | 8
[5 empty] | RESTEEL DOBIE SUPPORTS | 18.3 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 0.915 | 0 | 0 | 0 | 0 |  | 0 | 0.915 |  | 8
[5 empty] | PLACE PIPE ENCASEMENT | 2 | CY | 6 | 2 | 1 | 20 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 8
8
|  |  |  | 24" Slab on Grade |  |  |  | 6 | [14 empty] | 8
[5 empty] | HAND PREP SUBGRADE-BUILDING | 6754 | SF | 6 | 108.064 | 0.016 | 0.32 | 2161.28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2161.28 |  | 8
[5 empty] | POINT & PATCH | 692 | SF | 8 | 20.76 | 0.03 | 0.6 | 415.2 | 0.01 | 6.92 | 0 | 0 | 0 | 0 |  | 0 | 422.12 |  | 8
[5 empty] | FINISH CONCRETE | 6754 | SF | 6 | 94.556 | 0.014 | 0.28 | 1891.12 | 0.02 | 135.08 | 0 | 0 | 0 | 0 |  | 0 | 2026.2 |  | 8
[5 empty] | SLAB EDGEFORM | 692 | SF | 6 | 193.76 | 0.28 | 5.6 | 3875.2 | 0.7 | 484.4 | 0 | 0 | 1 | 692 |  | 0 | 5051.6 |  | 8
[5 empty] | 20" TYPE 1 SOG WALL BASE JT | 378 | LF | 6 | 181.44 | 0.48 | 9.6 | 3628.8 | 2.97 | 1122.66 | 0 | 0 | 0 | 0 |  | 0 | 4751.46 |  | 8
[5 empty] | 24" TYPE 2 SOG CONST JT | 326 | LF | 6 | 299.92 | 0.92 | 18.4 | 5998.4 | 4.2 | 1369.2 | 0 | 0 | 2.5 | 815 |  | 0 | 8182.6 |  | 8
[5 empty] | FORM SUMP BOXOUT/ S.O.G. | 40 | SF | 6 | 20 | 0.5 | 10 | 400 | 2.25 | 90 | 0 | 0 | 0 | 0 |  | 0 | 490 |  | 8
[5 empty] | SET EMBED ANGLE/ SLAB ON GRADE | 10 | LF | 6 | 2 | 0.2 | 4 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40 |  | 8
[5 empty] | RESTEEL DOBIE SUPPORTS | 6754 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 337.7 | 0 | 0 | 0 | 0 |  | 0 | 337.7 |  | 8
[5 empty] | PLACE SLAB ON GRADE | 500 | CY | 6 | 300 | 0.6 | 12 | 6000 | 0 | 0 |  | 0 |  | 0 |  | 0 | 6000 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 500 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 55000 | 0 | 0 | 0 | 0 |  | 0 | 55000 |  | 8
8
|  |  |  | Tank Walls |  |  |  | 6 | [14 empty] | 8
[5 empty] | POINT & PATCH | 17075.45 | SF | 8 | 512.2635 | 0.03 | 0.6 | 10245.27 | 0.01 | 170.7545 | 0 | 0 | 0 | 0 |  | 0 | 10416.0245 |  | 8
[5 empty] | STANDARD RUB WALLS | 5270 | SF | 6 | 395.25 | 0.075 | 1.5 | 7905 | 0.03 | 158.1 | 0 | 0 | 0 | 0 |  | 0 | 8063.1 |  | 8
[5 empty] | GANG WALLFORM: 16 - 20' | 16301.45 | SF | 6 | 1630.145 | 0.1 | 2 | 32602.9 | 0.55 | 8965.7975 | 0 | 0 | 1 | 16301.45 |  | 0 | 57870.1475 |  | 8
[5 empty] | GANG WALLFORM: 20+' | 774 | SF | 6 | 85.14 | 0.11 | 2.2 | 1702.8 | 0.55 | 425.7 | 0 | 0 | 1 | 774 |  | 0 | 2902.5 |  | 8
[5 empty] | GANG WALL END FORMS | 39 | SF | 6 | 11.193 | 0.287 | 5.74 | 223.86 | 1.091 | 42.549 | 0 | 0 | 0 | 0 |  | 0 | 266.409 |  | 8
[5 empty] | 12" TYPE 2 GANG WL TO TROUGH SLAB CONST JT | 24 | LF | 6 | 4.08 | 0.17 | 3.4 | 81.6 | 10 | 240 | 0 | 0 | 0 | 0 |  | 0 | 321.6 |  | 8
[5 empty] | 20" TYPE 2 GANG WL CONST JT | 195 | LF | 6 | 195 | 1 | 20 | 3900 | 4.17 | 813.15 | 0 | 0 | 2.5 | 487.5 |  | 0 | 5200.65 |  | 8
[5 empty] | 12" TYPE 2 GANG WL CONST JT | 56 | LF | 6 | 33.04 | 0.59 | 11.8 | 660.8 | 3.16 | 176.96 | 0 | 0 | 2.5 | 140 |  | 0 | 977.76 |  | 8
[5 empty] | 6"X6" CHAMFER / STR WALL | 16 | LF | 6 | 2.08 | 0.13 | 2.6 | 41.6 | 2.25 | 36 | 0 | 0 | 0 | 0 |  | 0 | 77.6 |  | 8
[5 empty] | FORM BOXOUT/ GANG | 66.8 | SF | 6 | 23.38 | 0.35 | 7 | 467.6 | 1.5 | 100.2 | 0 | 0 | 0 | 0 |  | 0 | 567.8 |  | 8
[5 empty] | FORM SLAB SLOT/ GANG | 24 | LF | 6 | 9.6 | 0.4 | 8 | 192 | 2.25 | 54 | 0 | 0 | 0 | 0 |  | 0 | 246 |  | 8
[5 empty] | SET EMBED ANGLE/ GANG | 22 | LF | 6 | 4.4 | 0.2 | 4 | 88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 88 |  | 8
[5 empty] | GANG-PIPE PENET 6" DIA | 2 | EA | 6 | 2 | 1 | 20 | 40 | 7.5 | 15 | 0 | 0 | 0 | 0 |  | 0 | 55 |  | 8
[5 empty] | GANG-PIPE PENET 30" DIA | 2 | EA | 6 | 3 | 1.5 | 30 | 60 | 22.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 105 |  | 8
[5 empty] | PLACE WALLS | 482 | CY | 6 | 337.4 | 0.7 | 14 | 6748 | 0 | 0 |  | 0 |  | 0 |  | 0 | 6748 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 482 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 53020 | 0 | 0 | 0 | 0 |  | 0 | 53020 |  | 8
8
|  |  |  | 16" Walkway Columns 18.5' - 16 EA |  |  |  | 6 | [14 empty] | 8
[5 empty] | POINT & PATCH | 1236.79 | SF | 8 | 37.1037 | 0.03 | 0.6 | 742.074 | 0.01 | 12.3679 | 0 | 0 | 0 | 0 |  | 0 | 754.4419 |  | 8
[5 empty] | SPECIAL CIRC COL FORM 16" DIA | 296 | LF | 6 | 169.016 | 0.571 | 11.42 | 3380.32 | 10 | 2960 | 0 | 0 | 0 | 0 |  | 0 | 6340.32 |  | 8
[5 empty] | PLACE COLUMNS | 16 | CY | 6 | 12.8 | 0.8 | 16 | 256 | 0 | 0 |  | 0 |  | 0 |  | 0 | 256 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 16 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1760 | 0 | 0 | 0 | 0 |  | 0 | 1760 |  | 8
8
|  |  |  | 12" Walkway |  |  |  | 6 | [14 empty] | 8
[5 empty] | POINT & PATCH | 440 | SF | 8 | 13.2 | 0.03 | 0.6 | 264 | 0.01 | 4.4 | 0 | 0 | 0 | 0 |  | 0 | 268.4 |  | 8
[5 empty] | FINISH CONCRETE | 1069 | SF | 6 | 14.966 | 0.014 | 0.28 | 299.32 | 0.02 | 21.38 | 0 | 0 | 0 | 0 |  | 0 | 320.7 |  | 8
[5 empty] | RUB CONC SUPP SLAB EDGES | 440 | SF | 6 | 44 | 0.1 | 2 | 880 | 0.03 | 13.2 | 0 | 0 | 0 | 0 |  | 0 | 893.2 |  | 8
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 1069 | SF | 6 | 11.759 | 0.011 | 0.22 | 235.18 | 0.02 | 21.38 | 0 | 0 | 0 | 0 |  | 0 | 256.56 |  | 8
[5 empty] | WALKWAY/TROUGH SOFFIT: 16- 20' | 1069 | SF | 6 | 581.536 | 0.544 | 10.88 | 11630.72 | 1.5 | 1603.5 | 0 | 0 | 0.975 | 1042.275 |  | 0 | 14276.495 |  | 8
[5 empty] | WALKWAY/TROUGH EDGE FORM | 440 | SF | 6 | 96.36 | 0.219 | 4.38 | 1927.2 | 1.35 | 594 | 0 | 0 | 0 | 0 |  | 0 | 2521.2 |  | 8
[5 empty] | 12" TYPE 2 WKY/TROUGH CONST JT | 24 | LF | 6 | 13.2 | 0.55 | 11 | 264 | 3.19 | 76.56 | 0 | 0 | 2.5 | 60 |  | 0 | 400.56 |  | 8
[5 empty] | FORM BOXOUT/ WALKWAY-TROUGH | 16 | SF | 6 | 4.8 | 0.3 | 6 | 96 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 120 |  | 8
[5 empty] | RESTEEL DOBIE SUPPORTS | 1069 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 53.45 | 0 | 0 | 0 | 0 |  | 0 | 53.45 |  | 8
[5 empty] | PLACE WALKWAY/TROUGH | 40 | CY | 6 | 28 | 0.7 | 14 | 560 | 0 | 0 |  | 0 |  | 0 |  | 0 | 560 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 40 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4400 | 0 | 0 | 0 | 0 |  | 0 | 4400 |  | 8
8
|  |  |  | 12" Trough Columns 9' - 3 EA |  |  |  | 6 | [14 empty] | 8
[5 empty] | POINT & PATCH | 84.82 | SF | 8 | 2.5446 | 0.03 | 0.6 | 50.892 | 0.01 | 0.8482 | 0 | 0 | 0 | 0 |  | 0 | 51.7402 |  | 8
[5 empty] | RUB CONC COLUMN/PIER | 84.82 | SF | 6 | 8.482 | 0.1 | 2 | 169.64 | 0.03 | 2.5446 | 0 | 0 | 0 | 0 |  | 0 | 172.1846 |  | 8
[5 empty] | SPECIAL CIRC COL FORM 12" DIA | 27 | LF | 6 | 13.257 | 0.491 | 9.82 | 265.14 | 7 | 189 | 0 | 0 | 0 | 0 |  | 0 | 454.14 |  | 8
[5 empty] | PLACE COLUMNS | 1 | CY | 6 | 3 | 3 | 60 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 8
8
|  |  |  | 12" Trough Slab |  |  |  | 6 | [14 empty] | 8
[5 empty] | POINT & PATCH | 36 | SF | 8 | 2.016 | 0.056 | 1.12 | 40.32 | 0.01 | 0.36 | 0 | 0 | 0 | 0 |  | 0 | 40.68 |  | 8
[5 empty] | FINISH CONCRETE | 144 | SF | 6 | 2.016 | 0.014 | 0.28 | 40.32 | 0.02 | 2.88 | 0 | 0 | 0 | 0 |  | 0 | 43.2 |  | 8
[5 empty] | RUB CONC SUPP SLAB EDGES | 36 | SF | 6 | 3.6 | 0.1 | 2 | 72 | 0.03 | 1.08 | 0 | 0 | 0 | 0 |  | 0 | 73.08 |  | 8
[5 empty] | RUB CONC UNDERSIDE OF SLAB | 144 | SF | 6 | 6.336 | 0.044 | 0.88 | 126.72 | 0.03 | 4.32 | 0 | 0 | 0 | 0 |  | 0 | 131.04 |  | 8
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 144 | SF | 6 | 2.016 | 0.014 | 0.28 | 40.32 | 0.02 | 2.88 | 0 | 0 | 0 | 0 |  | 0 | 43.2 |  | 8
[5 empty] | WALKWAY/TROUGH SOFFIT: 8 - 12' | 144 | SF | 6 | 30.24 | 0.21 | 4.2 | 604.8 | 1.5 | 216 | 0 | 0 | 0.675 | 97.2 |  | 0 | 918 |  | 8
[5 empty] | WALKWAY/TROUGH EDGE FORM | 36 | SF | 6 | 7.884 | 0.219 | 4.38 | 157.68 | 1.35 | 48.6 | 0 | 0 | 0 | 0 |  | 0 | 206.28 |  | 8
[5 empty] | 12" TYPE 1 WLK/TROUGH WL BS JT | 36 | LF | 6 | 16.92 | 0.47 | 9.4 | 338.4 | 2.96 | 106.56 | 0 | 0 | 0 | 0 |  | 0 | 444.96 |  | 8
[5 empty] | RESTEEL DOBIE SUPPORTS | 144 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 7.2 | 0 | 0 | 0 | 0 |  | 0 | 7.2 |  | 8
[5 empty] | PLACE WALKWAY/TROUGH | 6 | CY | 6 | 6 | 1 | 20 | 120 | 0 | 0 |  | 0 |  | 0 |  | 0 | 120 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 6 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 660 | 0 | 0 | 0 | 0 |  | 0 | 660 |  | 8
8
|  |  |  | 12" Trough Wall |  |  |  | 6 | [14 empty] | 8
[5 empty] | POINT & PATCH | 684 | SF | 8 | 20.52 | 0.03 | 0.6 | 410.4 | 0.01 | 6.84 | 0 | 0 | 0 | 0 |  | 0 | 417.24 |  | 8
[5 empty] | STANDARD RUB WALLS | 342 | SF | 6 | 25.65 | 0.075 | 1.5 | 513 | 0.03 | 10.26 | 0 | 0 | 0 | 0 |  | 0 | 523.26 |  | 8
[5 empty] | WALLFORM: 8 - 12' | 684 | SF | 6 | 82.08 | 0.12 | 2.4 | 1641.6 | 0.7 | 478.8 | 0 | 0 | 1 | 684 |  | 0 | 2804.4 |  | 8
[5 empty] | SET EMBED ANGLE/ STRAIGHT WALL | 30 | LF | 6 | 6 | 0.2 | 4 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 120 |  | 8
[5 empty] | STR WALL-PIPE PENET 13-36" DIA | 3 | EA | 6 | 4.5 | 1.5 | 30 | 90 | 22.5 | 67.5 | 0 | 0 | 0 | 0 |  | 0 | 157.5 |  | 8
[5 empty] | PLACE WALLS | 13 | CY | 6 | 13 | 1 | 20 | 260 | 0 | 0 |  | 0 |  | 0 |  | 0 | 260 |  | 8
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 13 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1430 | 0 | 0 | 0 | 0 |  | 0 | 1430 |  | 8
8
|  |  |  | Grout |  |  |  | 6 | [14 empty] | 8
[5 empty] | FINISH GROUT - SUMPS/PITS | 12.5 | SF | 6 | 2 | 0.16 | 3.2 | 40 | 0.02 | 0.25 | 0 | 0 | 0 | 0 |  | 0 | 40.25 |  | 8
[5 empty] | ROUGH/CLEAN NEW CONC | 12.5 | SF | 6 | 2 | 0.16 | 3.2 | 40 | 0.01 | 0.125 | 0 | 0 | 0 | 0 |  | 0 | 40.125 |  | 8
[5 empty] | PLACE GROUT - SUMPS/PITS | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 8
[5 empty] | PURCHASE: 2500 PSI GROUT | 1 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 115 | 0 | 0 | 0 | 0 |  | 0 | 115 |  | 8
|  |  | (30-W) Aeration Tank Mod. |  |  |  |  | 6
|  |  |  | 10" Walkway |  |  |  | 6
[5 empty] | POINT & PATCH | 110.39 | SF | 8 | 3.3117 | 0.03 | 0.6 | 66.234 | 0.01 | 1.1039 | 0 | 0 | 0 | 0 |  | 0 | 67.3379 |  | 9
[5 empty] | FINISH CONCRETE | 290.5 | SF | 6 | 4.067 | 0.014 | 0.28 | 81.34 | 0.02 | 5.81 | 0 | 0 | 0 | 0 |  | 0 | 87.15 |  | 9
[5 empty] | RUB CONC SUPP SLAB EDGES | 133 | SF | 6 | 13.3 | 0.1 | 2 | 266 | 0.03 | 3.99 | 0 | 0 | 0 | 0 |  | 0 | 269.99 |  | 9
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 290.5 | SF | 6 | 3.1955 | 0.011 | 0.22 | 63.91 | 0.02 | 5.81 | 0 | 0 | 0 | 0 |  | 0 | 69.72 |  | 9
[5 empty] | WALKWAY/TROUGH SOFFIT: 16- 20' | 290.5 | SF | 6 | 123.4625 | 0.425 | 8.5 | 2469.25 | 1.5 | 435.75 | 0 | 0 | 0.975 | 283.2375 |  | 0 | 3188.2375 |  | 9
[5 empty] | WALKWAY/TROUGH EDGE FORM | 133 | SF | 6 | 29.127 | 0.219 | 4.38 | 582.54 | 1.35 | 179.55 | 0 | 0 | 0 | 0 |  | 0 | 762.09 |  | 9
[5 empty] | 1/2" JOINT SEALANT | 25 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 62.5 |  | 0 | 62.5 |  | 9
[5 empty] | 10" NEW WALKWAY TO EXIST JT | 4 | LF | 6 | 2.08 | 0.52 | 10.4 | 41.6 | 7.01 | 28.04 | 0 | 0 | 2.5 | 10 |  | 0 | 79.64 |  | 9
[5 empty] | EXIST WL TO NEW WALKWAY JOINT | 52.5 | LF | 6 | 34.125 | 0.65 | 13 | 682.5 | 8.77 | 460.425 | 0 | 0 | 0 | 0 |  | 0 | 1142.925 |  | 9
[5 empty] | SAW CUT CONCRETE | 25 | LF | 6 | 3 | 0.12 | 2.4 | 60 | 0.18 | 4.5 | 0 | 0 | 0.75 | 18.75 |  | 0 | 83.25 |  | 9
[5 empty] | RESTEEL DOBIE SUPPORTS | 290.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 14.525 | 0 | 0 | 0 | 0 |  | 0 | 14.525 |  | 9
[5 empty] | PLACE WALKWAY/TROUGH | 9 | CY | 6 | 9 | 1 | 20 | 180 | 0 | 0 |  | 0 |  | 0 |  | 0 | 180 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 9 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 990 | 0 | 0 | 0 | 0 |  | 0 | 990 |  | 9
|  |  | (30-W) Internal Recycling P.S. #1 & #2 (D30-102W) |  |  |  |  | 6
|  |  |  | Sump Box Slab |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 18 | SF | 6 | 1.998 | 0.111 | 2.22 | 39.96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39.96 |  | 9
[5 empty] | POINT & PATCH | 24 | SF | 8 | 1.992 | 0.083 | 1.66 | 39.84 | 0.01 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 40.08 |  | 9
[5 empty] | FINISH CONCRETE | 18 | SF | 6 | 1.998 | 0.111 | 2.22 | 39.96 | 0.02 | 0.36 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 9
[5 empty] | SLAB EDGEFORM | 24 | SF | 6 | 5.76 | 0.24 | 4.8 | 115.2 | 0.7 | 16.8 | 0 | 0 | 1 | 24 |  | 0 | 156 |  | 9
[5 empty] | RESTEEL DOBIE SUPPORTS | 18 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 0.9 | 0 | 0 | 0 | 0 |  | 0 | 0.9 |  | 9
[5 empty] | PLACE SLAB ON GRADE | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 9
|  |  |  | Sump Box Walls |  |  |  | 6 | [14 empty] | 9
[5 empty] | POINT & PATCH | 144 | SF | 8 | 4.32 | 0.03 | 0.6 | 86.4 | 0.01 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 87.84 |  | 9
[5 empty] | WALLFORM: 0 - 4' | 144 | SF | 6 | 23.04 | 0.16 | 3.2 | 460.8 | 0.7 | 100.8 | 0 | 0 | 1 | 144 |  | 0 | 705.6 |  | 9
[5 empty] | SET EMBED ANGLE/ STRAIGHT WALL | 24 | LF | 6 | 4.8 | 0.2 | 4 | 96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 96 |  | 9
[5 empty] | PLACE WALLS | 3 | CY | 6 | 3 | 1 | 20 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 9
|  |  |  | 10" Slab on Grade |  |  |  | 6 | [14 empty] | 9
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1772 | SF | 6 | 28.352 | 0.016 | 0.32 | 567.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 567.04 |  | 9
[5 empty] | POINT & PATCH | 302.12 | SF | 8 | 9.0636 | 0.03 | 0.6 | 181.272 | 0.01 | 3.0212 | 0 | 0 | 0 | 0 |  | 0 | 184.2932 |  | 9
[5 empty] | FINISH CONCRETE | 1772 | SF | 6 | 24.808 | 0.014 | 0.28 | 496.16 | 0.02 | 35.44 | 0 | 0 | 0 | 0 |  | 0 | 531.6 |  | 9
[5 empty] | SLAB EDGEFORM | 364 | SF | 6 | 87.36 | 0.24 | 4.8 | 1747.2 | 0.7 | 254.8 | 0 | 0 | 1 | 364 |  | 0 | 2366 |  | 9
[5 empty] | 1/2" JOINT SEALANT | 76 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 190 |  | 0 | 190 |  | 9
[5 empty] | RESTEEL DOBIE SUPPORTS | 1772 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 88.6 | 0 | 0 | 0 | 0 |  | 0 | 88.6 |  | 9
[5 empty] | PLACE SLAB ON GRADE | 55 | CY | 6 | 33 | 0.6 | 12 | 660 | 0 | 0 |  | 0 |  | 0 |  | 0 | 660 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 55 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6050 | 0 | 0 | 0 | 0 |  | 0 | 6050 |  | 9
|  |  |  | Pipe Supports - 8 EA |  |  |  | 6 | [14 empty] | 9
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 418.74 | SF | 8 | 9.2123 | 0.022 | 0.44 | 184.2456 | 0.01 | 4.1874 | 0 | 0 | 0 | 0 |  | 0 | 188.433 |  | 9
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 37.36 | SF | 6 | 4.6326 | 0.124 | 2.48 | 92.6528 | 0.02 | 0.7472 | 0 | 0 | 0 | 0 |  | 0 | 93.4 |  | 9
[5 empty] | RUB CONC PIPE SUPPORT | 418.74 | SF | 6 | 41.874 | 0.1 | 2 | 837.48 | 0.03 | 12.5622 | 0 | 0 | 0 | 0 |  | 0 | 850.0422 |  | 9
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 37.36 | SF | 6 | 2.0174 | 0.054 | 1.08 | 40.3488 | 0.01 | 0.3736 | 0 | 0 | 0 | 0 |  | 0 | 40.7224 |  | 9
[5 empty] | PIPE SUPPORT FORMWORK | 360 | SF | 6 | 100.8 | 0.28 | 5.6 | 2016 | 1 | 360 | 0 | 0 | 0 | 0 |  | 0 | 2376 |  | 9
[5 empty] | PIPE SUPPORT FORMWORK | 58.74 | SF | 6 | 12.3354 | 0.21 | 4.2 | 246.708 | 1 | 58.74 | 0 | 0 | 0 | 0 |  | 0 | 305.448 |  | 9
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 24 | LF | 6 | 11.28 | 0.47 | 9.4 | 225.6 | 2.96 | 71.04 | 0 | 0 | 0 | 0 |  | 0 | 296.64 |  | 9
[5 empty] | 10" TYPE 1 SOG CONTROL JT | 37 | LF | 6 | 20.35 | 0.55 | 11 | 407 | 3.19 | 118.03 | 0 | 0 | 2.5 | 92.5 |  | 0 | 617.53 |  | 9
[5 empty] | FORM MEDIUM PIPE SADDLE 2' DIA | 4 | EA | 6 | 8 | 2 | 40 | 160 | 15 | 60 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 9
[5 empty] | SET ANCHOR BOLTS/ PIPE SUPPORT | 32 | EA | 6 | 19.2 | 0.6 | 12 | 384 | 1.5 | 48 | 0 | 0 | 0 | 0 |  | 0 | 432 |  | 9
[5 empty] | PLACE PIPE SUPPORT | 6 | CY | 6 | 4.8 | 0.8 | 16 | 96 | 0 | 0 |  | 0 |  | 0 |  | 0 | 96 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 6 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 660 | 0 | 0 | 0 | 0 |  | 0 | 660 |  | 9
|  |  | (40-W) Clarifiers No. 1 & 2 |  |  |  |  | 6
|  |  |  | Regrout Slab - 2.5" Thick |  |  |  | 6
[5 empty] | FINISH GROUT - TANK BOTTOMS | 6840 | SF | 6 | 47.88 | 0.007 | 0.14 | 957.6 | 0.02 | 136.8 | 0 | 0 | 0 | 0 |  | 0 | 1094.4 |  | 10
[5 empty] | CLEAN EXIST CONC FOR BONDING | 6840 | SF | 6 | 116.28 | 0.017 | 0.34 | 2325.6 | 0.075 | 513 | 0 | 0 | 0 | 0 |  | 0 | 2838.6 |  | 10
[5 empty] | PLACE GROUTING SCREEDS | 1 | LS | 6 | 80 | 80 | 1600 | 1600 |  | 0 |  | 0 |  | 0 |  | 0 | 1600 |  | 10
[5 empty] | PLACE GROUT - TANK BOTTOMS | 51 | CY | 6 | 35.7 | 0.7 | 14 | 714 | 0 | 0 |  | 0 |  | 0 |  | 0 | 714 |  | 10
[5 empty] | PURCHASE: 2500 PSI GROUT | 51 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 5865 | 0 | 0 | 0 | 0 |  | 0 | 5865 |  | 10
|  |  | (40-W) Scum Pump Station - 2 EA (D100-101W) |  |  |  |  | 6 | [14 empty] | 10
|  |  |  | Slab on Grade |  |  |  | 6 | [14 empty] | 10
[5 empty] | HAND PREP SUBGRADE-BUILDING | 84 | SF | 6 | 2.016 | 0.024 | 0.48 | 40.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 10
[5 empty] | POINT & PATCH | 58 | SF | 8 | 1.972 | 0.034 | 0.68 | 39.44 | 0.01 | 0.58 | 0 | 0 | 0 | 0 |  | 0 | 40.02 |  | 10
[5 empty] | FINISH CONCRETE | 84 | SF | 6 | 2.016 | 0.024 | 0.48 | 40.32 | 0.02 | 1.68 | 0 | 0 | 0 | 0 |  | 0 | 42 |  | 10
[5 empty] | SLAB EDGEFORM | 116 | SF | 6 | 27.84 | 0.24 | 4.8 | 556.8 | 0.7 | 81.2 | 0 | 0 | 1 | 116 |  | 0 | 754 |  | 10
[5 empty] | RESTEEL DOBIE SUPPORTS | 84 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 4.2 | 0 | 0 | 0 | 0 |  | 0 | 4.2 |  | 10
[5 empty] | PLACE SLAB ON GRADE | 4 | CY | 6 | 4 | 1 | 20 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 10
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 10
|  |  |  | Pipe Supports - 2 EA |  |  |  | 6 | [14 empty] | 10
[5 empty] | POINT & PATCH | 10.64 | SF | 8 | 2.0003 | 0.188 | 3.76 | 40.0064 | 0.01 | 0.1064 | 0 | 0 | 0 | 0 |  | 0 | 40.1128 |  | 10
[5 empty] | RUB CONC COLUMN/PIER | 10.64 | SF | 6 | 2.0003 | 0.188 | 3.76 | 40.0064 | 0.03 | 0.3192 | 0 | 0 | 0 | 0 |  | 0 | 40.3256 |  | 10
[5 empty] | PIER FORM: 4'-6' PERIM | 10.64 | SF | 6 | 2.7983 | 0.263 | 5.26 | 55.9664 | 0.818 | 8.7035 | 0 | 0 | 1 | 10.64 |  | 0 | 75.3099 |  | 10
[5 empty] | SET ANCHOR BOLTS/ PIER | 8 | EA | 6 | 4.8 | 0.6 | 12 | 96 | 1.5 | 12 | 0 | 0 | 0 | 0 |  | 0 | 108 |  | 10
[5 empty] | GROUT BASE PL NON-SHRINK GROUT | 2 | EA | 6 | 2 | 1 | 20 | 40 | 25 | 50 | 0 | 0 | 0 | 0 |  | 0 | 90 |  | 10
[5 empty] | PLACE PIERS | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 10
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 10
|  |  | (100W) RAS/WAS Pump Station |  |  |  |  | 6
|  |  |  | 8" Slab on Grade |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 324 | SF | 6 | 5.184 | 0.016 | 0.32 | 103.68 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 103.68 |  | 11
[5 empty] | POINT & PATCH | 85.5 | SF | 8 | 2.565 | 0.03 | 0.6 | 51.3 | 0.01 | 0.855 | 0 | 0 | 0 | 0 |  | 0 | 52.155 |  | 11
[5 empty] | FINISH CONCRETE | 324 | SF | 6 | 4.536 | 0.014 | 0.28 | 90.72 | 0.02 | 6.48 | 0 | 0 | 0 | 0 |  | 0 | 97.2 |  | 11
[5 empty] | SLAB EDGEFORM | 100 | SF | 6 | 24 | 0.24 | 4.8 | 480 | 0.7 | 70 | 0 | 0 | 1 | 100 |  | 0 | 650 |  | 11
[5 empty] | 1/2" JOINT SEALANT | 4 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 10 |  | 0 | 10 |  | 11
[5 empty] | SAW CUT CONCRETE | 4 | LF | 6 | 2 | 0.5 | 10 | 40 | 0.18 | 0.72 | 0 | 0 | 0.75 | 3 |  | 0 | 43.72 |  | 11
[5 empty] | RESTEEL DOBIE SUPPORTS | 324 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 16.2 | 0 | 0 | 0 | 0 |  | 0 | 16.2 |  | 11
[5 empty] | PLACE SLAB ON GRADE | 10 | CY | 6 | 7 | 0.7 | 14 | 140 | 0 | 0 |  | 0 |  | 0 |  | 0 | 140 |  | 11
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 10 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1100 | 0 | 0 | 0 | 0 |  | 0 | 1100 |  | 11
|  |  |  | Equipment Pads - 2 EA |  |  |  | 6 | [14 empty] | 11
[5 empty] | POINT & PATCH CONC PAD | 24 | SF | 8 | 1.992 | 0.083 | 1.66 | 39.84 | 0.01 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 40.08 |  | 11
[5 empty] | TROWEL FINISH PADS | 18 | SF | 6 | 1.998 | 0.111 | 2.22 | 39.96 | 0.02 | 0.36 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 11
[5 empty] | RUB CONC PAD | 24 | SF | 6 | 2.4 | 0.1 | 2 | 48 | 0.03 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 48.72 |  | 11
[5 empty] | PAD EDGEFORM | 24 | SF | 6 | 5.76 | 0.24 | 4.8 | 115.2 | 1 | 24 | 0 | 0 | 0 | 0 |  | 0 | 139.2 |  | 11
[5 empty] | SET ANCHOR BOLTS/ PAD | 8 | EA | 6 | 4.8 | 0.6 | 12 | 96 | 1.5 | 12 | 0 | 0 | 0 | 0 |  | 0 | 108 |  | 11
[5 empty] | PLACE PADS | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 11
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 11
|  |  | (105-W) Sludge Holding Tank |  |  |  |  | 6
|  |  |  | Repair Concrete - 2" Deep |  |  |  | 6 | [14 empty] | 11
[5 empty] | CHIP/CLEAN @ REPAIR | 72 | SF | 6 | 54 | 0.75 | 15 | 1080 | 0.1 | 7.2 | 0 | 0 | 1 | 72 |  | 0 | 1159.2 |  | 11
[5 empty] | EPOXY BOND CONCRETE | 72 | SF | 6 | 3.6 | 0.05 | 1 | 72 | 0.85 | 61.2 | 0 | 0 | 0 | 0 |  | 0 | 133.2 |  | 11
[5 empty] | PATCH/REPAIR CONCRETE | 12 | CF | 6 | 12 | 1 | 20 | 240 | 140 | 1680 | 0 | 0 | 0 | 0 |  | 0 | 1920 |  | 11
[5 empty] | TROWEL FINISH REPAIR | 72 | SF | 6 | 14.112 | 0.196 | 3.92 | 282.24 | 0.02 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 283.68 |  | 11
11
|  |  | (120-W) Generator / MCC Building |  |  |  |  | 6
|  |  |  | 12" Continuous Footing |  |  |  | 6
[5 empty] | HAND EXCAV CONTINUOUS FTG | 5.62 | CY | 6 | 11.24 | 2 | 40 | 224.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 224.8 |  | 13
[5 empty] | FINISH TOP FTG/PILE CAP | 459.99 | SF | 6 | 12.8797 | 0.028 | 0.56 | 257.5944 | 0.02 | 9.1998 | 0 | 0 | 0 | 0 |  | 0 | 266.7942 |  | 13
[5 empty] | CONTINUOUS FTG EDGEFORM | 306.66 | SF | 6 | 73.5984 | 0.24 | 4.8 | 1471.968 | 0.45 | 137.997 | 0 | 0 | 1 | 306.66 |  | 0 | 1916.625 |  | 13
[5 empty] | RESTEEL DOBIE SUPPORTS | 459.99 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 22.9995 | 0 | 0 | 0 | 0 |  | 0 | 22.9995 |  | 13
[5 empty] | PLACE CONTINUOUS FOOTING | 18 | CY | 6 | 14.4 | 0.8 | 16 | 288 | 0 | 0 |  | 0 |  | 0 |  | 0 | 288 |  | 13
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 18 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1980 | 0 | 0 | 0 | 0 |  | 0 | 1980 |  | 13
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 13
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1185.75 | SF | 6 | 18.972 | 0.016 | 0.32 | 379.44 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 379.44 |  | 13
[5 empty] | POINT & PATCH | 144 | SF | 8 | 4.32 | 0.03 | 0.6 | 86.4 | 0.01 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 87.84 |  | 13
[5 empty] | FINISH CONCRETE | 1185.75 | SF | 6 | 16.6005 | 0.014 | 0.28 | 332.01 | 0.02 | 23.715 | 0 | 0 | 0 | 0 |  | 0 | 355.725 |  | 13
[5 empty] | SLAB EDGEFORM | 12 | SF | 6 | 2.88 | 0.24 | 4.8 | 57.6 | 0.7 | 8.4 | 0 | 0 | 1 | 12 |  | 0 | 78 |  | 13
[5 empty] | ZIP STRIP | 142 | LF | 6 | 4.118 | 0.029 | 0.58 | 82.36 | 1.125 | 159.75 |  | 0 |  | 0 |  | 0 | 242.11 |  | 13
[5 empty] | 1/2" EXPANSION JOINT | 142 | SF | 6 | 12.07 | 0.085 | 1.7 | 241.4 | 1.5 | 213 | 0 | 0 | 0 | 0 |  | 0 | 454.4 |  | 13
[5 empty] | 1/2" JOINT SEALANT | 167 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 417.5 |  | 0 | 417.5 |  | 13
[5 empty] | 10 MIL VISQUEEN | 13.04 | SQS | 6 | 2.9862 | 0.229 | 4.58 | 59.7232 | 30 | 391.2 | 0 | 0 | 0 | 0 |  | 0 | 450.9232 |  | 13
[5 empty] | SAW CUT CONCRETE | 25 | LF | 6 | 3 | 0.12 | 2.4 | 60 | 0.18 | 4.5 | 0 | 0 | 0.75 | 18.75 |  | 0 | 83.25 |  | 13
[5 empty] | RESTEEL DOBIE SUPPORTS | 1185.75 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 59.2875 | 0 | 0 | 0 | 0 |  | 0 | 59.2875 |  | 13
[5 empty] | PLACE SLAB ON GRADE | 26 | CY | 6 | 15.6 | 0.6 | 12 | 312 | 0 | 0 |  | 0 |  | 0 |  | 0 | 312 |  | 13
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 26 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2860 | 0 | 0 | 0 | 0 |  | 0 | 2860 |  | 13
|  |  |  | Equipment Pads - 5 EA |  |  |  | 6 | [14 empty] | 13
[5 empty] | POINT & PATCH CONC PAD | 50.95 | SF | 8 | 1.9871 | 0.039 | 0.78 | 39.741 | 0.01 | 0.5095 | 0 | 0 | 0 | 0 |  | 0 | 40.2505 |  | 13
[5 empty] | TROWEL FINISH PADS | 293.32 | SF | 6 | 20.2391 | 0.069 | 1.38 | 404.7816 | 0.02 | 5.8664 | 0 | 0 | 0 | 0 |  | 0 | 410.648 |  | 13
[5 empty] | RUB CONC PAD | 50.95 | SF | 6 | 5.095 | 0.1 | 2 | 101.9 | 0.03 | 1.5285 | 0 | 0 | 0 | 0 |  | 0 | 103.4285 |  | 13
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 293.32 | SF | 6 | 4.6931 | 0.016 | 0.32 | 93.8624 | 0.01 | 2.9332 | 0 | 0 | 0 | 0 |  | 0 | 96.7956 |  | 13
[5 empty] | PAD EDGEFORM | 154.38 | SF | 6 | 37.0512 | 0.24 | 4.8 | 741.024 | 1 | 154.38 | 0 | 0 | 0 | 0 |  | 0 | 895.404 |  | 13
[5 empty] | PLACE PADS | 4 | CY | 6 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 13
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 13
|  |  |  | HVAC Pads |  |  |  | 6 | [14 empty] | 13
[5 empty] | HAND PREP SUBGRADE-BUILDING | 77.89 | SF | 6 | 2.0251 | 0.026 | 0.52 | 40.5028 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.5028 |  | 13
[5 empty] | POINT & PATCH | 29.84 | SF | 8 | 1.9993 | 0.067 | 1.34 | 39.9856 | 0.01 | 0.2984 | 0 | 0 | 0 | 0 |  | 0 | 40.284 |  | 13
[5 empty] | FINISH CONCRETE | 77.89 | SF | 6 | 2.0251 | 0.026 | 0.52 | 40.5028 | 0.02 | 1.5578 | 0 | 0 | 0 | 0 |  | 0 | 42.0606 |  | 13
[5 empty] | SLAB EDGEFORM | 70.32 | SF | 6 | 16.8768 | 0.24 | 4.8 | 337.536 | 0.7 | 49.224 | 0 | 0 | 1 | 70.32 |  | 0 | 457.08 |  | 13
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 13
[5 empty] | RESTEEL DOBIE SUPPORTS | 77.89 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 3.8945 | 0 | 0 | 0 | 0 |  | 0 | 3.8945 |  | 13
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 13
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 13
|  |  |  | 2' Thick Generator Slab |  |  |  | 6 | [14 empty] | 13
[5 empty] | HAND PREP SUBGRADE-BUILDING | 655 | SF | 6 | 10.48 | 0.016 | 0.32 | 209.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 209.6 |  | 13
[5 empty] | POINT & PATCH | 342 | SF | 8 | 10.26 | 0.03 | 0.6 | 205.2 | 0.01 | 3.42 | 0 | 0 | 0 | 0 |  | 0 | 208.62 |  | 13
[5 empty] | FINISH CONCRETE | 655 | SF | 6 | 9.17 | 0.014 | 0.28 | 183.4 | 0.02 | 13.1 | 0 | 0 | 0 | 0 |  | 0 | 196.5 |  | 13
[5 empty] | SLAB EDGEFORM | 342 | SF | 6 | 82.08 | 0.24 | 4.8 | 1641.6 | 0.7 | 239.4 | 0 | 0 | 1 | 342 |  | 0 | 2223 |  | 13
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 20 | EA | 6 | 12 | 0.6 | 12 | 240 | 1.5 | 30 | 0 | 0 | 0 | 0 |  | 0 | 270 |  | 13
[5 empty] | RESTEEL DOBIE SUPPORTS | 655 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 32.75 | 0 | 0 | 0 | 0 |  | 0 | 32.75 |  | 13
[5 empty] | PLACE SLAB ON GRADE | 49 | CY | 6 | 29.4 | 0.6 | 12 | 588 | 0 | 0 |  | 0 |  | 0 |  | 0 | 588 |  | 13
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 49 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 5390 | 0 | 0 | 0 | 0 |  | 0 | 5390 |  | 13
|  |  |  | Generator Slab on Grade |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1662 | SF | 8 | 26.592 | 0.016 | 0.32 | 531.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 531.84 |  | 13
[5 empty] | POINT & PATCH | 99.75 | SF | 6 | 2.9925 | 0.03 | 0.6 | 59.85 | 0.01 | 0.9975 | 0 | 0 | 0 | 0 |  | 0 | 60.8475 |  | 13
[5 empty] | FINISH CONCRETE | 1662 | SF | 6 | 22.8525 | 0.01375 | 0.275 | 457.05 | 0.02 | 33.24 | 0 | 0 | 0 | 0 |  | 0 | 490.29 |  | 13
[5 empty] | SLAB EDGEFORM | 199.5 | SF | 6 | 47.88 | 0.24 | 4.8 | 957.6 | 0.7 | 139.65 | 0 | 0 | 1 | 199.5 |  | 0 | 1296.75 |  | 13
[5 empty] | RESTEEL DOBIE SUPPORTS | 1662 | SF | 6 | 0 | 0 | 0 | 0 | 0.5 | 831 | 0 | 0 | 0 | 0 |  | 0 | 831 |  | 13
[5 empty] | PLACE SLAB ON GRADE | 44 | CY | 6 | 26.4 | 0.6 | 12 | 528 | 0 | 0 |  | 0 |  | 0 |  | 0 | 528 |  | 13
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 44 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4840 | 0 | 0 | 0 | 0 |  | 0 | 4840 |  | 13
6
|  |  | (125-W) Blower / MCC Building |  |  |  |  | 6
|  |  |  | 12" Continuous Footing |  |  |  | 6
[5 empty] | HAND EXCAV CONTINUOUS FTG | 7.09 | CY | 6 | 14.18 | 2 | 40 | 283.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 283.6 |  | 14
[5 empty] | FINISH TOP FTG/PILE CAP | 580.02 | SF | 6 | 16.2406 | 0.028 | 0.56 | 324.8112 | 0.02 | 11.6004 | 0 | 0 | 0 | 0 |  | 0 | 336.4116 |  | 14
[5 empty] | CONTINUOUS FTG EDGEFORM | 386.68 | SF | 6 | 92.8032 | 0.24 | 4.8 | 1856.064 | 0.45 | 174.006 | 0 | 0 | 1 | 386.68 |  | 0 | 2416.75 |  | 14
[5 empty] | RESTEEL DOBIE SUPPORTS | 580.02 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 29.001 | 0 | 0 | 0 | 0 |  | 0 | 29.001 |  | 14
[5 empty] | PLACE CONTINUOUS FOOTING | 22 | CY | 6 | 17.6 | 0.8 | 16 | 352 | 0 | 0 |  | 0 |  | 0 |  | 0 | 352 |  | 14
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 22 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2420 | 0 | 0 | 0 | 0 |  | 0 | 2420 |  | 14
|  |  |  | Blower Pads - 3 EA |  |  |  | 6 | [14 empty] | 14
[5 empty] | POINT & PATCH CONC PAD | 91.26 | SF | 8 | 2.0077 | 0.022 | 0.44 | 40.1544 | 0.01 | 0.9126 | 0 | 0 | 0 | 0 |  | 0 | 41.067 |  | 14
[5 empty] | TROWEL FINISH PADS | 90 | SF | 6 | 6.21 | 0.069 | 1.38 | 124.2 | 0.02 | 1.8 | 0 | 0 | 0 | 0 |  | 0 | 126 |  | 14
[5 empty] | RUB CONC PAD | 91.26 | SF | 6 | 9.126 | 0.1 | 2 | 182.52 | 0.03 | 2.7378 | 0 | 0 | 0 | 0 |  | 0 | 185.2578 |  | 14
[5 empty] | PAD EDGEFORM | 91.26 | SF | 6 | 21.9024 | 0.24 | 4.8 | 438.048 | 1 | 91.26 | 0 | 0 | 0 | 0 |  | 0 | 529.308 |  | 14
[5 empty] | SET ANCHOR BOLTS/ PAD | 24 | EA | 6 | 14.4 | 0.6 | 12 | 288 | 1.5 | 36 | 0 | 0 | 0 | 0 |  | 0 | 324 |  | 14
[5 empty] | PLACE PADS | 4 | CY | 6 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 14
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 14
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 14
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1822.96 | SF | 6 | 29.1674 | 0.016 | 0.32 | 583.3472 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 583.3472 |  | 14
[5 empty] | POINT & PATCH | 167.34 | SF | 8 | 5.0202 | 0.03 | 0.6 | 100.404 | 0.01 | 1.6734 | 0 | 0 | 0 | 0 |  | 0 | 102.0774 |  | 14
[5 empty] | FINISH CONCRETE | 1822.96 | SF | 6 | 25.5214 | 0.014 | 0.28 | 510.4288 | 0.02 | 36.4592 | 0 | 0 | 0 | 0 |  | 0 | 546.888 |  | 14
[5 empty] | SLAB EDGEFORM | 15 | SF | 6 | 3.6 | 0.24 | 4.8 | 72 | 0.7 | 10.5 | 0 | 0 | 1 | 15 |  | 0 | 97.5 |  | 14
[5 empty] | ZIP STRIP | 167 | LF | 6 | 4.843 | 0.029 | 0.58 | 96.86 | 1.125 | 187.875 |  | 0 |  | 0 |  | 0 | 284.735 |  | 14
[5 empty] | 3/4" EXPANSION JOINT | 203 | SF | 6 | 17.255 | 0.085 | 1.7 | 345.1 | 1.75 | 355.25 | 0 | 0 | 0 | 0 |  | 0 | 700.35 |  | 14
[5 empty] | 1/2" JOINT SEALANT | 326.7 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 816.75 |  | 0 | 816.75 |  | 14
[5 empty] | 10 MIL VISQUEEN | 19.09 | SQS | 6 | 4.3716 | 0.229 | 4.58 | 87.4322 | 30 | 572.7 | 0 | 0 | 0 | 0 |  | 0 | 660.1322 |  | 14
[5 empty] | SAW CUT CONCRETE | 162.67 | LF | 6 | 19.5204 | 0.12 | 2.4 | 390.408 | 0.18 | 29.2806 | 0 | 0 | 0.75 | 122.0025 |  | 0 | 541.6911 |  | 14
[5 empty] | RESTEEL DOBIE SUPPORTS | 1822.96 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 91.148 | 0 | 0 | 0 | 0 |  | 0 | 91.148 |  | 14
[5 empty] | PLACE SLAB ON GRADE | 41 | CY | 6 | 24.6 | 0.6 | 12 | 492 | 0 | 0 |  | 0 |  | 0 |  | 0 | 492 |  | 14
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 41 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4510 | 0 | 0 | 0 | 0 |  | 0 | 4510 |  | 14
|  |  |  | Equipment Pads - 3 EA |  |  |  | 6 | [14 empty] | 14
[5 empty] | POINT & PATCH CONC PAD | 40 | SF | 8 | 2.04 | 0.051 | 1.02 | 40.8 | 0.01 | 0.4 | 0 | 0 | 0 | 0 |  | 0 | 41.2 |  | 14
[5 empty] | TROWEL FINISH PADS | 130 | SF | 6 | 8.97 | 0.069 | 1.38 | 179.4 | 0.02 | 2.6 | 0 | 0 | 0 | 0 |  | 0 | 182 |  | 14
[5 empty] | RUB CONC PAD | 40 | SF | 6 | 4 | 0.1 | 2 | 80 | 0.03 | 1.2 | 0 | 0 | 0 | 0 |  | 0 | 81.2 |  | 14
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 130 | SF | 6 | 2.08 | 0.016 | 0.32 | 41.6 | 0.01 | 1.3 | 0 | 0 | 0 | 0 |  | 0 | 42.9 |  | 14
[5 empty] | PAD EDGEFORM | 120 | SF | 6 | 28.8 | 0.24 | 4.8 | 576 | 1 | 120 | 0 | 0 | 0 | 0 |  | 0 | 696 |  | 14
[5 empty] | PLACE PADS | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 14
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 14
|  |  |  | HVAC Pads |  |  |  | 6 | [14 empty] | 14
[5 empty] | HAND PREP SUBGRADE-BUILDING | 106.28 | SF | 6 | 2.0193 | 0.019 | 0.38 | 40.3864 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.3864 |  | 14
[5 empty] | POINT & PATCH | 35.02 | SF | 8 | 1.9961 | 0.057 | 1.14 | 39.9228 | 0.01 | 0.3502 | 0 | 0 | 0 | 0 |  | 0 | 40.273 |  | 14
[5 empty] | FINISH CONCRETE | 106.28 | SF | 6 | 2.0193 | 0.019 | 0.38 | 40.3864 | 0.02 | 2.1256 | 0 | 0 | 0 | 0 |  | 0 | 42.512 |  | 14
[5 empty] | SLAB EDGEFORM | 80.68 | SF | 6 | 19.3632 | 0.24 | 4.8 | 387.264 | 0.7 | 56.476 | 0 | 0 | 1 | 80.68 |  | 0 | 524.42 |  | 14
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 14
[5 empty] | RESTEEL DOBIE SUPPORTS | 106.28 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 5.314 | 0 | 0 | 0 | 0 |  | 0 | 5.314 |  | 14
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 14
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 14
|  |  | (130-W) Operations Building |  |  |  |  | 6
|  |  |  | 12" Continuous Footing |  |  |  | 6
[5 empty] | HAND EXCAV CONTINUOUS FTG | 7.57 | CY | 6 | 15.14 | 2 | 40 | 302.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 302.8 |  | 15
[5 empty] | FINISH TOP FTG/PILE CAP | 618.99 | SF | 6 | 17.3317 | 0.028 | 0.56 | 346.6344 | 0.02 | 12.3798 | 0 | 0 | 0 | 0 |  | 0 | 359.0142 |  | 15
[5 empty] | CONTINUOUS FTG EDGEFORM | 412.66 | SF | 6 | 99.0384 | 0.24 | 4.8 | 1980.768 | 0.45 | 185.697 | 0 | 0 | 1 | 412.66 |  | 0 | 2579.125 |  | 15
[5 empty] | RESTEEL DOBIE SUPPORTS | 618.99 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 30.9495 | 0 | 0 | 0 | 0 |  | 0 | 30.9495 |  | 15
[5 empty] | PLACE CONTINUOUS FOOTING | 23 | CY | 6 | 18.4 | 0.8 | 16 | 368 | 0 | 0 |  | 0 |  | 0 |  | 0 | 368 |  | 15
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 23 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2530 | 0 | 0 | 0 | 0 |  | 0 | 2530 |  | 15
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 15
[5 empty] | HAND PREP SUBGRADE-BUILDING | 2536.54 | SF | 6 | 40.5846 | 0.016 | 0.32 | 811.6928 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 811.6928 |  | 15
[5 empty] | POINT & PATCH | 123.42 | SF | 8 | 3.7026 | 0.03 | 0.6 | 74.052 | 0.01 | 1.2342 | 0 | 0 | 0 | 0 |  | 0 | 75.2862 |  | 15
[5 empty] | FINISH CONCRETE | 2536.54 | SF | 6 | 35.5116 | 0.014 | 0.28 | 710.2312 | 0.02 | 50.7308 | 0 | 0 | 0 | 0 |  | 0 | 760.962 |  | 15
[5 empty] | SLAB EDGEFORM | 162.83 | SF | 6 | 39.0792 | 0.24 | 4.8 | 781.584 | 0.7 | 113.981 | 0 | 0 | 1 | 162.83 |  | 0 | 1058.395 |  | 15
[5 empty] | 1/2" EXPANSION JOINT | 9.67 | SF | 6 | 2.0307 | 0.21 | 4.2 | 40.614 | 1.5 | 14.505 | 0 | 0 | 0 | 0 |  | 0 | 55.119 |  | 15
[5 empty] | 1/2" JOINT SEALANT | 9.67 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 24.175 |  | 0 | 24.175 |  | 15
[5 empty] | 10 MIL VISQUEEN | 24.86 | SQS | 6 | 5.6929 | 0.229 | 4.58 | 113.8588 | 30 | 745.8 | 0 | 0 | 0 | 0 |  | 0 | 859.6588 |  | 15
[5 empty] | RESTEEL DOBIE SUPPORTS | 2536.54 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 126.827 | 0 | 0 | 0 | 0 |  | 0 | 126.827 |  | 15
[5 empty] | PLACE SLAB ON GRADE | 54 | CY | 6 | 32.4 | 0.6 | 12 | 648 | 0 | 0 |  | 0 |  | 0 |  | 0 | 648 |  | 15
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 54 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 5940 | 0 | 0 | 0 | 0 |  | 0 | 5940 |  | 15
|  |  |  | HVAC Pads |  |  |  | 6 | [14 empty] | 15
[5 empty] | HAND PREP SUBGRADE-BUILDING | 100 | SF | 6 | 2 | 0.02 | 0.4 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40 |  | 15
[5 empty] | POINT & PATCH | 25 | SF | 8 | 2 | 0.08 | 1.6 | 40 | 0.01 | 0.25 | 0 | 0 | 0 | 0 |  | 0 | 40.25 |  | 15
[5 empty] | FINISH CONCRETE | 100 | SF | 6 | 2 | 0.02 | 0.4 | 40 | 0.02 | 2 | 0 | 0 | 0 | 0 |  | 0 | 42 |  | 15
[5 empty] | SLAB EDGEFORM | 50 | SF | 6 | 12 | 0.24 | 4.8 | 240 | 0.7 | 35 | 0 | 0 | 1 | 50 |  | 0 | 325 |  | 15
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 15
[5 empty] | RESTEEL DOBIE SUPPORTS | 100 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 5 | 0 | 0 | 0 | 0 |  | 0 | 5 |  | 15
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 15
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 15
|  |  | (20-E) Aeration / Anoxic Tank |  |  |  |  | 6
|  |  |  | Pipe Encasements - 10 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 8.33 | CY | 6 | 16.66 | 2 | 40 | 333.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 333.2 |  | 16
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 1362.84 | SF | 6 | 163.5408 | 0.12 | 2.4 | 3270.816 | 1 | 1362.84 | 0 | 0 | 1 | 1362.84 |  | 0 | 5996.496 |  | 16
[5 empty] | PIPE ENCASE FORMWK - VERT 8 ' | 122.56 | SF | 6 | 29.4144 | 0.24 | 4.8 | 588.288 | 1 | 122.56 | 0 | 0 | 1 | 122.56 |  | 0 | 833.408 |  | 16
[5 empty] | RESTEEL DOBIE SUPPORTS | 681.42 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 34.071 | 0 | 0 | 0 | 0 |  | 0 | 34.071 |  | 16
[5 empty] | PLACE PIPE ENCASEMENT | 55 | CY | 6 | 33 | 0.6 | 12 | 660 | 0 | 0 |  | 0 |  | 0 |  | 0 | 660 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 55 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6050 | 0 | 0 | 0 | 0 |  | 0 | 6050 |  | 16
|  |  |  | 20" Slab on Grade |  |  |  | 6 | [14 empty] | 16
[5 empty] | HAND PREP SUBGRADE-BUILDING | 35552 | SF | 6 | 568.832 | 0.016 | 0.32 | 11376.64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11376.64 |  | 16
[5 empty] | POINT & PATCH | 1444.55 | SF | 8 | 43.3365 | 0.03 | 0.6 | 866.73 | 0.01 | 14.4455 | 0 | 0 | 0 | 0 |  | 0 | 881.1755 |  | 16
[5 empty] | FINISH CONCRETE | 35552 | SF | 6 | 497.728 | 0.014 | 0.28 | 9954.56 | 0.02 | 711.04 | 0 | 0 | 0 | 0 |  | 0 | 10665.6 |  | 16
[5 empty] | SLAB EDGEFORM | 1444.55 | SF | 6 | 404.474 | 0.28 | 5.6 | 8089.48 | 0.7 | 1011.185 | 0 | 0 | 1 | 1444.55 |  | 0 | 10545.215 |  | 16
[5 empty] | 18" TYPE 1 SOG WALL BASE JT | 1253.5 | LF | 6 | 589.145 | 0.47 | 9.4 | 11782.9 | 2.97 | 3722.895 | 0 | 0 | 0 | 0 |  | 0 | 15505.795 |  | 16
[5 empty] | 20" TYPE 1 SOG EXPAN JT | 126.5 | LF | 6 | 211.255 | 1.67 | 33.4 | 4225.1 | 71.52 | 9047.28 | 0 | 0 | 2.5 | 316.25 |  | 0 | 13588.63 |  | 16
[5 empty] | 20" TYPE 1 SOG CONST JT | 1480 | LF | 6 | 1065.6 | 0.72 | 14.4 | 21312 | 3.67 | 5431.6 | 0 | 0 | 2.5 | 3700 |  | 0 | 30443.6 |  | 16
[5 empty] | RESTEEL DOBIE SUPPORTS | 35552 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 1777.6 | 0 | 0 | 0 | 0 |  | 0 | 1777.6 |  | 16
[5 empty] | PLACE SLAB ON GRADE | 2199 | CY | 6 | 1319.4 | 0.6 | 12 | 26388 | 0 | 0 |  | 0 |  | 0 |  | 0 | 26388 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2199 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 241890 | 0 | 0 | 0 | 0 |  | 0 | 241890 |  | 16
|  |  |  | Tank Walls |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 87331.06 | SF | 8 | 2619.9318 | 0.03 | 0.6 | 52398.636 | 0.01 | 873.3106 | 0 | 0 | 0 | 0 |  | 0 | 53271.9466 |  | 16
[5 empty] | STANDARD RUB WALLS | 14502.69 | SF | 6 | 1087.7017 | 0.075 | 1.5 | 21754.035 | 0.03 | 435.0807 | 0 | 0 | 0 | 0 |  | 0 | 22189.1157 |  | 16
[5 empty] | GANG WALLFORM: 16 - 20' | 51955.93 | SF | 6 | 5195.593 | 0.1 | 2 | 103911.86 | 0.55 | 28575.7615 | 0 | 0 | 1 | 51955.93 |  | 0 | 184443.5515 |  | 16
[5 empty] | GANG WALLFORM: 20+' | 14378 | SF | 6 | 1581.58 | 0.11 | 2.2 | 31631.6 | 0.55 | 7907.9 | 0 | 0 | 1 | 14378 |  | 0 | 53917.5 |  | 16
[5 empty] | CIRC GANGFORM: 10 -20' DIA | 528 | SF | 6 | 63.36 | 0.12 | 2.4 | 1267.2 | 0.7 | 369.6 | 0 | 0 | 1 | 528 |  | 0 | 2164.8 |  | 16
[5 empty] | CIRC GANGFORM: 40 - 60' DIA | 13293.7 | SF | 6 | 1462.307 | 0.11 | 2.2 | 29246.14 | 0.55 | 7311.535 | 0 | 0 | 2 | 26587.4 |  | 0 | 63145.075 |  | 16
[5 empty] | CIRC GANGFORM: 60 - 80' DIA | 7175.67 | SF | 6 | 932.8371 | 0.13 | 2.6 | 18656.742 | 0.55 | 3946.6185 | 0 | 0 | 2 | 14351.34 |  | 0 | 36954.7005 |  | 16
[5 empty] | GANG WALL END FORMS | 446.84 | SF | 6 | 128.2431 | 0.287 | 5.74 | 2564.8616 | 1.091 | 487.5024 | 0 | 0 | 0 | 0 |  | 0 | 3052.364 |  | 16
[5 empty] | 12" TYPE 1 GANG WLTO TROUGH SLAB CONST JT | 122.5 | LF | 6 | 20.825 | 0.17 | 3.4 | 416.5 | 2.01 | 246.225 | 0 | 0 | 0 | 0 |  | 0 | 662.725 |  | 16
[5 empty] | 12" TYPE 1 GANG WL EXPAN JT | 36.48 | LF | 6 | 55.0848 | 1.51 | 30.2 | 1101.696 | 70.91 | 2586.7968 | 0 | 0 | 5 | 182.4 |  | 0 | 3870.8928 |  | 16
[5 empty] | 18" TYPE 1 GANG WL EXPAN JT | 55.26 | LF | 6 | 93.3894 | 1.69 | 33.8 | 1867.788 | 71.42 | 3946.6692 | 0 | 0 | 5 | 276.3 |  | 0 | 6090.7572 |  | 16
[5 empty] | 12" TYPE 2 GANG WL CONST JT | 71.68 | LF | 6 | 42.2912 | 0.59 | 11.8 | 845.824 | 3.16 | 226.5088 | 0 | 0 | 2.5 | 179.2 |  | 0 | 1251.5328 |  | 16
[5 empty] | 18" TYPE 2 GANG WL CONST JT | 664.3 | LF | 6 | 524.797 | 0.79 | 15.8 | 10495.94 | 3.67 | 2437.981 | 0 | 0 | 2.5 | 1660.75 |  | 0 | 14594.671 |  | 16
[5 empty] | FORM BOXOUT/ GANG | 210 | SF | 6 | 73.5 | 0.35 | 7 | 1470 | 1.5 | 315 | 0 | 0 | 0 | 0 |  | 0 | 1785 |  | 16
[5 empty] | FORM SLAB SLOT/ GANG | 122.5 | LF | 6 | 30.625 | 0.25 | 5 | 612.5 | 0.7 | 85.75 | 0 | 0 | 0 | 0 |  | 0 | 698.25 |  | 16
[5 empty] | SET EMBED ANGLE/ GANG | 379 | LF | 6 | 75.8 | 0.2 | 4 | 1516 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1516 |  | 16
[5 empty] | PLACE WALLS | 2314 | CY | 6 | 1619.8 | 0.7 | 14 | 32396 | 0 | 0 |  | 0 |  | 0 |  | 0 | 32396 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2314 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 254540 | 0 | 0 | 0 | 0 |  | 0 | 254540 |  | 16
|  |  |  | 12" Trough Columns 11.75' - 10 EA |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 369.14 | SF | 8 | 11.0742 | 0.03 | 0.6 | 221.484 | 0.01 | 3.6914 | 0 | 0 | 0 | 0 |  | 0 | 225.1754 |  | 16
[5 empty] | RUB CONC COLUMN/PIER | 369.14 | SF | 6 | 36.914 | 0.1 | 2 | 738.28 | 0.03 | 11.0742 | 0 | 0 | 0 | 0 |  | 0 | 749.3542 |  | 16
[5 empty] | SPECIAL CIRC COL FORM 12" DIA | 117.5 | LF | 6 | 57.6925 | 0.491 | 9.82 | 1153.85 | 7 | 822.5 | 0 | 0 | 0 | 0 |  | 0 | 1976.35 |  | 16
[5 empty] | PLACE COLUMNS | 4 | CY | 6 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 16
|  |  |  | 12" Trough Slab |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 133.5 | SF | 8 | 4.005 | 0.03 | 0.6 | 80.1 | 0.01 | 1.335 | 0 | 0 | 0 | 0 |  | 0 | 81.435 |  | 16
[5 empty] | FINISH CONCRETE | 673.75 | SF | 8 | 9.4325 | 0.014 | 0.28 | 188.65 | 0.02 | 13.475 | 0 | 0 | 0 | 0 |  | 0 | 202.125 |  | 16
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 673.75 | SF | 6 | 7.4112 | 0.011 | 0.22 | 148.225 | 0.02 | 13.475 | 0 | 0 | 0 | 0 |  | 0 | 161.7 |  | 16
[5 empty] | SHORED SOFFIT FORM: 8 - 12' | 673.75 | SF | 6 | 161.7 | 0.24 | 4.8 | 3234 | 2 | 1347.5 | 0 | 0 | 1.125 | 757.9688 |  | 0 | 5339.4688 |  | 16
[5 empty] | SHORED SLAB EDGE FORM | 133.5 | SF | 6 | 29.37 | 0.22 | 4.4 | 587.4 | 1.8 | 240.3 | 0 | 0 | 0 | 0 |  | 0 | 827.7 |  | 16
[5 empty] | 12" TYPE 1 WLK/TROUGH WL BS JT | 122.5 | LF | 6 | 57.575 | 0.47 | 9.4 | 1151.5 | 2.96 | 362.6 | 0 | 0 | 0 | 0 |  | 0 | 1514.1 |  | 16
[5 empty] | 12" TYPE 2 WLK/TROUGH CONST JT | 16.5 | LF | 6 | 9.075 | 0.55 | 11 | 181.5 | 3.19 | 52.635 | 0 | 0 | 0 | 0 |  | 0 | 234.135 |  | 16
[5 empty] | RESTEEL DOBIE SUPPORTS | 673.75 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 33.6875 | 0 | 0 | 0 | 0 |  | 0 | 33.6875 |  | 16
[5 empty] | PLACE SHORED SLAB/BEAM | 25 | CY | 8 | 17.5 | 0.7 | 14 | 350 | 0 | 0 |  | 0 |  | 0 |  | 0 | 350 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 25 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2750 | 0 | 0 | 0 | 0 |  | 0 | 2750 |  | 16
|  |  |  | 12" Trough Wall |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 1754.21 | SF | 8 | 52.6263 | 0.03 | 0.6 | 1052.526 | 0.01 | 17.5421 | 0 | 0 | 0 | 0 |  | 0 | 1070.0681 |  | 16
[5 empty] | STANDARD RUB WALLS | 877.11 | SF | 6 | 65.7832 | 0.075 | 1.5 | 1315.665 | 0.03 | 26.3133 | 0 | 0 | 0 | 0 |  | 0 | 1341.9783 |  | 16
[5 empty] | WALLFORM: 4 - 8' | 1754.21 | SF | 6 | 249.0978 | 0.142 | 2.84 | 4981.9564 | 0.7 | 1227.947 | 0 | 0 | 1 | 1754.21 |  | 0 | 7964.1134 |  | 16
[5 empty] | 12" TYPE 1 WL CONST JT | 20 | LF | 6 | 3.4 | 0.17 | 3.4 | 68 | 2.01 | 40.2 | 0 | 0 | 0 | 0 |  | 0 | 108.2 |  | 16
[5 empty] | SET EMBED ANGLE/ STRAIGHT WALL | 122 | LF | 6 | 24.4 | 0.2 | 4 | 488 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 488 |  | 16
[5 empty] | STR WALL-PIPE PENET 13-36" DIA | 2 | EA | 6 | 3 | 1.5 | 30 | 60 | 22.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 105 |  | 16
[5 empty] | PLACE WALLS | 34 | CY | 8 | 23.8 | 0.7 | 14 | 476 | 0 | 0 |  | 0 |  | 0 |  | 0 | 476 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 34 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 3740 | 0 | 0 | 0 | 0 |  | 0 | 3740 |  | 16
|  |  |  | 16" Walkway Columns 17.42' - 24 EA |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 1746.875 | SF | 8 | 52.4062 | 0.03 | 0.6 | 1048.125 | 0.01 | 17.4688 | 0 | 0 | 0 | 0 |  | 0 | 1065.5938 |  | 16
[5 empty] | SPECIAL CIRC COL FORM 16" DIA | 418 | LF | 6 | 238.678 | 0.571 | 11.42 | 4773.56 | 10 | 4180 | 0 | 0 | 0 | 0 |  | 0 | 8953.56 |  | 16
[5 empty] | PLACE COLUMNS | 22 | CY | 8 | 17.6 | 0.8 | 16 | 352 | 0 | 0 |  | 0 |  | 0 |  | 0 | 352 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 22 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2420 | 0 | 0 | 0 | 0 |  | 0 | 2420 |  | 16
|  |  |  | 12" Walkways |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 1480 | SF | 8 | 44.4 | 0.03 | 0.6 | 888 | 0.01 | 14.8 | 0 | 0 | 0 | 0 |  | 0 | 902.8 |  | 16
[5 empty] | FINISH CONCRETE | 3577 | SF | 8 | 50.078 | 0.014 | 0.28 | 1001.56 | 0.02 | 71.54 | 0 | 0 | 0 | 0 |  | 0 | 1073.1 |  | 16
[5 empty] | RUB CONC SUPP SLAB EDGES | 1480 | SF | 6 | 148 | 0.1 | 2 | 2960 | 0.03 | 44.4 | 0 | 0 | 0 | 0 |  | 0 | 3004.4 |  | 16
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 3577 | SF | 6 | 39.347 | 0.011 | 0.22 | 786.94 | 0.02 | 71.54 | 0 | 0 | 0 | 0 |  | 0 | 858.48 |  | 16
[5 empty] | WALKWAY/TROUGH SOFFIT: 16- 20' | 3577 | SF | 6 | 1953.042 | 0.546 | 10.92 | 39060.84 | 1.5 | 5365.5 | 0 | 0 | 0.975 | 3487.575 |  | 0 | 47913.915 |  | 16
[5 empty] | WALKWAY/TROUGH EDGE FORM | 1480 | SF | 6 | 324.12 | 0.219 | 4.38 | 6482.4 | 1.35 | 1998 | 0 | 0 | 0 | 0 |  | 0 | 8480.4 |  | 16
[5 empty] | 12" TYPE 1 WKY/TROUGH CONST JT | 78 | LF | 6 | 42.9 | 0.55 | 11 | 858 | 3.19 | 248.82 | 0 | 0 | 2.5 | 195 |  | 0 | 1301.82 |  | 16
[5 empty] | SET EMBED ANGLE/ WALKWAY-TRGH | 22 | LF | 6 | 4.4 | 0.2 | 4 | 88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 88 |  | 16
[5 empty] | RESTEEL DOBIE SUPPORTS | 3577 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 178.85 | 0 | 0 | 0 | 0 |  | 0 | 178.85 |  | 16
[5 empty] | PLACE WALKWAY/TROUGH | 133 | CY | 8 | 106.4 | 0.8 | 16 | 2128 | 0 | 0 |  | 0 |  | 0 |  | 0 | 2128 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 133 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 14630 | 0 | 0 | 0 | 0 |  | 0 | 14630 |  | 16
|  |  |  | 12" Shored Slab @ EL 131.75 |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH | 1612.16 | SF | 8 | 48.3648 | 0.03 | 0.6 | 967.296 | 0.01 | 16.1216 | 0 | 0 | 0 | 0 |  | 0 | 983.4176 |  | 16
[5 empty] | FINISH CONCRETE | 8520 | SF | 8 | 119.28 | 0.014 | 0.28 | 2385.6 | 0.02 | 170.4 | 0 | 0 | 0 | 0 |  | 0 | 2556 |  | 16
[5 empty] | RUB CONC SUPP SLAB EDGES | 697 | SF | 6 | 69.7 | 0.1 | 2 | 1394 | 0.03 | 20.91 | 0 | 0 | 0 | 0 |  | 0 | 1414.91 |  | 16
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 8520 | SF | 6 | 93.72 | 0.011 | 0.22 | 1874.4 | 0.02 | 170.4 | 0 | 0 | 0 | 0 |  | 0 | 2044.8 |  | 16
[5 empty] | BEAM W/ SLAB SOFFIT: 12 - 16' | 548 | SF | 6 | 328.8 | 0.6 | 12 | 6576 | 2 | 1096 | 0 | 0 | 2.6 | 1424.8 |  | 0 | 9096.8 |  | 16
[5 empty] | INTERIOR BEAM SIDES | 915.16 | SF | 6 | 228.79 | 0.25 | 5 | 4575.8 | 1.5 | 1372.74 | 0 | 0 | 0 | 0 |  | 0 | 5948.54 |  | 16
[5 empty] | SHORED SOFFIT FORM: 16 - 20' | 8520 | SF | 6 | 3834 | 0.45 | 9 | 76680 | 2 | 17040 | 0 | 0 | 1.625 | 13845 |  | 0 | 107565 |  | 16
[5 empty] | SHORED SLAB EDGE FORM | 697 | SF | 6 | 153.34 | 0.22 | 4.4 | 3066.8 | 1.8 | 1254.6 | 0 | 0 | 0 | 0 |  | 0 | 4321.4 |  | 16
[5 empty] | FORM BOXOUT/ SHORED SLAB | 60 | SF | 6 | 18 | 0.3 | 6 | 360 | 1.5 | 90 | 0 | 0 | 0 | 0 |  | 0 | 450 |  | 16
[5 empty] | RESTEEL DOBIE SUPPORTS | 8520 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 426 | 0 | 0 | 0 | 0 |  | 0 | 426 |  | 16
[5 empty] | PLACE SHORED SLAB/BEAM | 350 | CY | 8 | 210 | 0.6 | 12 | 4200 | 0 | 0 |  | 0 |  | 0 |  | 0 | 4200 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 350 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 38500 | 0 | 0 | 0 | 0 |  | 0 | 38500 |  | 16
|  |  |  | Blower Slab |  |  |  | 6 | [14 empty] | 16
[5 empty] | HAND PREP SUBGRADE-BUILDING | 450 | SF | 6 | 7.2 | 0.016 | 0.32 | 144 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 144 |  | 16
[5 empty] | POINT & PATCH | 82.5 | SF | 8 | 2.475 | 0.03 | 0.6 | 49.5 | 0.01 | 0.825 | 0 | 0 | 0 | 0 |  | 0 | 50.325 |  | 16
[5 empty] | FINISH CONCRETE | 450 | SF | 8 | 6.3 | 0.014 | 0.28 | 126 | 0.02 | 9 | 0 | 0 | 0 | 0 |  | 0 | 135 |  | 16
[5 empty] | SLAB EDGEFORM | 165 | SF | 6 | 39.6 | 0.24 | 4.8 | 792 | 0.7 | 115.5 | 0 | 0 | 1 | 165 |  | 0 | 1072.5 |  | 16
[5 empty] | 1/2" EXPANSION JOINT | 15 | SF | 6 | 1.95 | 0.13 | 2.6 | 39 | 1.5 | 22.5 | 0 | 0 | 0 | 0 |  | 0 | 61.5 |  | 16
[5 empty] | 1/2" JOINT SEALANT | 30 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 75 |  | 0 | 75 |  | 16
[5 empty] | RESTEEL DOBIE SUPPORTS | 450 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 22.5 | 0 | 0 | 0 | 0 |  | 0 | 22.5 |  | 16
[5 empty] | PLACE SLAB ON GRADE | 12 | CY | 8 | 7.2 | 0.6 | 12 | 144 | 0 | 0 |  | 0 |  | 0 |  | 0 | 144 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 12 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1320 | 0 | 0 | 0 | 0 |  | 0 | 1320 |  | 16
|  |  |  | Blower Pads |  |  |  | 6 | [14 empty] | 16
[5 empty] | POINT & PATCH CONC PAD | 60 | SF | 8 | 1.32 | 0.022 | 0.44 | 26.4 | 0.01 | 0.6 | 0 | 0 | 0 | 0 |  | 0 | 27 |  | 16
[5 empty] | TROWEL FINISH PADS | 72 | SF | 6 | 4.968 | 0.069 | 1.38 | 99.36 | 0.02 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 100.8 |  | 16
[5 empty] | RUB CONC PAD | 60 | SF | 6 | 6 | 0.1 | 2 | 120 | 0.03 | 1.8 | 0 | 0 | 0 | 0 |  | 0 | 121.8 |  | 16
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 72 | SF | 6 | 2.16 | 0.03 | 0.6 | 43.2 | 0.01 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 43.92 |  | 16
[5 empty] | PAD EDGEFORM | 60 | SF | 6 | 14.4 | 0.24 | 4.8 | 288 | 1 | 60 | 0 | 0 | 0 | 0 |  | 0 | 348 |  | 16
[5 empty] | SET ANCHOR BOLTS/ PAD | 12 | EA | 6 | 7.2 | 0.6 | 12 | 144 | 1.5 | 18 | 0 | 0 | 0 | 0 |  | 0 | 162 |  | 16
[5 empty] | PLACE PADS | 3 | CY | 8 | 6 | 2 | 40 | 120 | 0 | 0 |  | 0 |  | 0 |  | 0 | 120 |  | 16
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 16
|  |  | (35-E) Clarifier Splitter Box |  |  |  |  | 6
|  |  |  | Pipe Encasements - 6 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 4.58 | CY | 6 | 9.16 | 2 | 40 | 183.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 183.2 |  | 17
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 750 | SF | 6 | 90 | 0.12 | 2.4 | 1800 | 1 | 750 | 0 | 0 | 1 | 750 |  | 0 | 3300 |  | 17
[5 empty] | PIPE ENCASE FORMWK - VERT 2.5 | 100 | SF | 6 | 24 | 0.24 | 4.8 | 480 | 1 | 100 | 0 | 0 | 1 | 100 |  | 0 | 680 |  | 17
[5 empty] | PIPE ENCASE FORMWK - VERT 6.5 | 416 | SF | 6 | 99.84 | 0.24 | 4.8 | 1996.8 | 1 | 416 | 0 | 0 | 1 | 416 |  | 0 | 2828.8 |  | 17
[5 empty] | RESTEEL DOBIE SUPPORTS | 375 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 18.75 | 0 | 0 | 0 | 0 |  | 0 | 18.75 |  | 17
[5 empty] | PLACE PIPE ENCASEMENT | 63 | CY | 8 | 37.8 | 0.6 | 12 | 756 | 0 | 0 |  | 0 |  | 0 |  | 0 | 756 |  | 17
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 63 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6930 | 0 | 0 | 0 | 0 |  | 0 | 6930 |  | 17
|  |  |  | 14" Slab on Grade |  |  |  | 6 | [14 empty] | 17
[5 empty] | HAND PREP SUBGRADE-BUILDING | 600 | SF | 6 | 9.6 | 0.016 | 0.32 | 192 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 192 |  | 17
[5 empty] | POINT & PATCH | 114.66 | SF | 8 | 3.4398 | 0.03 | 0.6 | 68.796 | 0.01 | 1.1466 | 0 | 0 | 0 | 0 |  | 0 | 69.9426 |  | 17
[5 empty] | FINISH CONCRETE | 600 | SF | 8 | 8.4 | 0.014 | 0.28 | 168 | 0.02 | 12 | 0 | 0 | 0 | 0 |  | 0 | 180 |  | 17
[5 empty] | SLAB EDGEFORM | 114.66 | SF | 6 | 32.1048 | 0.28 | 5.6 | 642.096 | 0.7 | 80.262 | 0 | 0 | 1 | 114.66 |  | 0 | 837.018 |  | 17
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 148 | LF | 6 | 69.56 | 0.47 | 9.4 | 1391.2 | 2.96 | 438.08 | 0 | 0 | 0 | 0 |  | 0 | 1829.28 |  | 17
[5 empty] | RESTEEL DOBIE SUPPORTS | 600 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 30 | 0 | 0 | 0 | 0 |  | 0 | 30 |  | 17
[5 empty] | PLACE SLAB ON GRADE | 26 | CY | 8 | 15.6 | 0.6 | 12 | 312 | 0 | 0 |  | 0 |  | 0 |  | 0 | 312 |  | 17
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 26 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2860 | 0 | 0 | 0 | 0 |  | 0 | 2860 |  | 17
|  |  |  | 12" Walls |  |  |  | 6 | [14 empty] | 17
[5 empty] | POINT & PATCH | 4522 | SF | 8 | 135.66 | 0.03 | 0.6 | 2713.2 | 0.01 | 45.22 | 0 | 0 | 0 | 0 |  | 0 | 2758.42 |  | 17
[5 empty] | STANDARD RUB WALLS | 1118 | SF | 6 | 83.85 | 0.075 | 1.5 | 1677 | 0.03 | 33.54 | 0 | 0 | 0 | 0 |  | 0 | 1710.54 |  | 17
[5 empty] | WALLFORM: 8 - 12' | 100 | SF | 6 | 12 | 0.12 | 2.4 | 240 | 0.7 | 70 | 0 | 0 | 1 | 100 |  | 0 | 410 |  | 17
[5 empty] | WALLFORM: 16 - 20' | 4422 | SF | 6 | 619.08 | 0.14 | 2.8 | 12381.6 | 0.7 | 3095.4 | 0 | 0 | 1 | 4422 |  | 0 | 19899 |  | 17
[5 empty] | 6"X6" CHAMFER / STR WALL | 24 | LF | 6 | 1.992 | 0.083 | 1.66 | 39.84 | 2.25 | 54 | 0 | 0 | 0 | 0 |  | 0 | 93.84 |  | 17
[5 empty] | FORM BOXOUT/ GANG | 64 | SF | 6 | 22.4 | 0.35 | 7 | 448 | 1.5 | 96 | 0 | 0 | 0 | 0 |  | 0 | 544 |  | 17
[5 empty] | SET EMBED ANGLE/ STRAIGHT WALL | 172 | LF | 6 | 34.4 | 0.2 | 4 | 688 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 688 |  | 17
[5 empty] | PLACE WALLS | 84 | CY | 8 | 58.8 | 0.7 | 14 | 1176 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1176 |  | 17
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 84 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 9240 | 0 | 0 | 0 | 0 |  | 0 | 9240 |  | 17
|  |  |  | Grout |  |  |  | 6 | [14 empty] | 17
[5 empty] | FINISH GROUT - SUMPS/PITS | 277 | SF | 8 | 1.939 | 0.007 | 0.14 | 38.78 | 0.02 | 5.54 | 0 | 0 | 0 | 0 |  | 0 | 44.32 |  | 17
[5 empty] | ROUGH/CLEAN NEW CONC | 277 | SF | 6 | 3.047 | 0.011 | 0.22 | 60.94 | 0.01 | 2.77 | 0 | 0 | 0 | 0 |  | 0 | 63.71 |  | 17
[5 empty] | PLACE GROUT - SUMPS/PITS | 7 | CY | 8 | 7 | 1 | 20 | 140 | 0 | 0 |  | 0 |  | 0 |  | 0 | 140 |  | 17
[5 empty] | PURCHASE: 2500 PSI GROUT | 7 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 805 | 0 | 0 | 0 | 0 |  | 0 | 805 |  | 17
|  |  | (40-E) Clarifier No. 3 & 4 |  |  |  |  | 6
|  |  |  | Pipe Encasements - 6 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 10.81 | CY | 6 | 21.62 | 2 | 40 | 432.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 432.4 |  | 18
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 1768.64 | SF | 6 | 212.2368 | 0.12 | 2.4 | 4244.736 | 1 | 1768.64 | 0 | 0 | 1 | 1768.64 |  | 0 | 7782.016 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 884.32 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 44.216 | 0 | 0 | 0 | 0 |  | 0 | 44.216 |  | 18
[5 empty] | PLACE PIPE ENCASEMENT | 93 | CY | 8 | 55.8 | 0.6 | 12 | 1116 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1116 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 93 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 10230 | 0 | 0 | 0 | 0 |  | 0 | 10230 |  | 18
|  |  |  | 18" Center Pier Slab |  |  |  | 6 | [14 empty] | 18
[5 empty] | HAND PREP SUBGRADE-BUILDING | 512 | SF | 6 | 8.192 | 0.016 | 0.32 | 163.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 163.84 |  | 18
[5 empty] | POINT & PATCH | 192 | SF | 8 | 5.76 | 0.03 | 0.6 | 115.2 | 0.01 | 1.92 | 0 | 0 | 0 | 0 |  | 0 | 117.12 |  | 18
[5 empty] | FINISH CONCRETE | 512 | SF | 8 | 7.168 | 0.014 | 0.28 | 143.36 | 0.02 | 10.24 | 0 | 0 | 0 | 0 |  | 0 | 153.6 |  | 18
[5 empty] | SLAB EDGEFORM | 192 | SF | 6 | 53.76 | 0.28 | 5.6 | 1075.2 | 0.7 | 134.4 | 0 | 0 | 1 | 192 |  | 0 | 1401.6 |  | 18
[5 empty] | 8 " TYPE 1 SOG WALL BASE JT | 11 | LF | 6 | 5.17 | 0.47 | 9.4 | 103.4 | 2.96 | 32.56 | 0 | 0 | 0 | 0 |  | 0 | 135.96 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 512 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 25.6 | 0 | 0 | 0 | 0 |  | 0 | 25.6 |  | 18
[5 empty] | PLACE SLAB ON GRADE | 29 | CY | 8 | 20.3 | 0.7 | 14 | 406 | 0 | 0 |  | 0 |  | 0 |  | 0 | 406 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 29 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 3190 | 0 | 0 | 0 | 0 |  | 0 | 3190 |  | 18
|  |  |  | Center Pier |  |  |  | 6 | [14 empty] | 18
[5 empty] | HAND PREP SUBGRADE-BUILDING | 512 | SF | 6 | 8.192 | 0.016 | 0.32 | 163.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 163.84 |  | 18
[5 empty] | FINISH CONCRETE | 512 | SF | 8 | 7.168 | 0.014 | 0.28 | 143.36 | 0.02 | 10.24 | 0 | 0 | 0 | 0 |  | 0 | 153.6 |  | 18
[5 empty] | CENTER PIER FORM | 768 | SF | 6 | 228.096 | 0.297 | 5.94 | 4561.92 | 1.4 | 1075.2 | 0 | 0 | 1 | 768 |  | 0 | 6405.12 |  | 18
[5 empty] | SONOTUBE PIER FORM 30" DIA | 12 | LF | 6 | 15.912 | 1.326 | 26.52 | 318.24 | 20 | 240 | 0 | 0 | 0.25 | 3 |  | 0 | 561.24 |  | 18
[5 empty] | 14" TYPE 2 SOG CONST JT | 128 | LF | 6 | 93.44 | 0.73 | 14.6 | 1868.8 | 3.7 | 473.6 | 0 | 0 | 2.5 | 320 |  | 0 | 2662.4 |  | 18
[5 empty] | FORM SUMP BOXOUT/ CENTER PIER | 128 | SF | 6 | 64 | 0.5 | 10 | 1280 | 2.25 | 288 | 0 | 0 | 0 | 0 |  | 0 | 1568 |  | 18
[5 empty] | FORM SLAB SLOT/ CENTER PIER | 128 | LF | 6 | 32 | 0.25 | 5 | 640 | 0.7 | 89.6 | 0 | 0 | 0 | 0 |  | 0 | 729.6 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 512 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 25.6 | 0 | 0 | 0 | 0 |  | 0 | 25.6 |  | 18
[5 empty] | PLACE CENTER PIER | 114 | CY | 8 | 68.4 | 0.6 | 12 | 1368 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1368 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 114 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 12540 | 0 | 0 | 0 | 0 |  | 0 | 12540 |  | 18
|  |  |  | 14" Slab on Grade |  |  |  | 6 | [14 empty] | 18
[5 empty] | HAND PREP SUBGRADE-BUILDING | 14074 | SF | 6 | 225.184 | 0.016 | 0.32 | 4503.68 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4503.68 |  | 18
[5 empty] | POINT & PATCH | 705.37 | SF | 8 | 21.1611 | 0.03 | 0.6 | 423.222 | 0.01 | 7.0537 | 0 | 0 | 0 | 0 |  | 0 | 430.2757 |  | 18
[5 empty] | FINISH CONCRETE | 14074 | SF | 8 | 197.036 | 0.014 | 0.28 | 3940.72 | 0.02 | 281.48 | 0 | 0 | 0 | 0 |  | 0 | 4222.2 |  | 18
[5 empty] | SLAB EDGEFORM | 705.37 | SF | 6 | 197.5036 | 0.28 | 5.6 | 3950.072 | 0.7 | 493.759 | 0 | 0 | 1 | 705.37 |  | 0 | 5149.201 |  | 18
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 592 | LF | 6 | 278.24 | 0.47 | 9.4 | 5564.8 | 2.96 | 1752.32 | 0 | 0 | 0 | 0 |  | 0 | 7317.12 |  | 18
[5 empty] | 14" TYPE 2 SOG CONST JT | 384 | LF | 6 | 280.32 | 0.73 | 14.6 | 5606.4 | 3.19 | 1224.96 | 0 | 0 | 2.5 | 960 |  | 0 | 7791.36 |  | 18
[5 empty] | PIPE PENET 10" DIA | 2 | EA | 6 | 2 | 1 | 20 | 40 | 7.5 | 15 | 0 | 0 | 0 | 0 |  | 0 | 55 |  | 18
[5 empty] | STR WALL-PIPE PENET 13-36" DIA | 4 | EA | 6 | 6 | 1.5 | 30 | 120 | 22.5 | 90 | 0 | 0 | 0 | 0 |  | 0 | 210 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 14074 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 703.7 | 0 | 0 | 0 | 0 |  | 0 | 703.7 |  | 18
[5 empty] | PLACE SLAB ON GRADE | 610 | CY | 8 | 366 | 0.6 | 12 | 7320 | 0 | 0 |  | 0 |  | 0 |  | 0 | 7320 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 610 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 67100 | 0 | 0 | 0 | 0 |  | 0 | 67100 |  | 18
|  |  |  | 12" Tank Walls |  |  |  | 6 | [14 empty] | 18
[5 empty] | POINT & PATCH | 17166 | SF | 8 | 514.98 | 0.03 | 0.6 | 10299.6 | 0.01 | 171.66 | 0 | 0 | 0 | 0 |  | 0 | 10471.26 |  | 18
[5 empty] | STANDARD RUB WALLS | 4230 | SF | 6 | 317.25 | 0.075 | 1.5 | 6345 | 0.03 | 126.9 | 0 | 0 | 0 | 0 |  | 0 | 6471.9 |  | 18
[5 empty] | GANG WALLFORM: 12 - 16' | 264 | SF | 6 | 25.08 | 0.095 | 1.9 | 501.6 | 0.55 | 145.2 | 0 | 0 | 1 | 264 |  | 0 | 910.8 |  | 18
[5 empty] | CIRC GANGFORM: 12 - 16' | 16902 | SF | 6 | 1593.8586 | 0.0943 | 1.886 | 31877.172 | 0.55 | 9296.1 | 0 | 0 | 2 | 33804 |  | 0 | 74977.272 |  | 18
[5 empty] | 10" TYPE 1 CIRC GANG WALL TO TROUGH SLAB CONST JT | 578 | LF | 6 | 97.104 | 0.168 | 3.36 | 1942.08 | 10.01 | 5785.78 | 0 | 0 | 0 | 0 |  | 0 | 7727.86 |  | 18
[5 empty] | 12" TYPE 2 CIRC GANG CONST JT | 276 | LF | 6 | 162.84 | 0.59 | 11.8 | 3256.8 | 3.16 | 872.16 | 0 | 0 | 2.5 | 690 |  | 0 | 4818.96 |  | 18
[5 empty] | 6"X6" CHAMFER / CIRC GANG | 580 | LF | 6 | 34.8 | 0.06 | 1.2 | 696 | 2.25 | 1305 | 0 | 0 | 0 | 0 |  | 0 | 2001 |  | 18
[5 empty] | FORM SLAB SLOT/ CIRC GANG | 578 | LF | 6 | 144.5 | 0.25 | 5 | 2890 | 0.7 | 404.6 | 0 | 0 | 0 | 0 |  | 0 | 3294.6 |  | 18
[5 empty] | GANG-PIPE PENET 30" DIA | 2 | EA | 6 | 3 | 1.5 | 30 | 60 | 22.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 105 |  | 18
[5 empty] | PLACE WALLS | 316 | CY | 8 | 221.2 | 0.7 | 14 | 4424 | 0 | 0 |  | 0 |  | 0 |  | 0 | 4424 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 316 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 34760 | 0 | 0 | 0 | 0 |  | 0 | 34760 |  | 18
|  |  |  | 10" Trough Slab |  |  |  | 6 | [14 empty] | 18
[5 empty] | POINT & PATCH | 516.26 | SF | 8 | 15.4878 | 0.03 | 0.6 | 309.756 | 0.01 | 5.1626 | 0 | 0 | 0 | 0 |  | 0 | 314.9186 |  | 18
[5 empty] | FINISH CONCRETE | 2030 | SF | 8 | 28.42 | 0.014 | 0.28 | 568.4 | 0.02 | 40.6 | 0 | 0 | 0 | 0 |  | 0 | 609 |  | 18
[5 empty] | RUB CONC SUPP SLAB EDGES | 622 | SF | 6 | 62.2 | 0.1 | 2 | 1244 | 0.03 | 18.66 | 0 | 0 | 0 | 0 |  | 0 | 1262.66 |  | 18
[5 empty] | RUB CONC UNDERSIDE OF SLAB | 2030 | SF | 6 | 89.32 | 0.044 | 0.88 | 1786.4 | 0.03 | 60.9 | 0 | 0 | 0 | 0 |  | 0 | 1847.3 |  | 18
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 2030 | SF | 6 | 22.33 | 0.011 | 0.22 | 446.6 | 0.02 | 40.6 | 0 | 0 | 0 | 0 |  | 0 | 487.2 |  | 18
[5 empty] | WALKWAY/TROUGH SOFFIT: 4 - 8' | 2030 | SF | 6 | 406 | 0.2 | 4 | 8120 | 1.5 | 3045 | 0 | 0 | 0.525 | 1065.75 |  | 0 | 12230.75 |  | 18
[5 empty] | WALKWAY/TROUGH EDGE FORM | 622 | SF | 6 | 136.218 | 0.219 | 4.38 | 2724.36 | 1.35 | 839.7 | 0 | 0 | 0 | 0 |  | 0 | 3564.06 |  | 18
[5 empty] | 10" TYPE 2 WLK/TROUGH CONST JT | 56 | LF | 6 | 30.8 | 0.55 | 11 | 616 | 3.19 | 178.64 | 0 | 0 | 0 | 0 |  | 0 | 794.64 |  | 18
[5 empty] | 10" TYPE 2 WLK/TROUGH WL BS JT | 616 | LF | 6 | 289.52 | 0.47 | 9.4 | 5790.4 | 2.96 | 1823.36 | 0 | 0 | 0 | 0 |  | 0 | 7613.76 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 2030 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 101.5 | 0 | 0 | 0 | 0 |  | 0 | 101.5 |  | 18
[5 empty] | PLACE WALKWAY/TROUGH | 63 | CY | 8 | 44.1 | 0.7 | 14 | 882 | 0 | 0 |  | 0 |  | 0 |  | 0 | 882 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 63 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6930 | 0 | 0 | 0 | 0 |  | 0 | 6930 |  | 18
|  |  |  | 10" Trough Wall |  |  |  | 6 | [14 empty] | 18
[5 empty] | POINT & PATCH | 5580 | SF | 8 | 167.4 | 0.03 | 0.6 | 3348 | 0.01 | 55.8 | 0 | 0 | 0 | 0 |  | 0 | 3403.8 |  | 18
[5 empty] | STANDARD RUB WALLS | 2790 | SF | 6 | 209.25 | 0.075 | 1.5 | 4185 | 0.03 | 83.7 | 0 | 0 | 0 | 0 |  | 0 | 4268.7 |  | 18
[5 empty] | CIRC WALLFORM: 4 - 8' | 5580 | SF | 6 | 892.8 | 0.16 | 3.2 | 17856 | 0.7 | 3906 | 0 | 0 | 1 | 5580 |  | 0 | 27342 |  | 18
[5 empty] | 10" TYPE 2 CIRC GANG CONST JT | 72 | LF | 6 | 42.48 | 0.59 | 11.8 | 849.6 | 3.16 | 227.52 | 0 | 0 | 2.5 | 180 |  | 0 | 1257.12 |  | 18
[5 empty] | PLACE WALLS | 86 | CY | 8 | 60.2 | 0.7 | 14 | 1204 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1204 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 86 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 9460 | 0 | 0 | 0 | 0 |  | 0 | 9460 |  | 18
|  |  |  | Grout |  |  |  | 6 | [14 empty] | 18
[5 empty] | FINISH GROUT - TANK BOTTOMS | 12720 | SF | 8 | 89.04 | 0.007 | 0.14 | 1780.8 | 0.02 | 254.4 | 0 | 0 | 0 | 0 |  | 0 | 2035.2 |  | 18
[5 empty] | FINISH GROUT - SUMPS/PITS | 16 | SF | 8 | 2 | 0.125 | 2.5 | 40 | 0.02 | 0.32 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 18
[5 empty] | ROUGH/CLEAN NEW CONC | 12736 | SF | 6 | 63.68 | 0.005 | 0.1 | 1273.6 | 0.01 | 127.36 | 0 | 0 | 0 | 0 |  | 0 | 1400.96 |  | 18
[5 empty] | PLACE GROUTING SCREEDS | 1 | LS | 8 | 160 | 160 | 3200 | 3200 |  | 0 |  | 0 |  | 0 |  | 0 | 3200 |  | 18
[5 empty] | PLACE GROUT - TANK BOTTOMS | 81 | CY | 8 | 81 | 1 | 20 | 1620 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1620 |  | 18
[5 empty] | PLACE GROUT - SUMPS/PITS | 1 | CY | 8 | 3 | 3 | 60 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 18
[5 empty] | PURCHASE: 2500 PSI GROUT | 82 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 9430 | 0 | 0 | 0 | 0 |  | 0 | 9430 |  | 18
|  |  |  | Slab for Metal Walkway - 2 EA (B/S40-102E) |  |  |  | 6 | [14 empty] | 18
[5 empty] | HAND PREP SUBGRADE-BUILDING | 24 | SF | 6 | 1.992 | 0.083 | 1.66 | 39.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39.84 |  | 18
[5 empty] | POINT & PATCH | 48 | SF | 8 | 2.016 | 0.042 | 0.84 | 40.32 | 0.01 | 0.48 | 0 | 0 | 0 | 0 |  | 0 | 40.8 |  | 18
[5 empty] | FINISH CONCRETE | 24 | SF | 8 | 1.992 | 0.083 | 1.66 | 39.84 | 0.02 | 0.48 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 18
[5 empty] | SLAB EDGEFORM | 48 | SF | 6 | 13.44 | 0.28 | 5.6 | 268.8 | 0.7 | 33.6 | 0 | 0 | 1 | 48 |  | 0 | 350.4 |  | 18
[5 empty] | SET ANCHOR BOLTS/ PAD | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 24 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 1.2 | 0 | 0 | 0 | 0 |  | 0 | 1.2 |  | 18
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 8 | 2 | 1 | 20 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 18
|  |  | (40-E) Scum Pump Station - 2 EA (D40-101E) |  |  |  |  | 6 | [14 empty] | 18
|  |  |  | Slab on Grade |  |  |  | 6 | [14 empty] | 18
[5 empty] | HAND PREP SUBGRADE-BUILDING | 112.5 | SF | 6 | 2.025 | 0.018 | 0.36 | 40.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.5 |  | 18
[5 empty] | POINT & PATCH | 65 | SF | 8 | 2.015 | 0.031 | 0.62 | 40.3 | 0.01 | 0.65 | 0 | 0 | 0 | 0 |  | 0 | 40.95 |  | 18
[5 empty] | FINISH CONCRETE | 112.5 | SF | 8 | 2.025 | 0.018 | 0.36 | 40.5 | 0.02 | 2.25 | 0 | 0 | 0 | 0 |  | 0 | 42.75 |  | 18
[5 empty] | SLAB EDGEFORM | 130 | SF | 6 | 31.2 | 0.24 | 4.8 | 624 | 0.7 | 91 | 0 | 0 | 1 | 130 |  | 0 | 845 |  | 18
[5 empty] | 1/2" JOINT SEALANT | 20 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 50 |  | 0 | 50 |  | 18
[5 empty] | SAW CUT CONCRETE | 20 | LF | 6 | 2.4 | 0.12 | 2.4 | 48 | 0.18 | 3.6 | 0 | 0 | 0.75 | 15 |  | 0 | 66.6 |  | 18
[5 empty] | RESTEEL DOBIE SUPPORTS | 112.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 5.625 | 0 | 0 | 0 | 0 |  | 0 | 5.625 |  | 18
[5 empty] | PLACE SLAB ON GRADE | 4 | CY | 8 | 2.8 | 0.7 | 14 | 56 | 0 | 0 |  | 0 |  | 0 |  | 0 | 56 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 18
|  |  |  | Equipment Pads - 2 EA |  |  |  | 6 | [14 empty] | 18
[5 empty] | POINT & PATCH CONC PAD | 27 | SF | 8 | 1.998 | 0.074 | 1.48 | 39.96 | 0.01 | 0.27 | 0 | 0 | 0 | 0 |  | 0 | 40.23 |  | 18
[5 empty] | TROWEL FINISH PADS | 22 | SF | 6 | 2.002 | 0.091 | 1.82 | 40.04 | 0.02 | 0.44 | 0 | 0 | 0 | 0 |  | 0 | 40.48 |  | 18
[5 empty] | RUB CONC PAD | 27 | SF | 6 | 1.998 | 0.074 | 1.48 | 39.96 | 0.03 | 0.81 | 0 | 0 | 0 | 0 |  | 0 | 40.77 |  | 18
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 22 | SF | 6 | 2.002 | 0.091 | 1.82 | 40.04 | 0.01 | 0.22 | 0 | 0 | 0 | 0 |  | 0 | 40.26 |  | 18
[5 empty] | PAD EDGEFORM | 27 | SF | 6 | 6.48 | 0.24 | 4.8 | 129.6 | 1 | 27 | 0 | 0 | 0 | 0 |  | 0 | 156.6 |  | 18
[5 empty] | SET ANCHOR BOLTS/ PAD | 8 | EA | 6 | 4.8 | 0.6 | 12 | 96 | 1.5 | 12 | 0 | 0 | 0 | 0 |  | 0 | 108 |  | 18
[5 empty] | PLACE PADS | 1 | CY | 8 | 4 | 4 | 80 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 18
|  |  |  | Pipe Supports - 4 EA |  |  |  | 6 | [14 empty] | 18
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 28.06 | SF | 8 | 1.9923 | 0.071 | 1.42 | 39.8452 | 0.01 | 0.2806 | 0 | 0 | 0 | 0 |  | 0 | 40.1258 |  | 18
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 2.68 | SF | 6 | 1.9993 | 0.746 | 14.92 | 39.9856 | 0.02 | 0.0536 | 0 | 0 | 0 | 0 |  | 0 | 40.0392 |  | 18
[5 empty] | RUB CONC PIPE SUPPORT | 28.06 | SF | 6 | 2.806 | 0.1 | 2 | 56.12 | 0.03 | 0.8418 | 0 | 0 | 0 | 0 |  | 0 | 56.9618 |  | 18
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 2.68 | SF | 6 | 1.9993 | 0.746 | 14.92 | 39.9856 | 0.01 | 0.0268 | 0 | 0 | 0 | 0 |  | 0 | 40.0124 |  | 18
[5 empty] | PIPE SUPPORT FORMWORK | 28.06 | SF | 6 | 5.8926 | 0.21 | 4.2 | 117.852 | 1 | 28.06 | 0 | 0 | 0 | 0 |  | 0 | 145.912 |  | 18
[5 empty] | FORM SMALL PIPE SADDLE 1' DIA | 4 | EA | 6 | 4 | 1 | 20 | 80 | 7.5 | 30 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 18
[5 empty] | PLACE PIPE SUPPORT | 1 | CY | 8 | 4 | 4 | 80 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 18
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 18
|  |  | (50-E) Filters / Rapid Mix Basin |  |  |  |  | 6
|  |  |  | Pipe Encasements - 7 EA |  |  |  | 6 | [14 empty] | 19
[5 empty] | HAND EXCAV PIPE ENCASE | 1.83 | CY | 6 | 3.66 | 2 | 40 | 73.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73.2 |  | 19
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 300 | SF | 6 | 36 | 0.12 | 2.4 | 720 | 1 | 300 | 0 | 0 | 1 | 300 |  | 0 | 1320 |  | 19
[5 empty] | RESTEEL DOBIE SUPPORTS | 150 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 7.5 | 0 | 0 | 0 | 0 |  | 0 | 7.5 |  | 19
[5 empty] | PLACE PIPE ENCASEMENT | 13 | CY | 8 | 7.8 | 0.6 | 12 | 156 | 0 | 0 |  | 0 |  | 0 |  | 0 | 156 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 13 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1430 | 0 | 0 | 0 | 0 |  | 0 | 1430 |  | 19
|  |  |  | 18" Slab on Grade |  |  |  | 6 | [14 empty] | 19
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1536.15 | SF | 6 | 24.5784 | 0.016 | 0.32 | 491.568 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 491.568 |  | 19
[5 empty] | POINT & PATCH | 248.79 | SF | 8 | 7.4637 | 0.03 | 0.6 | 149.274 | 0.01 | 2.4879 | 0 | 0 | 0 | 0 |  | 0 | 151.7619 |  | 19
[5 empty] | FINISH CONCRETE | 1536.15 | SF | 8 | 21.5061 | 0.014 | 0.28 | 430.122 | 0.02 | 30.723 | 0 | 0 | 0 | 0 |  | 0 | 460.845 |  | 19
[5 empty] | SLAB EDGEFORM | 248.79 | SF | 6 | 69.6612 | 0.28 | 5.6 | 1393.224 | 0.7 | 174.153 | 0 | 0 | 1 | 248.79 |  | 0 | 1816.167 |  | 19
[5 empty] | TYPE 1 SOG WALL BASE JT | 262 | LF | 6 | 123.14 | 0.47 | 9.4 | 2462.8 | 2.97 | 778.14 | 0 | 0 | 0 | 0 |  | 0 | 3240.94 |  | 19
[5 empty] | 18" TYPE 2 SOG CONST JT | 28 | LF | 6 | 20.44 | 0.73 | 14.6 | 408.8 | 3.7 | 103.6 | 0 | 0 | 2.5 | 70 |  | 0 | 582.4 |  | 19
[5 empty] | RESTEEL DOBIE SUPPORTS | 1536.15 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 76.8075 | 0 | 0 | 0 | 0 |  | 0 | 76.8075 |  | 19
[5 empty] | PLACE SLAB ON GRADE | 86 | CY | 8 | 51.6 | 0.6 | 12 | 1032 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1032 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 86 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 9460 | 0 | 0 | 0 | 0 |  | 0 | 9460 |  | 19
|  |  |  | Tall Tank Walls |  |  |  | 6 | [14 empty] | 19
[5 empty] | POINT & PATCH | 10858.37 | SF | 8 | 325.7511 | 0.03 | 0.6 | 6515.022 | 0.01 | 108.5837 | 0 | 0 | 0 | 0 |  | 0 | 6623.6057 |  | 19
[5 empty] | GANG WALLFORM: 16 - 20' | 191.7 | SF | 6 | 19.17 | 0.1 | 2 | 383.4 | 0.55 | 105.435 | 0 | 0 | 1 | 191.7 |  | 0 | 680.535 |  | 19
[5 empty] | GANG WALLFORM: 20+' | 10666.67 | SF | 6 | 1770.6672 | 0.166 | 3.32 | 35413.3444 | 0.55 | 5866.6685 | 0 | 0 | 1 | 10666.67 |  | 0 | 51946.6829 |  | 19
[5 empty] | 6"X6" CHAMFER / GANG | 36 | LF | 6 | 2.16 | 0.06 | 1.2 | 43.2 | 2.25 | 81 | 0 | 0 | 0 | 0 |  | 0 | 124.2 |  | 19
[5 empty] | FORM BOXOUT/ GANG | 143.64 | SF | 6 | 50.274 | 0.35 | 7 | 1005.48 | 1.5 | 215.46 | 0 | 0 | 0 | 0 |  | 0 | 1220.94 |  | 19
[5 empty] | FORM SLAB SLOT/ GANG | 110 | LF | 6 | 44 | 0.4 | 8 | 880 | 2.25 | 247.5 | 0 | 0 | 0 | 0 |  | 0 | 1127.5 |  | 19
[5 empty] | 12" TYPE 1 CIRC GANG WALL TO TROUGH SLAB CONST JT | 139 | LF | 6 | 23.63 | 0.17 | 3.4 | 472.6 | 2.01 | 279.39 | 0 | 0 | 0 | 0 |  | 0 | 751.99 |  | 18
[5 empty] | 16" TYPE 2 GANG WL CONST JT | 76 | LF | 6 | 60.04 | 0.79 | 15.8 | 1200.8 | 3.67 | 278.92 | 0 | 0 | 2.5 | 190 |  | 0 | 1669.72 |  | 19
[5 empty] | SET EMBED ANGLE/ GANG | 468 | LF | 6 | 93.6 | 0.2 | 4 | 1872 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1872 |  | 19
[5 empty] | GANG-PIPE PENET 12" DIA | 6 | EA | 6 | 4.8 | 0.8 | 16 | 96 | 7.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 141 |  | 19
[5 empty] | PLACE WALLS | 256 | CY | 8 | 179.2 | 0.7 | 14 | 3584 | 0 | 0 |  | 0 |  | 0 |  | 0 | 3584 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 256 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 28160 | 0 | 0 | 0 | 0 |  | 0 | 28160 |  | 19
|  |  |  | 18" Slab on Grade @ EL 95.83 |  |  |  | 6 | [14 empty] | 19
[5 empty] | HAND PREP SUBGRADE-BUILDING | 259.05 | SF | 6 | 4.1448 | 0.016 | 0.32 | 82.896 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 82.896 |  | 19
[5 empty] | POINT & PATCH | 97.77 | SF | 8 | 2.9331 | 0.03 | 0.6 | 58.662 | 0.01 | 0.9777 | 0 | 0 | 0 | 0 |  | 0 | 59.6397 |  | 19
[5 empty] | FINISH CONCRETE | 259.05 | SF | 8 | 3.6267 | 0.014 | 0.28 | 72.534 | 0.02 | 5.181 | 0 | 0 | 0 | 0 |  | 0 | 77.715 |  | 19
[5 empty] | SLAB EDGEFORM | 97.77 | SF | 6 | 27.3756 | 0.28 | 5.6 | 547.512 | 0.7 | 68.439 | 0 | 0 | 1 | 97.77 |  | 0 | 713.721 |  | 19
[5 empty] | TYPE 1 SOG WALL BASE JT | 46 | LF | 6 | 21.62 | 0.47 | 9.4 | 432.4 | 2.96 | 136.16 | 0 | 0 | 0 | 0 |  | 0 | 568.56 |  | 19
[5 empty] | RESTEEL DOBIE SUPPORTS | 259.05 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 12.9525 | 0 | 0 | 0 | 0 |  | 0 | 12.9525 |  | 19
[5 empty] | PLACE SLAB ON GRADE | 15 | CY | 8 | 9 | 0.6 | 12 | 180 | 0 | 0 |  | 0 |  | 0 |  | 0 | 180 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 15 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1650 | 0 | 0 | 0 | 0 |  | 0 | 1650 |  | 19
|  |  |  | Short Tank Walls |  |  |  | 6 | [14 empty] | 19
[5 empty] | POINT & PATCH | 1523.28 | SF | 8 | 45.6984 | 0.03 | 0.6 | 913.968 | 0.01 | 15.2328 | 0 | 0 | 0 | 0 |  | 0 | 929.2008 |  | 19
[5 empty] | GANG WALLFORM: 12 - 16' | 1523.28 | SF | 6 | 237.6317 | 0.156 | 3.12 | 4752.6336 | 0.55 | 837.804 | 0 | 0 | 1 | 1523.28 |  | 0 | 7113.7176 |  | 19
[5 empty] | 6"X6" CHAMFER / GANG | 3 | LF | 6 | 0.18 | 0.06 | 1.2 | 3.6 | 2.25 | 6.75 | 0 | 0 | 1 | 3 |  | 0 | 13.35 |  | 19
[5 empty] | FORM BOXOUT/ GANG | 30 | SF | 6 | 10.5 | 0.35 | 7 | 210 | 1.5 | 45 | 0 | 0 | 1 | 30 |  | 0 | 285 |  | 19
[5 empty] | TYPE 1 GANG WL CONST JT | 30 | LF | 6 | 23.7 | 0.79 | 15.8 | 474 | 3.67 | 110.1 | 0 | 0 | 2.5 | 75 |  | 0 | 659.1 |  | 19
[5 empty] | SET EMBED ANGLE/ GANG | 71 | LF | 6 | 14.2 | 0.2 | 4 | 284 | 0 | 0 | 0 | 0 | 2.5 | 177.5 |  | 0 | 461.5 |  | 19
[5 empty] | GANG-PIPE PENET 24" DIA | 2 | EA | 6 | 3 | 1.5 | 30 | 60 | 22.5 | 45 | 0 | 0 | 2.5 | 5 |  | 0 | 110 |  | 19
[5 empty] | PLACE WALLS | 31 | CY | 6 | 21.7 | 0.7 | 14 | 434 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 434 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 31 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 3410 | 0 | 0 | 0 | 0 |  | 0 | 3410 |  | 19
|  |  |  | 12" Effluent Channel Slab @ EL 104.38 |  |  |  | 6 | [14 empty] | 19
[5 empty] | HAND PREP SUBGRADE-BUILDING | 272.44 | SF | 6 | 4.359 | 0.016 | 0.32 | 87.1808 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 87.1808 |  | 19
[5 empty] | POINT & PATCH | 73 | SF | 8 | 2.19 | 0.03 | 0.6 | 43.8 | 0.01 | 0.73 | 0 | 0 | 0 | 0 |  | 0 | 44.53 |  | 19
[5 empty] | FINISH CONCRETE | 272.44 | SF | 8 | 3.8142 | 0.014 | 0.28 | 76.2832 | 0.02 | 5.4488 | 0 | 0 | 0 | 0 |  | 0 | 81.732 |  | 19
[5 empty] | SLAB EDGEFORM | 73 | SF | 6 | 17.52 | 0.24 | 4.8 | 350.4 | 0.7 | 51.1 | 0 | 0 | 1 | 73 |  | 0 | 474.5 |  | 19
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 70.5 | LF | 6 | 33.135 | 0.47 | 9.4 | 662.7 | 2.96 | 208.68 | 0 | 0 | 0 | 0 |  | 0 | 871.38 |  | 19
[5 empty] | 12" TYPE 1 SOG CONST JT | 4 | LF | 6 | 2.2 | 0.55 | 11 | 44 | 3.19 | 12.76 | 0 | 0 | 2.5 | 10 |  | 0 | 66.76 |  | 19
[5 empty] | RESTEEL DOBIE SUPPORTS | 272.44 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 13.622 | 0 | 0 | 0 | 0 |  | 0 | 13.622 |  | 19
[5 empty] | PLACE SLAB ON GRADE | 11 | CY | 8 | 7.7 | 0.7 | 14 | 154 | 0 | 0 |  | 0 |  | 0 |  | 0 | 154 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 11 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1210 | 0 | 0 | 0 | 0 |  | 0 | 1210 |  | 19
|  |  |  | 12" Effluent Channel Wall |  |  |  | 6 | [14 empty] | 19
[5 empty] | POINT & PATCH | 783.09 | SF | 8 | 23.4927 | 0.03 | 0.6 | 469.854 | 0.01 | 7.8309 | 0 | 0 | 0 | 0 |  | 0 | 477.6849 |  | 19
[5 empty] | GANG WALLFORM: 4 - 8' | 783.09 | SF | 6 | 62.6472 | 0.08 | 1.6 | 1252.944 | 0.55 | 430.6995 | 0 | 0 | 1 | 783.09 |  | 0 | 2466.7335 |  | 19
[5 empty] | 12" TYPE 2 GANG WL CONST JT | 5.62 | LF | 6 | 3.372 | 0.6 | 12 | 67.44 | 3.19 | 17.9278 | 0 | 0 | 2.5 | 14.05 |  | 0 | 99.4178 |  | 19
[5 empty] | SET EMBED ANGLE/ GANG | 66 | LF | 6 | 13.2 | 0.2 | 4 | 264 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 264 |  | 19
[5 empty] | PLACE WALLS | 15 | CY | 8 | 12 | 0.8 | 16 | 240 | 0 | 0 |  | 0 |  | 0 |  | 0 | 240 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 15 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1650 | 0 | 0 | 0 | 0 |  | 0 | 1650 |  | 19
|  |  |  | 12" Influent Channel Slab @ EL 106.50 |  |  |  | 6 | [14 empty] | 19
[5 empty] | HAND PREP SUBGRADE-BUILDING | 313.5 | SF | 6 | 5.016 | 0.016 | 0.32 | 100.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100.32 |  | 19
[5 empty] | POINT & PATCH | 68 | SF | 8 | 2.04 | 0.03 | 0.6 | 40.8 | 0.01 | 0.68 | 0 | 0 | 0 | 0 |  | 0 | 41.48 |  | 19
[5 empty] | FINISH CONCRETE | 313.5 | SF | 8 | 4.389 | 0.014 | 0.28 | 87.78 | 0.02 | 6.27 | 0 | 0 | 0 | 0 |  | 0 | 94.05 |  | 19
[5 empty] | SLAB EDGEFORM | 68 | SF | 6 | 16.32 | 0.24 | 4.8 | 326.4 | 0.7 | 47.6 | 0 | 0 | 1 | 68 |  | 0 | 442 |  | 19
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 70.5 | LF | 6 | 33.135 | 0.47 | 9.4 | 662.7 | 2.96 | 208.68 | 0 | 0 | 0 | 0 |  | 0 | 871.38 |  | 19
[5 empty] | 12" TYPE 1 SOG CONST JT | 5.5 | LF | 6 | 3.025 | 0.55 | 11 | 60.5 | 3.19 | 17.545 | 0 | 0 | 2.5 | 13.75 |  | 0 | 91.795 |  | 19
[5 empty] | RESTEEL DOBIE SUPPORTS | 313.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 15.675 | 0 | 0 | 0 | 0 |  | 0 | 15.675 |  | 19
[5 empty] | PLACE SLAB ON GRADE | 12 | CY | 8 | 8.4 | 0.7 | 14 | 168 | 0 | 0 |  | 0 |  | 0 |  | 0 | 168 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 12 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1320 | 0 | 0 | 0 | 0 |  | 0 | 1320 |  | 19
|  |  |  | 12" Influent Channel Wall |  |  |  | 6 | [14 empty] | 19
[5 empty] | POINT & PATCH | 1242 | SF | 8 | 37.26 | 0.03 | 0.6 | 745.2 | 0.01 | 12.42 | 0 | 0 | 0 | 0 |  | 0 | 757.62 |  | 19
[5 empty] | STANDARD RUB WALLS | 357.5 | SF | 6 | 26.8125 | 0.075 | 1.5 | 536.25 | 0.03 | 10.725 | 0 | 0 | 0 | 0 |  | 0 | 546.975 |  | 19
[5 empty] | GANG WALLFORM: 8 - 12' | 1242 | SF | 6 | 111.78 | 0.09 | 1.8 | 2235.6 | 0.55 | 683.1 | 0 | 0 | 1 | 1242 |  | 0 | 4160.7 |  | 19
[5 empty] | FORM BOXOUT/ GANG | 16.4 | SF | 6 | 5.74 | 0.35 | 7 | 114.8 | 1.5 | 24.6 | 0 | 0 | 0 | 0 |  | 0 | 139.4 |  | 19
[5 empty] | 12" TYPE 2 GANG WL CONST JT | 9 | LF | 6 | 5.4 | 0.6 | 12 | 108 | 3.19 | 28.71 | 0 | 0 | 2.5 | 22.5 |  | 0 | 159.21 |  | 19
[5 empty] | SET EMBED ANGLE/ GANG | 70 | LF | 6 | 14 | 0.2 | 4 | 280 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 280 |  | 19
[5 empty] | PLACE WALLS | 24 | CY | 8 | 19.2 | 0.8 | 16 | 384 | 0 | 0 |  | 0 |  | 0 |  | 0 | 384 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 24 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2640 | 0 | 0 | 0 | 0 |  | 0 | 2640 |  | 19
|  |  |  | Concrete Fill (Per Filter Manufacturer) |  |  |  | 6 | [14 empty] | 19
[5 empty] | FINISH GROUT - TANK BOTTOMS | 4909 | SF | 8 | 34.363 | 0.007 | 0.14 | 687.26 | 0.02 | 98.18 | 0 | 0 | 0 | 0 |  | 0 | 785.44 |  | 19
[5 empty] | ROUGH/CLEAN NEW CONC | 4909 | SF | 6 | 53.999 | 0.011 | 0.22 | 1079.98 | 0.01 | 49.09 | 0 | 0 | 0 | 0 |  | 0 | 1129.07 |  | 19
[5 empty] | FORM GROUT - TANK BOTTOM | 234 | SF | 6 | 71.37 | 0.305 | 6.1 | 1427.4 | 1.5 | 351 | 0 | 0 | 0 | 0 |  | 0 | 1778.4 |  | 19
[5 empty] | PLACE GROUT - TANK BOTTOMS | 86 | CY | 8 | 51.6 | 0.6 | 12 | 1032 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1032 |  | 19
[5 empty] | PURCHASE: 2500 PSI GROUT | 86 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 9890 | 0 | 0 | 0 | 0 |  | 0 | 9890 |  | 19
|  |  |  | Equipment Pads - 6 EA |  |  |  | 6 | [14 empty] | 19
[5 empty] | POINT & PATCH CONC PAD | 32.04 | SF | 8 | 1.9865 | 0.062 | 1.24 | 39.7296 | 0.01 | 0.3204 | 0 | 0 | 0 | 0 |  | 0 | 40.05 |  | 19
[5 empty] | TROWEL FINISH PADS | 42.77 | SF | 6 | 2.9511 | 0.069 | 1.38 | 59.0226 | 0.02 | 0.8554 | 0 | 0 | 0 | 0 |  | 0 | 59.878 |  | 19
[5 empty] | RUB CONC PAD | 32.04 | SF | 6 | 3.204 | 0.1 | 2 | 64.08 | 0.03 | 0.9612 | 0 | 0 | 0 | 0 |  | 0 | 65.0412 |  | 19
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 42.77 | SF | 6 | 2.0102 | 0.047 | 0.94 | 40.2038 | 0.01 | 0.4277 | 0 | 0 | 0 | 0 |  | 0 | 40.6315 |  | 19
[5 empty] | PAD EDGEFORM | 64.08 | SF | 6 | 15.3792 | 0.24 | 4.8 | 307.584 | 1 | 64.08 | 0 | 0 | 0 | 0 |  | 0 | 371.664 |  | 19
[5 empty] | SET ANCHOR BOLTS/ PAD | 24 | EA | 6 | 14.4 | 0.6 | 12 | 288 | 1.5 | 36 | 0 | 0 | 0 | 0 |  | 0 | 324 |  | 19
[5 empty] | PLACE PADS | 1 | CY | 8 | 4 | 4 | 80 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 19
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 19
|  |  | (60-E) C.C Tank / Eff. Trans. P.S. |  |  |  |  | 6
|  |  |  | Pipe Encasements - 2 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 0.89 | CY | 6 | 1.958 | 2.2 | 44 | 39.16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39.16 |  | 20
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 146.4 | SF | 6 | 17.568 | 0.12 | 2.4 | 351.36 | 1 | 146.4 | 0 | 0 | 1 | 146.4 |  | 0 | 644.16 |  | 20
[5 empty] | PIPE ENCASE FORMWK - VERT 9.5 | 69.54 | SF | 6 | 16.6896 | 0.24 | 4.8 | 333.792 | 1 | 69.54 | 0 | 0 | 1 | 69.54 |  | 0 | 472.872 |  | 20
[5 empty] | RESTEEL DOBIE SUPPORTS | 73.2 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 3.66 | 0 | 0 | 0 | 0 |  | 0 | 3.66 |  | 20
[5 empty] | PLACE PIPE ENCASEMENT | 6 | CY | 8 | 6 | 1 | 20 | 120 | 0 | 0 |  | 0 |  | 0 |  | 0 | 120 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 6 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 660 | 0 | 0 | 0 | 0 |  | 0 | 660 |  | 20
|  |  |  | 14" Slab on Grade @ EL 96.5 |  |  |  | 6 | [14 empty] | 20
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1436.42 | SF | 6 | 22.9827 | 0.016 | 0.32 | 459.6544 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 459.6544 |  | 20
[5 empty] | POINT & PATCH | 191.48 | SF | 8 | 5.7444 | 0.03 | 0.6 | 114.888 | 0.01 | 1.9148 | 0 | 0 | 0 | 0 |  | 0 | 116.8028 |  | 20
[5 empty] | FINISH CONCRETE | 1436.42 | SF | 8 | 20.1099 | 0.014 | 0.28 | 402.1976 | 0.02 | 28.7284 | 0 | 0 | 0 | 0 |  | 0 | 430.926 |  | 20
[5 empty] | SLAB EDGEFORM | 191.48 | SF | 6 | 53.6144 | 0.28 | 5.6 | 1072.288 | 0.7 | 134.036 | 0 | 0 | 1 | 191.48 |  | 0 | 1397.804 |  | 20
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 181 | LF | 6 | 85.07 | 0.47 | 9.4 | 1701.4 | 2.96 | 535.76 | 0 | 0 | 0 | 0 |  | 0 | 2237.16 |  | 20
[5 empty] | 14" TYPE 1 SOG CONST JT | 25.5 | LF | 6 | 18.615 | 0.73 | 14.6 | 372.3 | 3.7 | 94.35 | 0 | 0 | 2.5 | 63.75 |  | 0 | 530.4 |  | 20
[5 empty] | RESTEEL DOBIE SUPPORTS | 1436.42 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 71.821 | 0 | 0 | 0 | 0 |  | 0 | 71.821 |  | 20
[5 empty] | PLACE SLAB ON GRADE | 63 | CY | 8 | 37.8 | 0.6 | 12 | 756 | 0 | 0 |  | 0 |  | 0 |  | 0 | 756 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 63 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6930 | 0 | 0 | 0 | 0 |  | 0 | 6930 |  | 20
|  |  |  | 14" Slab on Grade @ EL 99 |  |  |  | 6 | [14 empty] | 20
[5 empty] | HAND PREP SUBGRADE-BUILDING | 5097.87 | SF | 6 | 81.5659 | 0.016 | 0.32 | 1631.3184 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1631.3184 |  | 20
[5 empty] | POINT & PATCH | 343.58 | SF | 8 | 10.3074 | 0.03 | 0.6 | 206.148 | 0.01 | 3.4358 | 0 | 0 | 0 | 0 |  | 0 | 209.5838 |  | 20
[5 empty] | FINISH CONCRETE | 5097.87 | SF | 8 | 71.3702 | 0.014 | 0.28 | 1427.4036 | 0.02 | 101.9574 | 0 | 0 | 0 | 0 |  | 0 | 1529.361 |  | 20
[5 empty] | SLAB EDGEFORM | 343.58 | SF | 6 | 96.2024 | 0.28 | 5.6 | 1924.048 | 0.7 | 240.506 | 0 | 0 | 1 | 343.58 |  | 0 | 2508.134 |  | 20
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 368 | LF | 6 | 172.96 | 0.47 | 9.4 | 3459.2 | 2.96 | 1089.28 | 0 | 0 | 0 | 0 |  | 0 | 4548.48 |  | 20
[5 empty] | 14" TYPE 1 SOG CONST JT | 203.2 | LF | 6 | 148.336 | 0.73 | 14.6 | 2966.72 | 3.7 | 751.84 | 0 | 0 | 2.5 | 508 |  | 0 | 4226.56 |  | 20
[5 empty] | RESTEEL DOBIE SUPPORTS | 5097.87 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 254.8935 | 0 | 0 | 0 | 0 |  | 0 | 254.8935 |  | 20
[5 empty] | PLACE SLAB ON GRADE | 232 | CY | 8 | 139.2 | 0.6 | 12 | 2784 | 0 | 0 |  | 0 |  | 0 |  | 0 | 2784 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 232 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 25520 | 0 | 0 | 0 | 0 |  | 0 | 25520 |  | 20
|  |  |  | 12" Tank Walls |  |  |  | 6 | [14 empty] | 20
[5 empty] | POINT & PATCH | 1740 | SF | 8 | 52.2 | 0.03 | 0.6 | 1044 | 0.01 | 17.4 | 0 | 0 | 0 | 0 |  | 0 | 1061.4 |  | 20
[5 empty] | POINT & PATCH | 8737.02 | SF | 8 | 262.1106 | 0.03 | 0.6 | 5242.212 | 0.01 | 87.3702 | 0 | 0 | 0 | 0 |  | 0 | 5329.5822 |  | 20
[5 empty] | WALLFORM: 4 - 8' | 777.01 | SF | 6 | 93.2412 | 0.12 | 2.4 | 1864.824 | 0.7 | 543.907 | 0 | 0 | 1 | 777.01 |  | 0 | 3185.741 |  | 20
[5 empty] | WALLFORM: 8 - 12' | 6829.26 | SF | 6 | 717.0723 | 0.105 | 2.1 | 14341.446 | 0.7 | 4780.482 | 0 | 0 | 1 | 6829.26 |  | 0 | 25951.188 |  | 20
[5 empty] | WALLFORM: 12 - 16' | 2870.75 | SF | 6 | 373.1975 | 0.13 | 2.6 | 7463.95 | 0.7 | 2009.525 | 0 | 0 | 1 | 2870.75 |  | 0 | 12344.225 |  | 20
[5 empty] | STRAIGHT WALL END FORMS | 12.5 | SF | 6 | 3.5875 | 0.287 | 5.74 | 71.75 | 1.091 | 13.6375 | 0 | 0 | 0 | 0 |  | 0 | 85.3875 |  | 20
[5 empty] | 12" TYPE 2 STRAIT WL CONST JT | 101.5 | LF | 6 | 59.885 | 0.59 | 11.8 | 1197.7 | 3.16 | 320.74 | 0 | 0 | 2.5 | 253.75 |  | 0 | 1772.19 |  | 20
[5 empty] | 6"X6" CHAMFER / STR WALL | 66.5 | LF | 6 | 3.99 | 0.06 | 1.2 | 79.8 | 2.25 | 149.625 | 0 | 0 | 0 | 0 |  | 0 | 229.425 |  | 20
[5 empty] | STR WALL-PIPE PENET 13-36" DIA | 2 | EA | 6 | 3 | 1.5 | 30 | 60 | 22.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 105 |  | 20
[5 empty] | STR WALL-PIPE PENET 13-36" DIA | 2 | EA | 6 | 3 | 1.5 | 30 | 60 | 22.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 105 |  | 20
[5 empty] | PLACE WALLS | 195 | CY | 8 | 136.5 | 0.7 | 14 | 2730 | 0 | 0 |  | 0 |  | 0 |  | 0 | 2730 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 195 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 21450 | 0 | 0 | 0 | 0 |  | 0 | 21450 |  | 20
|  |  |  | 12" x 12" Columns (1/S60-102E) |  |  |  | 6 | [14 empty] | 20
[5 empty] | POINT & PATCH | 52.08 | SF | 8 | 1.979 | 0.038 | 0.76 | 39.5808 | 0.01 | 0.5208 | 0 | 0 | 0 | 0 |  | 0 | 40.1016 |  | 20
[5 empty] | PIER FORM: 4'-6' PERIM | 52.08 | SF | 6 | 13.697 | 0.263 | 5.26 | 273.9408 | 0.818 | 42.6014 | 0 | 0 | 1 | 52.08 |  | 0 | 368.6222 |  | 20
[5 empty] | PLACE PIERS | 1 | CY | 8 | 3 | 3 | 60 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 20
|  |  |  | 12" Walkway |  |  |  | 6 | [14 empty] | 20
[5 empty] | POINT & PATCH | 190.5 | SF | 8 | 5.715 | 0.03 | 0.6 | 114.3 | 0.01 | 1.905 | 0 | 0 | 0 | 0 |  | 0 | 116.205 |  | 20
[5 empty] | FINISH CONCRETE | 432.75 | SF | 8 | 6.0585 | 0.014 | 0.28 | 121.17 | 0.02 | 8.655 | 0 | 0 | 0 | 0 |  | 0 | 129.825 |  | 20
[5 empty] | RUB CONC SUPP SLAB EDGES | 190.5 | SF | 6 | 19.05 | 0.1 | 2 | 381 | 0.03 | 5.715 | 0 | 0 | 0 | 0 |  | 0 | 386.715 |  | 20
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 432.75 | SF | 6 | 4.7603 | 0.011 | 0.22 | 95.205 | 0.02 | 8.655 | 0 | 0 | 0 | 0 |  | 0 | 103.86 |  | 20
[5 empty] | WALKWAY/TROUGH SOFFIT: 8 - 12' | 432.75 | SF | 6 | 233.685 | 0.54 | 10.8 | 4673.7 | 1.5 | 649.125 | 0 | 0 | 0.675 | 292.1063 |  | 0 | 5614.9312 |  | 20
[5 empty] | WALKWAY/TROUGH EDGE FORM | 190.5 | SF | 6 | 41.7195 | 0.219 | 4.38 | 834.39 | 1.35 | 257.175 | 0 | 0 | 0 | 0 |  | 0 | 1091.565 |  | 20
[5 empty] | 1/2" JOINT SEALANT | 9 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 22.5 |  | 0 | 22.5 |  | 20
[5 empty] | 12" TYPE 1 WKY/TROUGH CNTRL JT | 9 | LF | 6 | 4.95 | 0.55 | 11 | 99 | 3.19 | 28.71 | 0 | 0 | 2.5 | 22.5 |  | 0 | 150.21 |  | 20
[5 empty] | SAW CUT CONCRETE | 9 | LF | 6 | 1.998 | 0.222 | 4.44 | 39.96 | 0.18 | 1.62 | 0 | 0 | 0.75 | 6.75 |  | 0 | 48.33 |  | 20
[5 empty] | RESTEEL DOBIE SUPPORTS | 432.75 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 21.6375 | 0 | 0 | 0 | 0 |  | 0 | 21.6375 |  | 20
[5 empty] | PLACE WALKWAY/TROUGH | 17 | CY | 8 | 11.9 | 0.7 | 14 | 238 | 0 | 0 |  | 0 |  | 0 |  | 0 | 238 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 17 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1870 | 0 | 0 | 0 | 0 |  | 0 | 1870 |  | 20
|  |  |  | 12" Top Slab |  |  |  | 6 | [14 empty] | 20
[5 empty] | POINT & PATCH | 272.66 | SF | 8 | 8.1798 | 0.03 | 0.6 | 163.596 | 0.01 | 2.7266 | 0 | 0 | 0 | 0 |  | 0 | 166.3226 |  | 20
[5 empty] | FINISH CONCRETE | 1226.59 | SF | 8 | 17.1723 | 0.014 | 0.28 | 343.4452 | 0.02 | 24.5318 | 0 | 0 | 0 | 0 |  | 0 | 367.977 |  | 20
[5 empty] | RUB CONC SUPP SLAB EDGES | 152.66 | SF | 6 | 15.266 | 0.1 | 2 | 305.32 | 0.03 | 4.5798 | 0 | 0 | 0 | 0 |  | 0 | 309.8998 |  | 20
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 1226.59 | SF | 6 | 13.4925 | 0.011 | 0.22 | 269.8498 | 0.02 | 24.5318 | 0 | 0 | 0 | 0 |  | 0 | 294.3816 |  | 20
[5 empty] | BEAM W/ SLAB SOFFIT: 12 - 16' | 60 | SF | 6 | 36 | 0.6 | 12 | 720 | 2 | 120 | 0 | 0 | 2.6 | 156 |  | 0 | 996 |  | 20
[5 empty] | INTERIOR BEAM SIDES | 120 | SF | 6 | 30 | 0.25 | 5 | 600 | 1.5 | 180 | 0 | 0 | 0 | 0 |  | 0 | 780 |  | 20
[5 empty] | SHORED SOFFIT FORM: 12 - 16' | 1226.59 | SF | 6 | 527.4337 | 0.43 | 8.6 | 10548.674 | 2 | 2453.18 | 0 | 0 | 1.375 | 1686.5612 |  | 0 | 14688.4152 |  | 20
[5 empty] | SHORED SLAB EDGE FORM | 152.66 | SF | 6 | 33.5852 | 0.22 | 4.4 | 671.704 | 1.8 | 274.788 | 0 | 0 | 0 | 0 |  | 0 | 946.492 |  | 20
[5 empty] | SET EMBED ANGLE/ SLAB | 40 | LF | 6 | 8 | 0.2 | 4 | 160 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 |  | 20
[5 empty] | RESTEEL DOBIE SUPPORTS | 1226.59 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 61.3295 | 0 | 0 | 0 | 0 |  | 0 | 61.3295 |  | 20
[5 empty] | PLACE SHORED SLAB/BEAM | 48 | CY | 8 | 33.6 | 0.7 | 14 | 672 | 0 | 0 |  | 0 |  | 0 |  | 0 | 672 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 48 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 5280 | 0 | 0 | 0 | 0 |  | 0 | 5280 |  | 20
|  |  |  | Pipe Supports - 10 EA |  |  |  | 6 | [14 empty] | 20
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 136.2 | SF | 8 | 2.9964 | 0.022 | 0.44 | 59.928 | 0.01 | 1.362 | 0 | 0 | 0 | 0 |  | 0 | 61.29 |  | 20
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 16.54 | SF | 6 | 2.051 | 0.124 | 2.48 | 41.0192 | 0.02 | 0.3308 | 0 | 0 | 0 | 0 |  | 0 | 41.35 |  | 20
[5 empty] | RUB CONC PIPE SUPPORT | 136.2 | SF | 6 | 13.62 | 0.1 | 2 | 272.4 | 0.03 | 4.086 | 0 | 0 | 0 | 0 |  | 0 | 276.486 |  | 20
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 16.54 | SF | 6 | 2.0013 | 0.121 | 2.42 | 40.0268 | 0.01 | 0.1654 | 0 | 0 | 0 | 0 |  | 0 | 40.1922 |  | 20
[5 empty] | PIPE SUPPORT FORMWORK | 136.2 | SF | 6 | 28.602 | 0.21 | 4.2 | 572.04 | 1 | 136.2 | 0 | 0 | 0 | 0 |  | 0 | 708.24 |  | 20
[5 empty] | FORM MEDIUM PIPE SADDLE 2' DIA | 6 | EA | 6 | 12 | 2 | 40 | 240 | 15 | 90 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 20
[5 empty] | FORM LARGE PIPE SADDLE 3'+ DIA | 4 | EA | 6 | 16 | 4 | 80 | 320 | 22.5 | 90 | 0 | 0 | 0 | 0 |  | 0 | 410 |  | 20
[5 empty] | PLACE PIPE SUPPORT | 2 | CY | 8 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 20
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 20
|  |  |  | Grout |  |  |  | 6 | [14 empty] | 20
[5 empty] | FINISH GROUT - TANK BOTTOMS | 1057.01 | SF | 8 | 7.3991 | 0.007 | 0.14 | 147.9814 | 0.02 | 21.1402 | 0 | 0 | 0 | 0 |  | 0 | 169.1216 |  | 20
[5 empty] | ROUGH/CLEAN NEW CONC | 1057.01 | SF | 6 | 11.6271 | 0.011 | 0.22 | 232.5422 | 0.01 | 10.5701 | 0 | 0 | 0 | 0 |  | 0 | 243.1123 |  | 20
[5 empty] | PLACE GROUT - TANK BOTTOMS | 14 | CY | 8 | 9.8 | 0.7 | 14 | 196 | 0 | 0 |  | 0 |  | 0 |  | 0 | 196 |  | 20
[5 empty] | PURCHASE: 2500 PSI GROUT | 14 | CY | 6 | 0 | 0 | 0 | 0 | 115 | 1610 | 0 | 0 | 0 | 0 |  | 0 | 1610 |  | 20
|  |  | (80-E) Reclaimed Water PS No. 2 |  |  |  |  | 6
|  |  |  | 30" Lock Slab |  |  |  | 6
[5 empty] | HAND EXCAV COLUMN FTG | 0.61 | CY | 6 | 1.9965 | 3.273 | 65.46 | 39.9306 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39.9306 |  | 21
[5 empty] | FINISH TOP FTG/PILE CAP | 50 | SF | 8 | 2 | 0.04 | 0.8 | 40 | 0.02 | 1 | 0 | 0 | 0 | 0 |  | 0 | 41 |  | 21
[5 empty] | COLUMN FTG EDGEFORM | 100 | SF | 6 | 24 | 0.24 | 4.8 | 480 | 0.45 | 45 | 0 | 0 | 1 | 100 |  | 0 | 625 |  | 21
[5 empty] | 8 " TYPE 1 SOG WALL BASE JT | 20 | LF | 6 | 9.4 | 0.47 | 9.4 | 188 | 2.96 | 59.2 | 0 | 0 | 0 | 0 |  | 0 | 247.2 |  | 21
[5 empty] | RESTEEL DOBIE SUPPORTS | 50 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 2.5 | 0 | 0 | 0 | 0 |  | 0 | 2.5 |  | 21
[5 empty] | PLACE COLUMN FOOTING | 5 | CY | 8 | 10 | 2 | 40 | 200 | 0 | 0 |  | 0 |  | 0 |  | 0 | 200 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 5 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 550 | 0 | 0 | 0 | 0 |  | 0 | 550 |  | 21
|  |  |  | 8" Pump Can Walls |  |  |  | 6 | [14 empty] | 21
[5 empty] | SET PUMP CAN | 3 | EA | 6 | 24 | 8 | 160 | 480 |  | 0 |  | 0 |  | 0 |  | 0 | 480 |  | 21
[5 empty] | PIPE ENCASE FORMWK - VERT 14.5 | 444.28 | SF | 6 | 106.6272 | 0.24 | 4.8 | 2132.544 | 1 | 444.28 | 0 | 0 | 1 | 444.28 |  | 0 | 3021.104 |  | 21
[5 empty] | PLACE PIPE ENCASEMENT | 11 | CY | 8 | 11 | 1 | 20 | 220 | 0 | 0 |  | 0 |  | 0 |  | 0 | 220 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 11 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1210 | 0 | 0 | 0 | 0 |  | 0 | 1210 |  | 21
|  |  |  | 12" Slab on Grade |  |  |  | 6 | [14 empty] | 21
[5 empty] | HAND PREP SUBGRADE-BUILDING | 537.5 | SF | 6 | 8.6 | 0.016 | 0.32 | 172 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 172 |  | 21
[5 empty] | POINT & PATCH | 93 | SF | 8 | 2.79 | 0.03 | 0.6 | 55.8 | 0.01 | 0.93 | 0 | 0 | 0 | 0 |  | 0 | 56.73 |  | 21
[5 empty] | FINISH CONCRETE | 537.5 | SF | 8 | 7.525 | 0.014 | 0.28 | 150.5 | 0.02 | 10.75 | 0 | 0 | 0 | 0 |  | 0 | 161.25 |  | 21
[5 empty] | SLAB EDGEFORM | 93 | SF | 6 | 22.32 | 0.24 | 4.8 | 446.4 | 0.7 | 65.1 | 0 | 0 | 1 | 93 |  | 0 | 604.5 |  | 21
[5 empty] | RESTEEL DOBIE SUPPORTS | 537.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 26.875 | 0 | 0 | 0 | 0 |  | 0 | 26.875 |  | 21
[5 empty] | PLACE SLAB ON GRADE | 20 | CY | 8 | 12 | 0.6 | 12 | 240 | 0 | 0 |  | 0 |  | 0 |  | 0 | 240 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 20 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2200 | 0 | 0 | 0 | 0 |  | 0 | 2200 |  | 21
|  |  |  | Pipe Supports - 2 EA |  |  |  | 6 | [14 empty] | 21
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 38.4 | SF | 8 | 1.9968 | 0.052 | 1.04 | 39.936 | 0.01 | 0.384 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 21
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 4.25 | SF | 6 | 2.0017 | 0.471 | 9.42 | 40.035 | 0.02 | 0.085 | 0 | 0 | 0 | 0 |  | 0 | 40.12 |  | 21
[5 empty] | RUB CONC PIPE SUPPORT | 38.4 | SF | 6 | 3.84 | 0.1 | 2 | 76.8 | 0.03 | 1.152 | 0 | 0 | 0 | 0 |  | 0 | 77.952 |  | 21
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 4.25 | SF | 6 | 2.0017 | 0.471 | 9.42 | 40.035 | 0.01 | 0.0425 | 0 | 0 | 0 | 0 |  | 0 | 40.0775 |  | 21
[5 empty] | PIPE SUPPORT FORMWORK | 38.4 | SF | 6 | 8.064 | 0.21 | 4.2 | 161.28 | 1 | 38.4 | 0 | 0 | 0 | 0 |  | 0 | 199.68 |  | 21
[5 empty] | FORM LARGE PIPE SADDLE 3'+ DIA | 2 | EA | 6 | 8 | 4 | 80 | 160 | 22.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 205 |  | 21
[5 empty] | PLACE PIPE SUPPORT | 1 | CY | 8 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 21
6
|  |  |  | 6" HVAC Slab |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 530.5 | SF | 6 | 8.488 | 0.016 | 0.32 | 169.76 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 169.76 |  | 21
[5 empty] | POINT & PATCH | 114.5 | SF | 6 | 3.435 | 0.03 | 0.6 | 68.7 | 0.01 | 1.145 | 0 | 0 | 0 | 0 |  | 0 | 69.845 |  | 21
[5 empty] | FINISH CONCRETE | 530.5 | SF | 6 | 7.427 | 0.014 | 0.28 | 148.54 | 0.02 | 10.61 | 0 | 0 | 0 | 0 |  | 0 | 159.15 |  | 21
[5 empty] | SLAB EDGEFORM | 229 | SF | 6 | 54.96 | 0.24 | 4.8 | 1099.2 | 0.7 | 160.3 | 0 | 0 | 1 | 229 |  | 0 | 1488.5 |  | 21
[5 empty] | RESTEEL DOBIE SUPPORTS | 530.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 26.525 | 0 | 0 | 0 | 0 |  | 0 | 26.525 |  | 21
[5 empty] | PLACE SLAB ON GRADE | 10 | CY | 6 | 7.5 | 0.75 | 15 | 150 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 150 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 10 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1100 | 0 | 0 | 0 | 0 |  | 0 | 1100 |  | 21
0
|  |  |  | 6" Curb Wall for AC Unit - 2' tall |  |  |  | 6 | [14 empty] | 21
[5 empty] | POINT & PATCH | 268 | SF | 6 | 8.04 | 0.03 | 0.6 | 160.8 | 0.01 | 2.68 | 0 | 0 | 0 | 0 |  | 0 | 163.48 |  | 21
[5 empty] | STANDARD RUB WALLS | 134 | SF | 6 | 10.05 | 0.075 | 1.5 | 201 | 0.03 | 4.02 | 0 | 0 | 0 | 0 |  | 0 | 205.02 |  | 21
[5 empty] | WALLFORM: 0 - 4' | 268 | SF | 6 | 42.88 | 0.16 | 3.2 | 857.6 | 0.7 | 187.6 | 0 | 0 | 1 | 268 |  | 0 | 1313.2 |  | 21
[5 empty] | FORM BOXOUT/ STRAIGHT WALL | 40 | SF | 6 | 14 | 0.35 | 7 | 280 | 1.5 | 60 | 0 | 0 | 0 | 0 |  | 0 | 340 |  | 21
[5 empty] | PLACE WALLS | 3 | CY | 6 | 3 | 1 | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 60 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 21
|  |  |  | 6" HVAC Top Slab |  |  |  | 6 | [14 empty] | 21
[5 empty] | POINT & PATCH | 25.66 | SF | 8 | 2.0528 | 0.08 | 1.6 | 41.056 | 0.01 | 0.2566 | 0 | 0 | 0 | 0 |  | 0 | 41.3126 |  | 21
[5 empty] | FINISH CONCRETE | 78.47 | SF | 8 | 2.0402 | 0.026 | 0.52 | 40.8044 | 0.02 | 1.5694 | 0 | 0 | 0 | 0 |  | 0 | 42.3738 |  | 21
[5 empty] | RUB CONC SUPP SLAB EDGES | 51.32 | SF | 6 | 5.132 | 0.1 | 2 | 102.64 | 0.03 | 1.5396 | 0 | 0 | 0 | 0 |  | 0 | 104.1796 |  | 21
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 78.47 | SF | 6 | 1.9618 | 0.025 | 0.5 | 39.235 | 0.02 | 1.5694 | 0 | 0 | 0 | 0 |  | 0 | 40.8044 |  | 21
[5 empty] | SUSPENDED SOFFIT FORM: 0-4' | 78.47 | SF | 6 | 11.7705 | 0.15 | 3 | 235.41 | 1.75 | 137.3225 | 0 | 0 | 0.45 | 35.3115 |  | 0 | 408.044 |  | 21
[5 empty] | SUSPENDED SLAB EDGE FORM | 51.32 | SF | 6 | 11.2904 | 0.22 | 4.4 | 225.808 | 1.575 | 80.829 | 0 | 0 | 0 | 0 |  | 0 | 306.637 |  | 21
[5 empty] | FORM BOXOUT/SUSPEND SLAB | 42.34 | SF | 6 | 12.702 | 0.3 | 6 | 254.04 | 1.5 | 63.51 | 0 | 0 | 0 | 0 |  | 0 | 317.55 |  | 21
[5 empty] | RESTEEL DOBIE SUPPORTS | 78.47 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 3.9235 | 0 | 0 | 0 | 0 |  | 0 | 3.9235 |  | 21
[5 empty] | PLACE SUSPEND SLAB | 2 | CY | 8 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 21
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 21
|  |  | (90-E) Chemical Feed Building |  |  |  |  | 6
|  |  |  | 24" Footings |  |  |  | 6
[5 empty] | HAND EXCAV COLUMN FTG | 3.35 | CY | 6 | 6.7 | 2 | 40 | 134 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 134 |  | 22
[5 empty] | FINISH TOP FTG/PILE CAP | 274 | SF | 8 | 7.672 | 0.028 | 0.56 | 153.44 | 0.02 | 5.48 | 0 | 0 | 0 | 0 |  | 0 | 158.92 |  | 22
[5 empty] | COLUMN FTG EDGEFORM | 624 | SF | 6 | 149.76 | 0.24 | 4.8 | 2995.2 | 0.45 | 280.8 | 0 | 0 | 1 | 624 |  | 0 | 3900 |  | 22
[5 empty] | RESTEEL DOBIE SUPPORTS | 274 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 13.7 | 0 | 0 | 0 | 0 |  | 0 | 13.7 |  | 22
[5 empty] | PLACE COLUMN FOOTING | 31 | CY | 8 | 18.6 | 0.6 | 12 | 372 | 0 | 0 |  | 0 |  | 0 |  | 0 | 372 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 31 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 3410 | 0 | 0 | 0 | 0 |  | 0 | 3410 |  | 22
|  |  |  | Sump Box Slab |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 18.75 | SF | 6 | 2.0625 | 0.11 | 2.2 | 41.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 41.25 |  | 22
[5 empty] | POINT & PATCH | 11.6 | SF | 6 | 1.972 | 0.17 | 3.4 | 39.44 | 0.01 | 0.116 | 0 | 0 | 0 | 0 |  | 0 | 39.556 |  | 22
[5 empty] | FINISH CONCRETE | 18.75 | SF | 6 | 2.0625 | 0.11 | 2.2 | 41.25 | 0.02 | 0.375 | 0 | 0 | 0 | 0 |  | 0 | 41.625 |  | 22
[5 empty] | SLAB EDGEFORM | 17.32 | SF | 6 | 4.1568 | 0.24 | 4.8 | 83.136 | 0.7 | 12.124 | 0 | 0 | 1 | 17.32 |  | 0 | 112.58 |  | 22
[5 empty] | 12" TYPE 1 SOG WALL BASE JT | 14 | LF | 6 | 6.58 | 0.47 | 9.4 | 131.6 | 2.96 | 41.44 | 0 | 0 | 0 | 0 |  | 0 | 173.04 |  | 22
[5 empty] | RESTEEL DOBIE SUPPORTS | 18.75 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 0.9375 | 0 | 0 | 0 | 0 |  | 0 | 0.9375 |  | 22
[5 empty] | PLACE SLAB ON GRADE | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 22
|  |  |  | Sump Box Walls |  |  |  | 6
[5 empty] | POINT & PATCH | 58.8 | SF | 6 | 2.058 | 0.035 | 0.7 | 41.16 | 0.01 | 0.588 | 0 | 0 | 0 | 0 |  | 0 | 41.748 |  | 22
[5 empty] | WALLFORM: 0 - 4' | 58.8 | SF | 6 | 9.408 | 0.16 | 3.2 | 188.16 | 0.7 | 41.16 | 0 | 0 | 1 | 58.8 |  | 0 | 288.12 |  | 22
[5 empty] | PLACE WALLS | 1 | CY | 6 | 3 | 3 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 60 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 22
6
|  |  |  | Storage Tank Pads - 3 EA |  |  |  | 6 | [14 empty] | 22
[5 empty] | HAND PREP SUBGRADE-BUILDING | 363 | SF | 6 | 5.808 | 0.016 | 0.32 | 116.16 |  | 0 |  | 0 |  | 0 |  | 0 | 116.16 |  | 22
[5 empty] | POINT & PATCH CONC PAD | 175.56 | SF | 8 | 3.8623 | 0.022 | 0.44 | 77.2464 | 0.01 | 1.7556 | 0 | 0 | 0 | 0 |  | 0 | 79.002 |  | 22
[5 empty] | TROWEL FINISH PADS | 363 | SF | 6 | 25.047 | 0.069 | 1.38 | 500.94 | 0.02 | 7.26 | 0 | 0 | 0 | 0 |  | 0 | 508.2 |  | 22
[5 empty] | RUB CONC PAD | 175.56 | SF | 6 | 17.556 | 0.1 | 2 | 351.12 | 0.03 | 5.2668 | 0 | 0 | 0 | 0 |  | 0 | 356.3868 |  | 22
[5 empty] | PAD EDGEFORM | 175.56 | SF | 6 | 42.1344 | 0.24 | 4.8 | 842.688 | 1 | 175.56 | 0 | 0 | 0 | 0 |  | 0 | 1018.248 |  | 22
[5 empty] | SET ANCHOR BOLTS/ PAD | 18 | EA | 6 | 10.8 | 0.6 | 12 | 216 | 1.5 | 27 | 0 | 0 | 0 | 0 |  | 0 | 243 |  | 22
[5 empty] | PLACE PADS | 18 | CY | 8 | 10.8 | 0.6 | 12 | 216 | 0 | 0 |  | 0 |  | 0 |  | 0 | 216 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 18 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1980 | 0 | 0 | 0 | 0 |  | 0 | 1980 |  | 22
|  |  |  | 8" Slab on Grade |  |  |  | 6 | [14 empty] | 22
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1793 | SF | 6 | 28.688 | 0.016 | 0.32 | 573.76 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 573.76 |  | 22
[5 empty] | POINT & PATCH | 196.5 | SF | 8 | 5.895 | 0.03 | 0.6 | 117.9 | 0.01 | 1.965 | 0 | 0 | 0 | 0 |  | 0 | 119.865 |  | 22
[5 empty] | FINISH CONCRETE | 1793 | SF | 8 | 25.102 | 0.014 | 0.28 | 502.04 | 0.02 | 35.86 | 0 | 0 | 0 | 0 |  | 0 | 537.9 |  | 22
[5 empty] | SLAB EDGEFORM | 196.5 | SF | 6 | 47.16 | 0.24 | 4.8 | 943.2 | 0.7 | 137.55 | 0 | 0 | 1 | 196.5 |  | 0 | 1277.25 |  | 22
[5 empty] | 1/2" EXPANSION JOINT | 88.44 | SF | 6 | 7.5174 | 0.085 | 1.7 | 150.348 | 1.5 | 132.66 | 0 | 0 | 0 | 0 |  | 0 | 283.008 |  | 22
[5 empty] | 1/2" JOINT SEALANT | 285 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 712.5 |  | 0 | 712.5 |  | 22
[5 empty] | 10 MIL VISQUEEN | 19.72 | SQS | 6 | 4.5159 | 0.229 | 4.58 | 90.3176 | 30 | 591.6 | 0 | 0 | 0 | 0 |  | 0 | 681.9176 |  | 22
[5 empty] | FORM SUMP BOXOUT/ S.O.G. | 9 | SF | 6 | 4.5 | 0.5 | 10 | 90 | 2.25 | 20.25 | 0 | 0 | 0 | 0 |  | 0 | 110.25 |  | 22
[5 empty] | SET EMBED ANGLE/ SLAB | 12 | LF | 6 | 2.4 | 0.2 | 4 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 48 |  | 22
[5 empty] | 8" TYPE 1 SOG WALL BASE JT FOR CURB | 184 | LF | 6 | 53.36 | 0.29 | 5.8 | 1067.2 | 2 | 368 | 0 | 0 | 0 | 0 |  | 0 | 1435.2 |  | 22
[5 empty] | SAW CUT CONCRETE | 153 | LF | 6 | 18.36 | 0.12 | 2.4 | 367.2 | 0.18 | 27.54 | 0 | 0 | 0.75 | 114.75 |  | 0 | 509.49 |  | 22
[5 empty] | RESTEEL DOBIE SUPPORTS | 1793 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 89.65 | 0 | 0 | 0 | 0 |  | 0 | 89.65 |  | 22
[5 empty] | PLACE SLAB ON GRADE | 49 | CY | 8 | 29.4 | 0.6 | 12 | 588 | 0 | 0 |  | 0 |  | 0 |  | 0 | 588 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 49 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 5390 | 0 | 0 | 0 | 0 |  | 0 | 5390 |  | 22
|  |  |  | 4" High Curb |  |  |  | 6
[5 empty] | POINT & PATCH CONC CURB | 121.11 | SF | 6 | 2.6644 | 0.022 | 0.44 | 53.2884 | 0.01 | 1.2111 | 0 | 0 | 0 | 0 |  | 0 | 54.4995 |  | 22
[5 empty] | TROWEL FINISH CURBS | 122.95 | SF | 6 | 8.4836 | 0.069 | 1.38 | 169.671 | 0.02 | 2.459 | 0 | 0 | 0 | 0 |  | 0 | 172.13 |  | 22
[5 empty] | RUB CONC CURB | 121.11 | SF | 6 | 12.111 | 0.1 | 2 | 242.22 | 0.03 | 3.6333 | 0 | 0 | 0 | 0 |  | 0 | 245.8533 |  | 22
[5 empty] | ROUGH/CLEAN NEW CONC-CURB | 122.95 | SF | 6 | 1.9672 | 0.016 | 0.32 | 39.344 | 0.01 | 1.2295 | 0 | 0 | 0 | 0 |  | 0 | 40.5735 |  | 22
[5 empty] | CURB FORMWORK | 367 | SF | 6 | 88.08 | 0.24 | 4.8 | 1761.6 | 1 | 367 | 0 | 0 | 0 | 0 |  | 0 | 2128.6 |  | 22
[5 empty] | PLACE INTERIOR CURBS | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 80 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 22
|  |  |  | Equipment Pad - 1 EA |  |  |  | 6 | [14 empty] | 22
[5 empty] | POINT & PATCH CONC PAD | 8.5 | SF | 8 | 1.9975 | 0.235 | 4.7 | 39.95 | 0.01 | 0.085 | 0 | 0 | 0 | 0 |  | 0 | 40.035 |  | 22
[5 empty] | TROWEL FINISH PADS | 17.5 | SF | 6 | 1.995 | 0.114 | 2.28 | 39.9 | 0.02 | 0.35 | 0 | 0 | 0 | 0 |  | 0 | 40.25 |  | 22
[5 empty] | RUB CONC PAD | 8.5 | SF | 6 | 1.9975 | 0.235 | 4.7 | 39.95 | 0.03 | 0.255 | 0 | 0 | 0 | 0 |  | 0 | 40.205 |  | 22
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 17.5 | SF | 6 | 1.995 | 0.114 | 2.28 | 39.9 | 0.01 | 0.175 | 0 | 0 | 0 | 0 |  | 0 | 40.075 |  | 22
[5 empty] | PAD EDGEFORM | 17 | SF | 6 | 4.08 | 0.24 | 4.8 | 81.6 | 1 | 17 | 0 | 0 | 0 | 0 |  | 0 | 98.6 |  | 22
[5 empty] | SET ANCHOR BOLTS/ PAD | 4 | EA | 6 | 2.4 | 0.6 | 12 | 48 | 1.5 | 6 | 0 | 0 | 0 | 0 |  | 0 | 54 |  | 22
[5 empty] | PLACE PADS | 1 | CY | 8 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 22
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 22
|  |  | (100-E) RAS/WAS Pump Station |  |  |  |  | 6
|  |  |  | 8" Slab on Grade |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 860.5 | SF | 6 | 13.768 | 0.016 | 0.32 | 275.36 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 275.36 |  | 23
[5 empty] | POINT & PATCH | 255 | SF | 8 | 7.65 | 0.03 | 0.6 | 153 | 0.01 | 2.55 | 0 | 0 | 0 | 0 |  | 0 | 155.55 |  | 23
[5 empty] | FINISH CONCRETE | 860.5 | SF | 8 | 12.047 | 0.014 | 0.28 | 240.94 | 0.02 | 17.21 | 0 | 0 | 0 | 0 |  | 0 | 258.15 |  | 23
[5 empty] | SLAB EDGEFORM | 300 | SF | 6 | 72 | 0.24 | 4.8 | 1440 | 0.7 | 210 | 0 | 0 | 1 | 300 |  | 0 | 1950 |  | 23
[5 empty] | 1/2" JOINT SEALANT | 90.5 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 226.25 |  | 0 | 226.25 |  | 23
[5 empty] | SAW CUT CONCRETE | 90.5 | LF | 6 | 10.86 | 0.12 | 2.4 | 217.2 | 0.18 | 16.29 | 0 | 0 | 0.75 | 67.875 |  | 0 | 301.365 |  | 23
[5 empty] | RESTEEL DOBIE SUPPORTS | 860.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 43.025 | 0 | 0 | 0 | 0 |  | 0 | 43.025 |  | 23
[5 empty] | PLACE SLAB ON GRADE | 27 | CY | 8 | 18.9 | 0.7 | 14 | 378 | 0 | 0 |  | 0 |  | 0 |  | 0 | 378 |  | 23
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 27 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2970 | 0 | 0 | 0 | 0 |  | 0 | 2970 |  | 23
|  |  |  | Equipment Pads - 5 EA |  |  |  | 6 | [14 empty] | 23
[5 empty] | POINT & PATCH CONC PAD | 99 | SF | 8 | 2.178 | 0.022 | 0.44 | 43.56 | 0.01 | 0.99 | 0 | 0 | 0 | 0 |  | 0 | 44.55 |  | 23
[5 empty] | TROWEL FINISH PADS | 104.5 | SF | 6 | 7.2105 | 0.069 | 1.38 | 144.21 | 0.02 | 2.09 | 0 | 0 | 0 | 0 |  | 0 | 146.3 |  | 23
[5 empty] | RUB CONC PAD | 99 | SF | 6 | 9.9 | 0.1 | 2 | 198 | 0.03 | 2.97 | 0 | 0 | 0 | 0 |  | 0 | 200.97 |  | 23
[5 empty] | PAD EDGEFORM | 99 | SF | 6 | 23.76 | 0.24 | 4.8 | 475.2 | 1 | 99 | 0 | 0 | 0 | 0 |  | 0 | 574.2 |  | 23
[5 empty] | SET ANCHOR BOLTS/ PAD | 30 | EA | 6 | 18 | 0.6 | 12 | 360 | 1.5 | 45 | 0 | 0 | 0 | 0 |  | 0 | 405 |  | 23
[5 empty] | PLACE PADS | 4 | CY | 8 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 23
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 23
|  |  |  | Pipe Supports - 3 EA |  |  |  | 6 | [14 empty] | 23
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 36.05 | SF | 8 | 1.9827 | 0.055 | 1.1 | 39.655 | 0.01 | 0.3605 | 0 | 0 | 0 | 0 |  | 0 | 40.0155 |  | 23
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 4.02 | SF | 6 | 2.002 | 0.498 | 9.96 | 40.0392 | 0.02 | 0.0804 | 0 | 0 | 0 | 0 |  | 0 | 40.1196 |  | 23
[5 empty] | RUB CONC PIPE SUPPORT | 36.05 | SF | 6 | 3.605 | 0.1 | 2 | 72.1 | 0.03 | 1.0815 | 0 | 0 | 0 | 0 |  | 0 | 73.1815 |  | 23
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 4.02 | SF | 6 | 2.002 | 0.498 | 9.96 | 40.0392 | 0.01 | 0.0402 | 0 | 0 | 0 | 0 |  | 0 | 40.0794 |  | 23
[5 empty] | PIPE SUPPORT FORMWORK | 36.05 | SF | 6 | 7.5705 | 0.21 | 4.2 | 151.41 | 1 | 36.05 | 0 | 0 | 0 | 0 |  | 0 | 187.46 |  | 23
[5 empty] | FORM MEDIUM PIPE SADDLE 2' DIA | 3 | EA | 6 | 6 | 2 | 40 | 120 | 15 | 45 | 0 | 0 | 0 | 0 |  | 0 | 165 |  | 23
[5 empty] | PLACE PIPE SUPPORT | 1 | CY | 8 | 3 | 3 | 60 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 23
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 23
|  |  | (110-E) Aerobic Digesters |  |  |  |  | 6
|  |  |  | Pipe Encasements - 12 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 10.9 | CY | 6 | 21.8 | 2 | 40 | 436 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 436 |  | 24
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 1782.92 | SF | 6 | 213.9504 | 0.12 | 2.4 | 4279.008 | 1 | 1782.92 | 0 | 0 | 1 | 1782.92 |  | 0 | 7844.848 |  | 24
[5 empty] | PIPE ENCASE FORMWK - VERT 17.5 | 116.9 | SF | 6 | 28.056 | 0.24 | 4.8 | 561.12 | 1 | 116.9 | 0 | 0 | 1 | 116.9 |  | 0 | 794.92 |  | 24
[5 empty] | PIPE ENCASE FORMWK - VERT 32.5 | 237.9 | SF | 6 | 57.096 | 0.24 | 4.8 | 1141.92 | 1 | 237.9 | 0 | 0 | 1 | 237.9 |  | 0 | 1617.72 |  | 24
[5 empty] | PIPE ENCASE FORMWK - VERT 42.75 | 312.93 | SF | 6 | 75.1032 | 0.24 | 4.8 | 1502.064 | 1 | 312.93 | 0 | 0 | 1 | 312.93 |  | 0 | 2127.924 |  | 24
[5 empty] | PIPE ENCASE FORMWK - VERT 9 ' | 60.12 | SF | 6 | 14.4288 | 0.24 | 4.8 | 288.576 | 1 | 60.12 | 0 | 0 | 1 | 60.12 |  | 0 | 408.816 |  | 24
[5 empty] | RESTEEL DOBIE SUPPORTS | 891.46 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 44.573 | 0 | 0 | 0 | 0 |  | 0 | 44.573 |  | 24
[5 empty] | PLACE PIPE ENCASEMENT | 68 | CY | 8 | 40.8 | 0.6 | 12 | 816 | 0 | 0 |  | 0 |  | 0 |  | 0 | 816 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 68 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 7480 | 0 | 0 | 0 | 0 |  | 0 | 7480 |  | 24
|  |  |  | 24" Slab on Grade |  |  |  | 6 | [14 empty] | 24
[5 empty] | HAND PREP SUBGRADE-BUILDING | 11112.5 | SF | 6 | 177.8 | 0.016 | 0.32 | 3556 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3556 |  | 24
[5 empty] | POINT & PATCH | 858 | SF | 8 | 25.74 | 0.03 | 0.6 | 514.8 | 0.01 | 8.58 | 0 | 0 | 0 | 0 |  | 0 | 523.38 |  | 24
[5 empty] | FINISH CONCRETE | 11112.5 | SF | 8 | 155.575 | 0.014 | 0.28 | 3111.5 | 0.02 | 222.25 | 0 | 0 | 0 | 0 |  | 0 | 3333.75 |  | 24
[5 empty] | SLAB EDGEFORM | 858 | SF | 6 | 240.24 | 0.28 | 5.6 | 4804.8 | 0.7 | 600.6 | 0 | 0 | 1 | 858 |  | 0 | 6263.4 |  | 24
[5 empty] | 18" TYPE 1 SOG WALL BASE JT | 776 | LF | 6 | 364.72 | 0.47 | 9.4 | 7294.4 | 2.97 | 2304.72 | 0 | 0 | 0 | 0 |  | 0 | 9599.12 |  | 24
[5 empty] | 24" TYPE 1 SOG CONST JT | 302 | LF | 6 | 277.84 | 0.92 | 18.4 | 5556.8 | 4.2 | 1268.4 | 0 | 0 | 2.5 | 755 |  | 0 | 7580.2 |  | 24
[5 empty] | RESTEEL DOBIE SUPPORTS | 11112.5 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 555.625 | 0 | 0 | 0 | 0 |  | 0 | 555.625 |  | 24
[5 empty] | PLACE SLAB ON GRADE | 824 | CY | 8 | 494.4 | 0.6 | 12 | 9888 | 0 | 0 |  | 0 |  | 0 |  | 0 | 9888 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 824 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 90640 | 0 | 0 | 0 | 0 |  | 0 | 90640 |  | 24
|  |  |  | 18" Tank Walls |  |  |  | 6 | [14 empty] | 24
[5 empty] | POINT & PATCH | 27456 | SF | 8 | 823.68 | 0.03 | 0.6 | 16473.6 | 0.01 | 274.56 | 0 | 0 | 0 | 0 |  | 0 | 16748.16 |  | 24
[5 empty] | STANDARD RUB WALLS | 7434 | SF | 6 | 557.55 | 0.075 | 1.5 | 11151 | 0.03 | 223.02 | 0 | 0 | 0 | 0 |  | 0 | 11374.02 |  | 24
[5 empty] | GANG WALLFORM: 16 - 20' | 27456 | SF | 6 | 2745.6 | 0.1 | 2 | 54912 | 0.55 | 15100.8 | 0 | 0 | 1 | 27456 |  | 0 | 97468.8 |  | 24
[5 empty] | 18" TYPE 2 STRAIT WL CONST JT | 212 | LF | 6 | 167.48 | 0.79 | 15.8 | 3349.6 | 3.67 | 778.04 | 0 | 0 | 2.5 | 530 |  | 0 | 4657.64 |  | 24
[5 empty] | FORM BOXOUT/ GANG | 54 | SF | 6 | 18.9 | 0.35 | 7 | 378 | 1.5 | 81 | 0 | 0 | 0 | 0 |  | 0 | 459 |  | 24
[5 empty] | GANG-PIPE PENET 0-12" DIA | 4 | EA | 6 | 3.2 | 0.8 | 16 | 64 | 7.5 | 30 | 0 | 0 | 0 | 0 |  | 0 | 94 |  | 24
[5 empty] | PLACE WALLS | 763 | CY | 8 | 534.1 | 0.7 | 14 | 10682 | 0 | 0 |  | 0 |  | 0 |  | 0 | 10682 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 763 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 83930 | 0 | 0 | 0 | 0 |  | 0 | 83930 |  | 24
|  |  |  | 12" Slab on Grade @ 109.25 |  |  |  | 6 | [14 empty] | 24
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1890 | SF | 6 | 30.24 | 0.016 | 0.32 | 604.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 604.8 |  | 24
[5 empty] | POINT & PATCH | 133.5 | SF | 8 | 4.005 | 0.03 | 0.6 | 80.1 | 0.01 | 1.335 | 0 | 0 | 0 | 0 |  | 0 | 81.435 |  | 24
[5 empty] | FINISH CONCRETE | 1890 | SF | 8 | 26.46 | 0.014 | 0.28 | 529.2 | 0.02 | 37.8 | 0 | 0 | 0 | 0 |  | 0 | 567 |  | 24
[5 empty] | SLAB EDGEFORM | 133.5 | SF | 6 | 32.04 | 0.24 | 4.8 | 640.8 | 0.7 | 93.45 | 0 | 0 | 1 | 133.5 |  | 0 | 867.75 |  | 24
[5 empty] | 1/2" EXPANSION JOINT | 185.5 | SF | 6 | 15.7675 | 0.085 | 1.7 | 315.35 | 1.5 | 278.25 | 0 | 0 | 0 | 0 |  | 0 | 593.6 |  | 24
[5 empty] | 1/2" JOINT SEALANT | 310.5 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 776.25 |  | 0 | 776.25 |  | 24
[5 empty] | SAW CUT CONCRETE | 125 | LF | 6 | 15 | 0.12 | 2.4 | 300 | 0.18 | 22.5 | 0 | 0 | 0.75 | 93.75 |  | 0 | 416.25 |  | 24
[5 empty] | RESTEEL DOBIE SUPPORTS | 1890 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 94.5 | 0 | 0 | 0 | 0 |  | 0 | 94.5 |  | 24
[5 empty] | PLACE SLAB ON GRADE | 72 | CY | 8 | 43.2 | 0.6 | 12 | 864 | 0 | 0 |  | 0 |  | 0 |  | 0 | 864 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 72 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 7920 | 0 | 0 | 0 | 0 |  | 0 | 7920 |  | 24
|  |  |  | 12" Walkway |  |  |  | 6 | [14 empty] | 24
[5 empty] | POINT & PATCH | 679.36 | SF | 8 | 20.3808 | 0.03 | 0.6 | 407.616 | 0.01 | 6.7936 | 0 | 0 | 0 | 0 |  | 0 | 414.4096 |  | 24
[5 empty] | FINISH CONCRETE | 1964.07 | SF | 8 | 27.497 | 0.014 | 0.28 | 549.9396 | 0.02 | 39.2814 | 0 | 0 | 0 | 0 |  | 0 | 589.221 |  | 24
[5 empty] | RUB CONC SUPP SLAB EDGES | 679.36 | SF | 6 | 67.936 | 0.1 | 2 | 1358.72 | 0.03 | 20.3808 | 0 | 0 | 0 | 0 |  | 0 | 1379.1008 |  | 24
[5 empty] | CLEAN U/SIDE SLAB-REMOVE FINS | 1964.07 | SF | 6 | 21.6048 | 0.011 | 0.22 | 432.0954 | 0.02 | 39.2814 | 0 | 0 | 0 | 0 |  | 0 | 471.3768 |  | 24
[5 empty] | WALKWAY/TROUGH SOFFIT: 16- 20' | 1964.07 | SF | 6 | 1115.5918 | 0.568 | 11.36 | 22311.8352 | 1.5 | 2946.105 | 0 | 0 | 0.975 | 1914.9682 |  | 0 | 27172.9084 |  | 24
[5 empty] | WALKWAY/TROUGH EDGE FORM | 679.36 | SF | 6 | 148.7798 | 0.219 | 4.38 | 2975.5968 | 1.35 | 917.136 | 0 | 0 | 0 | 0 |  | 0 | 3892.7328 |  | 24
[5 empty] | 1/2" JOINT SEALANT | 36 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 90 |  | 0 | 90 |  | 24
[5 empty] | 12" TYPE 1 WKY/TROUGH CNTRL JT | 16 | LF | 6 | 8.8 | 0.55 | 11 | 176 | 3.19 | 51.04 | 0 | 0 | 2.5 | 40 |  | 0 | 267.04 |  | 24
[5 empty] | FORM BOXOUT/ WALKWAY-TROUGH | 16 | SF | 6 | 4.8 | 0.3 | 6 | 96 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 120 |  | 24
[5 empty] | SAW CUT CONCRETE | 36 | LF | 6 | 4.32 | 0.12 | 2.4 | 86.4 | 0.18 | 6.48 | 0 | 0 | 0.75 | 27 |  | 0 | 119.88 |  | 24
[5 empty] | RESTEEL DOBIE SUPPORTS | 1964.07 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 98.2035 | 0 | 0 | 0 | 0 |  | 0 | 98.2035 |  | 24
[5 empty] | PLACE WALKWAY/TROUGH | 73 | CY | 8 | 51.1 | 0.7 | 14 | 1022 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1022 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 73 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 8030 | 0 | 0 | 0 | 0 |  | 0 | 8030 |  | 24
|  |  |  | Equipment Pads - 6 EA |  |  |  | 6 | [14 empty] | 24
[5 empty] | POINT & PATCH CONC PAD | 201 | SF | 8 | 4.422 | 0.022 | 0.44 | 88.44 | 0.01 | 2.01 | 0 | 0 | 0 | 0 |  | 0 | 90.45 |  | 24
[5 empty] | TROWEL FINISH PADS | 240 | SF | 6 | 16.56 | 0.069 | 1.38 | 331.2 | 0.02 | 4.8 | 0 | 0 | 0 | 0 |  | 0 | 336 |  | 24
[5 empty] | RUB CONC PAD | 201 | SF | 6 | 20.1 | 0.1 | 2 | 402 | 0.03 | 6.03 | 0 | 0 | 0 | 0 |  | 0 | 408.03 |  | 24
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 42 | SF | 6 | 2.016 | 0.048 | 0.96 | 40.32 | 0.01 | 0.42 | 0 | 0 | 0 | 0 |  | 0 | 40.74 |  | 24
[5 empty] | PAD EDGEFORM | 223.5 | SF | 6 | 53.64 | 0.24 | 4.8 | 1072.8 | 1 | 223.5 | 0 | 0 | 0 | 0 |  | 0 | 1296.3 |  | 24
[5 empty] | SET ANCHOR BOLTS/ PAD | 36 | EA | 6 | 21.6 | 0.6 | 12 | 432 | 1.5 | 54 | 0 | 0 | 0 | 0 |  | 0 | 486 |  | 24
[5 empty] | PLACE PADS | 14 | CY | 8 | 14 | 1 | 20 | 280 | 0 | 0 |  | 0 |  | 0 |  | 0 | 280 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 14 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1540 | 0 | 0 | 0 | 0 |  | 0 | 1540 |  | 24
|  |  |  | Pipe Supports - 7 EA |  |  |  | 6 | [14 empty] | 24
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 45.08 | SF | 8 | 1.9835 | 0.044 | 0.88 | 39.6704 | 0.01 | 0.4508 | 0 | 0 | 0 | 0 |  | 0 | 40.1212 |  | 24
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 5.49 | SF | 6 | 1.9984 | 0.364 | 7.28 | 39.9672 | 0.02 | 0.1098 | 0 | 0 | 0 | 0 |  | 0 | 40.077 |  | 24
[5 empty] | RUB CONC PIPE SUPPORT | 45.08 | SF | 6 | 4.508 | 0.1 | 2 | 90.16 | 0.03 | 1.3524 | 0 | 0 | 0 | 0 |  | 0 | 91.5124 |  | 24
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 5.49 | SF | 6 | 1.9984 | 0.364 | 7.28 | 39.9672 | 0.01 | 0.0549 | 0 | 0 | 0 | 0 |  | 0 | 40.0221 |  | 24
[5 empty] | PIPE SUPPORT FORMWORK | 45.08 | SF | 6 | 9.4668 | 0.21 | 4.2 | 189.336 | 1 | 45.08 | 0 | 0 | 0 | 0 |  | 0 | 234.416 |  | 24
[5 empty] | FORM SMALL PIPE SADDLE 1' DIA | 7 | EA | 6 | 7 | 1 | 20 | 140 | 7.5 | 52.5 | 0 | 0 | 0 | 0 |  | 0 | 192.5 |  | 24
[5 empty] | PLACE PIPE SUPPORT | 1 | CY | 8 | 3 | 3 | 60 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 24
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 24
|  |  | (115-E) Biosolids Dewatering |  |  |  |  | 6
|  |  |  | Pipe Encasements - 6 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 6.72 | CY | 6 | 13.44 | 2 | 40 | 268.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 268.8 |  | 25
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 1099.28 | SF | 6 | 131.9136 | 0.12 | 2.4 | 2638.272 | 1 | 1099.28 | 0 | 0 | 1 | 1099.28 |  | 0 | 4836.832 |  | 25
[5 empty] | PIPE ENCASE FORMWK - VERT 12' | 96 | SF | 6 | 23.04 | 0.24 | 4.8 | 460.8 | 1 | 96 | 0 | 0 | 1 | 96 |  | 0 | 652.8 |  | 25
[5 empty] | PIPE ENCASE FORMWK - VERT 8 ' | 53.44 | SF | 6 | 12.8256 | 0.24 | 4.8 | 256.512 | 1 | 53.44 | 0 | 0 | 1 | 53.44 |  | 0 | 363.392 |  | 25
[5 empty] | RESTEEL DOBIE SUPPORTS | 549.64 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 27.482 | 0 | 0 | 0 | 0 |  | 0 | 27.482 |  | 25
[5 empty] | PLACE PIPE ENCASEMENT | 39 | CY | 8 | 27.3 | 0.7 | 14 | 546 | 0 | 0 |  | 0 |  | 0 |  | 0 | 546 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 39 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4290 | 0 | 0 | 0 | 0 |  | 0 | 4290 |  | 25
|  |  |  | 24" Footings |  |  |  | 6 | [14 empty] | 25
[5 empty] | HAND EXCAV COLUMN FTG | 3.1 | CY | 6 | 6.2 | 2 | 40 | 124 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 124 |  | 25
[5 empty] | FINISH TOP FTG/PILE CAP | 254 | SF | 8 | 7.112 | 0.028 | 0.56 | 142.24 | 0.02 | 5.08 | 0 | 0 | 0 | 0 |  | 0 | 147.32 |  | 25
[5 empty] | COLUMN FTG EDGEFORM | 588 | SF | 6 | 141.12 | 0.24 | 4.8 | 2822.4 | 0.45 | 264.6 | 0 | 0 | 1 | 588 |  | 0 | 3675 |  | 25
[5 empty] | RESTEEL DOBIE SUPPORTS | 254 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 12.7 | 0 | 0 | 0 | 0 |  | 0 | 12.7 |  | 25
[5 empty] | PLACE COLUMN FOOTING | 29 | CY | 8 | 23.2 | 0.8 | 16 | 464 | 0 | 0 |  | 0 |  | 0 |  | 0 | 464 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 29 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 3190 | 0 | 0 | 0 | 0 |  | 0 | 3190 |  | 25
|  |  |  | 12" Belt Filter Press Pit |  |  |  | 6 | [14 empty] | 25
[5 empty] | HAND PREP SUBGRADE-BUILDING | 648.12 | SF | 6 | 10.3699 | 0.016 | 0.32 | 207.3984 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 207.3984 |  | 25
[5 empty] | POINT & PATCH | 147.04 | SF | 8 | 4.4112 | 0.03 | 0.6 | 88.224 | 0.01 | 1.4704 | 0 | 0 | 0 | 0 |  | 0 | 89.6944 |  | 25
[5 empty] | FINISH CONCRETE | 648.12 | SF | 8 | 9.0737 | 0.014 | 0.28 | 181.4736 | 0.02 | 12.9624 | 0 | 0 | 0 | 0 |  | 0 | 194.436 |  | 25
[5 empty] | SLAB EDGEFORM | 147.04 | SF | 6 | 35.2896 | 0.24 | 4.8 | 705.792 | 0.7 | 102.928 | 0 | 0 | 1 | 147.04 |  | 0 | 955.76 |  | 25
[5 empty] | RESTEEL DOBIE SUPPORTS | 648.12 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 32.406 | 0 | 0 | 0 | 0 |  | 0 | 32.406 |  | 25
[5 empty] | PLACE SLAB ON GRADE | 24 | CY | 8 | 14.4 | 0.6 | 12 | 288 | 0 | 0 |  | 0 |  | 0 |  | 0 | 288 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 24 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2640 | 0 | 0 | 0 | 0 |  | 0 | 2640 |  | 25
|  |  |  | Belt Filter Press Pit Curb |  |  |  | 6 | [14 empty] | 25
[5 empty] | POINT & PATCH CONC CURB | 387.2 | SF | 8 | 8.5184 | 0.022 | 0.44 | 170.368 | 0.01 | 3.872 | 0 | 0 | 0 | 0 |  | 0 | 174.24 |  | 25
[5 empty] | TROWEL FINISH CURBS | 144.27 | SF | 6 | 9.9546 | 0.069 | 1.38 | 199.0926 | 0.02 | 2.8854 | 0 | 0 | 0 | 0 |  | 0 | 201.978 |  | 25
[5 empty] | RUB CONC CURB | 387.2 | SF | 6 | 38.72 | 0.1 | 2 | 774.4 | 0.03 | 11.616 | 0 | 0 | 0 | 0 |  | 0 | 786.016 |  | 25
[5 empty] | ROUGH/CLEAN NEW CONC-CURB | 144.27 | SF | 6 | 2.3083 | 0.016 | 0.32 | 46.1664 | 0.01 | 1.4427 | 0 | 0 | 0 | 0 |  | 0 | 47.6091 |  | 25
[5 empty] | CURB FORMWORK | 387.2 | SF | 6 | 92.928 | 0.24 | 4.8 | 1858.56 | 1 | 387.2 | 0 | 0 | 0 | 0 |  | 0 | 2245.76 |  | 25
[5 empty] | SET ANCHOR BOLTS/ CURB | 12 | EA | 6 | 7.2 | 0.6 | 12 | 144 | 1.5 | 18 | 0 | 0 | 0 | 0 |  | 0 | 162 |  | 25
[5 empty] | PLACE INTERIOR CURBS | 7 | CY | 8 | 5.6 | 0.8 | 16 | 112 | 0 | 0 |  | 0 |  | 0 |  | 0 | 112 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 7 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 770 | 0 | 0 | 0 | 0 |  | 0 | 770 |  | 25
|  |  |  | Belt Filter Press Pedestals |  |  |  | 6 | [14 empty] | 25
[5 empty] | POINT & PATCH | 85.12 | SF | 8 | 2.5536 | 0.03 | 0.6 | 51.072 | 0.01 | 0.8512 | 0 | 0 | 0 | 0 |  | 0 | 51.9232 |  | 25
[5 empty] | RUB CONC COLUMN/PIER | 85.12 | SF | 6 | 8.512 | 0.1 | 2 | 170.24 | 0.03 | 2.5536 | 0 | 0 | 0 | 0 |  | 0 | 172.7936 |  | 25
[5 empty] | PIER FORM: 4'-6' PERIM | 85.12 | SF | 6 | 22.3866 | 0.263 | 5.26 | 447.7312 | 0.818 | 69.6282 | 0 | 0 | 1 | 85.12 |  | 0 | 602.4794 |  | 25
[5 empty] | SET ANCHOR BOLTS/ PIER | 64 | EA | 6 | 38.4 | 0.6 | 12 | 768 | 1.5 | 96 | 0 | 0 | 0 | 0 |  | 0 | 864 |  | 25
[5 empty] | GROUT BASE PL NON-SHRINK GROUT | 16 | EA | 6 | 16 | 1 | 20 | 320 | 25 | 400 | 0 | 0 | 0 | 0 |  | 0 | 720 |  | 25
[5 empty] | PLACE PIERS | 1 | CY | 8 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 25
|  |  |  | 12" Slab @ Platform Supports |  |  |  | 6 | [14 empty] | 25
[5 empty] | HAND PREP SUBGRADE-BUILDING | 72 | SF | 6 | 2.016 | 0.028 | 0.56 | 40.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.32 |  | 25
[5 empty] | POINT & PATCH | 66 | SF | 8 | 1.98 | 0.03 | 0.6 | 39.6 | 0.01 | 0.66 | 0 | 0 | 0 | 0 |  | 0 | 40.26 |  | 25
[5 empty] | FINISH CONCRETE | 72 | SF | 8 | 2.016 | 0.028 | 0.56 | 40.32 | 0.02 | 1.44 | 0 | 0 | 0 | 0 |  | 0 | 41.76 |  | 25
[5 empty] | SLAB EDGEFORM | 66 | SF | 6 | 15.84 | 0.24 | 4.8 | 316.8 | 0.7 | 46.2 | 0 | 0 | 1 | 66 |  | 0 | 429 |  | 25
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 12 | EA | 6 | 7.2 | 0.6 | 12 | 144 | 1.5 | 18 | 0 | 0 | 0 | 0 |  | 0 | 162 |  | 25
[5 empty] | RESTEEL DOBIE SUPPORTS | 72 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 3.6 | 0 | 0 | 0 | 0 |  | 0 | 3.6 |  | 25
[5 empty] | PLACE SLAB ON GRADE | 3 | CY | 8 | 6 | 2 | 40 | 120 | 0 | 0 |  | 0 |  | 0 |  | 0 | 120 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 25
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 25
[5 empty] | HAND PREP SUBGRADE-BUILDING | 2807.68 | SF | 6 | 44.9229 | 0.016 | 0.32 | 898.4576 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 898.4576 |  | 25
[5 empty] | POINT & PATCH | 237 | SF | 8 | 7.11 | 0.03 | 0.6 | 142.2 | 0.01 | 2.37 | 0 | 0 | 0 | 0 |  | 0 | 144.57 |  | 25
[5 empty] | FINISH CONCRETE | 2807.68 | SF | 8 | 39.3075 | 0.014 | 0.28 | 786.1504 | 0.02 | 56.1536 | 0 | 0 | 0 | 0 |  | 0 | 842.304 |  | 25
[5 empty] | SLAB EDGEFORM | 474 | SF | 6 | 113.76 | 0.24 | 4.8 | 2275.2 | 0.7 | 331.8 | 0 | 0 | 1 | 474 |  | 0 | 3081 |  | 25
[5 empty] | 1/2" EXPANSION JOINT | 147 | SF | 6 | 12.495 | 0.085 | 1.7 | 249.9 | 1.5 | 220.5 | 0 | 0 | 0 | 0 |  | 0 | 470.4 |  | 25
[5 empty] | 1/2" JOINT SEALANT | 300 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 750 |  | 0 | 750 |  | 25
[5 empty] | FORM TRENCH BOXOUT/ S.O.G. | 35.67 | SF | 6 | 14.268 | 0.4 | 8 | 285.36 | 2.25 | 80.2575 | 0 | 0 | 0 | 0 |  | 0 | 365.6175 |  | 25
[5 empty] | SET EMBED ANGLE/ SLAB ON GRADE | 74 | LF | 6 | 14.8 | 0.2 | 4 | 296 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 296 |  | 25
[5 empty] | SAW CUT CONCRETE | 153 | LF | 6 | 18.36 | 0.12 | 2.4 | 367.2 | 0.18 | 27.54 | 0 | 0 | 0.75 | 114.75 |  | 0 | 509.49 |  | 25
[5 empty] | RESTEEL DOBIE SUPPORTS | 2807.68 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 140.384 | 0 | 0 | 0 | 0 |  | 0 | 140.384 |  | 25
[5 empty] | PLACE SLAB ON GRADE | 60 | CY | 8 | 36 | 0.6 | 12 | 720 | 0 | 0 |  | 0 |  | 0 |  | 0 | 720 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 60 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 6600 | 0 | 0 | 0 | 0 |  | 0 | 6600 |  | 25
|  |  |  | Pipe Supports - 8 EA |  |  |  | 6 | [14 empty] | 25
[5 empty] | POINT & PATCH | 42.56 | SF | 8 | 2.128 | 0.05 | 1 | 42.56 | 0.01 | 0.4256 | 0 | 0 | 0 | 0 |  | 0 | 42.9856 |  | 25
[5 empty] | RUB CONC COLUMN/PIER | 42.56 | SF | 6 | 4.256 | 0.1 | 2 | 85.12 | 0.03 | 1.2768 | 0 | 0 | 0 | 0 |  | 0 | 86.3968 |  | 25
[5 empty] | PIER FORM: 4'-6' PERIM | 42.56 | SF | 6 | 11.1933 | 0.263 | 5.26 | 223.8656 | 0.818 | 34.8141 | 0 | 0 | 1 | 42.56 |  | 0 | 301.2397 |  | 25
[5 empty] | SET ANCHOR BOLTS/ PIER | 32 | EA | 6 | 19.2 | 0.6 | 12 | 384 | 1.5 | 48 | 0 | 0 | 0 | 0 |  | 0 | 432 |  | 25
[5 empty] | GROUT BASE PL NON-SHRINK GROUT | 8 | EA | 6 | 8 | 1 | 20 | 160 | 25 | 200 | 0 | 0 | 0 | 0 |  | 0 | 360 |  | 25
[5 empty] | PLACE PIERS | 2 | CY | 8 | 3 | 1.5 | 30 | 60 | 0 | 0 |  | 0 |  | 0 |  | 0 | 60 |  | 25
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 25
|  |  | (118-E) Sludge Drying |  |  |  |  | 6
|  |  |  | Pipe Encasements - 1 EA |  |  |  | 6
[5 empty] | HAND EXCAV PIPE ENCASE | 0.27 | CY | 6 | 2.035 | 7.537 | 150.74 | 40.6998 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.6998 |  | 26
[5 empty] | PIPE ENCASE FORMWK - HORIZ | 43.42 | SF | 6 | 5.2104 | 0.12 | 2.4 | 104.208 | 1 | 43.42 | 0 | 0 | 1 | 43.42 |  | 0 | 191.048 |  | 26
[5 empty] | PIPE ENCASE FORMWK - VERT 4 ' | 26.72 | SF | 6 | 6.4128 | 0.24 | 4.8 | 128.256 | 1 | 26.72 | 0 | 0 | 1 | 26.72 |  | 0 | 181.696 |  | 26
[5 empty] | RESTEEL DOBIE SUPPORTS | 21.71 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 1.0855 | 0 | 0 | 0 | 0 |  | 0 | 1.0855 |  | 26
[5 empty] | PLACE PIPE ENCASEMENT | 2 | CY | 8 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 26
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 26
| worth ~ $10k |  |  | 24" Footings (THIS IS THE 90% KOMLINE 92' X 50' BUILDING) |  |  |  | 6 | [14 empty] | 26
[5 empty] | HAND EXCAV COLUMN FTG | 5.28 | CY | 6 |  | 2 |  |  | 0 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | FINISH TOP FTG/PILE CAP | 432 | SF | 8 |  | 0.028 |  |  | 0.02 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | COLUMN FTG EDGEFORM | 576 | SF | 6 |  | 0.24 |  |  | 0.45 |  | 0 |  | 1 | [5 empty] | 26
[5 empty] | RESTEEL DOBIE SUPPORTS | 432 | SF | 6 |  | 0 |  |  | 0.05 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | PLACE COLUMN FOOTING | 32 | CY | 8 |  | 0.7 |  |  | 0 | [9 empty] | 26
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 32 | CY | 6 |  | 0 |  |  | 110 |  | 0 |  | 0 | [5 empty] | 26
| worth ~ $28k |  |  | Slab on Grade (THIS IS THE 90% KOMLINE 92' X 50' BUILDING) |  |  |  | 6 | [14 empty] | 26
[5 empty] | HAND PREP SUBGRADE-BUILDING | 4586.03 | SF | 6 |  | 0.016 |  |  | 0 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | POINT & PATCH | 432 | SF | 8 |  | 0.03 |  |  | 0.01 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | FINISH CONCRETE | 4586 | SF | 8 |  | 0.014 |  |  | 0.02 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | SLAB EDGEFORM | 574 | SF | 6 |  | 0.24 |  |  | 0.7 |  | 0 |  | 1 | [5 empty] | 26
[5 empty] | 1/2" JOINT SEALANT | 347 | LF | 6 |  | 0 |  |  | 0 |  | 0 |  | 2.5 | [5 empty] | 26
[5 empty] | FORM TRENCH BOXOUT/ S.O.G. | 36.5 | SF | 6 |  | 0.4 |  |  | 2.25 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | SET EMBED ANGLE/ SLAB ON GRADE | 75 | LF | 6 |  | 0.2 |  |  | 0 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | SAW CUT CONCRETE | 347 | LF | 6 |  | 0.12 |  |  | 0.18 |  | 0 |  | 0.75 | [5 empty] | 26
[5 empty] | RESTEEL DOBIE SUPPORTS | 4586.03 | SF | 6 |  | 0 |  |  | 0.05 |  | 0 |  | 0 | [5 empty] | 26
[5 empty] | PLACE SLAB ON GRADE | 128 | CY | 8 |  | 0.6 |  |  | 0 | [9 empty] | 26
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 128 | CY | 6 |  | 0 |  |  | 110 |  | 0 |  | 0 | [5 empty] | 26
6
| worth ~ $13k |  |  | 24" Footings (THIS IS THE 60% THERMA-FLITE 115' X 60' BLDG) |  |  |  | 6 | [14 empty] | 9
[5 empty] | HAND EXCAV COLUMN FTG | 4.66 | CY | 6 | 9.32 | 2 | 40 | 186.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 186.4 |  | 9
[5 empty] | FINISH TOP FTG/PILE CAP | 381 | SF | 8 | 10.668 | 0.028 | 0.56 | 213.36 | 0.02 | 7.62 | 0 | 0 | 0 | 0 |  | 0 | 220.98 |  | 9
[5 empty] | COLUMN FTG EDGEFORM | 882 | SF | 6 | 211.68 | 0.24 | 4.8 | 4233.6 | 0.45 | 396.9 | 0 | 0 | 1 | 882 |  | 0 | 5512.5 |  | 9
[5 empty] | RESTEEL DOBIE SUPPORTS | 381 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 19.05 | 0 | 0 | 0 | 0 |  | 0 | 19.05 |  | 9
[5 empty] | PLACE COLUMN FOOTING | 43 | CY | 8 | 30.1 | 0.7 | 14 | 602 | 0 | 0 |  | 0 |  | 0 |  | 0 | 602 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 43 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4730 | 0 | 0 | 0 | 0 |  | 0 | 4730 |  | 14
9
| worth ~ $32k |  |  | Slab on Grade (THIS IS THE 60% THERMA-FLITE 115' X 60' BLDG) |  |  |  | 6 | [14 empty] | 9
[5 empty] | HAND PREP SUBGRADE-BUILDING | 7100 | SF | 6 | 113.6 | 0.016 | 0.32 | 2272 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2272 |  | 9
[5 empty] | POINT & PATCH | 350 | SF | 1 | 10.5 | 0.03 | 0 | 0 | 0.01 | 3.5 | 0 | 0 | 0 | 0 |  | 0 | 3.5 |  | 9
[5 empty] | FINISH CONCRETE | 7100 | SF | 8 | 99.4 | 0.014 | 0.28 | 1988 | 0.02 | 142 | 0 | 0 | 0 | 0 |  | 0 | 2130 |  | 9
[5 empty] | SLAB EDGEFORM | 350 | SF | 6 | 84 | 0.24 | 4.8 | 1680 | 0.7 | 245 | 0 | 0 | 1 | 350 |  | 0 | 2275 |  | 9
[5 empty] | 1/2" JOINT SEALANT | 615 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 1537.5 |  | 0 | 1537.5 |  | 9
[5 empty] | FORM TRENCH BOXOUT/ S.O.G. | 48 | SF | 6 | 19.2 | 0.4 | 8 | 384 | 2.25 | 108 | 0 | 0 | 0 | 0 |  | 0 | 492 |  | 9
[5 empty] | SET EMBED ANGLE/ SLAB ON GRADE | 98 | LF | 6 | 19.6 | 0.2 | 4 | 392 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 392 |  | 9
[5 empty] | SAW CUT CONCRETE | 615 | LF | 6 | 73.8 | 0.12 | 2.4 | 1476 | 0.18 | 110.7 | 0 | 0 | 0.75 | 461.25 |  | 0 | 2047.95 |  | 9
[5 empty] | RESTEEL DOBIE SUPPORTS | 7100 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 355 | 0 | 0 | 0 | 0 |  | 0 | 355 |  | 9
[5 empty] | PLACE SLAB ON GRADE | 142 | CY | 8 | 85.2 | 0.6 | 12 | 1704 | 0 | 0 |  | 0 |  | 0 |  | 0 | 1704 |  | 9
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 142 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 15620 | 0 | 0 | 0 | 0 |  | 0 | 15620 |  | 14
6
|  |  |  | 9" High Containment Curb |  |  |  | 6
[5 empty] | POINT & PATCH CONC CURB | 123 | SF | 6 | 2.706 | 0.022 | 0.44 | 54.12 | 0.01 | 1.23 | 0 | 0 | 0 | 0 |  | 0 | 55.35 |  | 26
[5 empty] | TROWEL FINISH CURBS | 54.94 | SF | 6 | 3.7909 | 0.069 | 1.38 | 75.8172 | 0.02 | 1.0988 | 0 | 0 | 0 | 0 |  | 0 | 76.916 |  | 26
[5 empty] | RUB CONC CURB | 123 | SF | 6 | 12.3 | 0.1 | 2 | 246 | 0.03 | 3.69 | 0 | 0 | 0 | 0 |  | 0 | 249.69 |  | 26
[5 empty] | ROUGH/CLEAN NEW CONC-CURB | 54.94 | SF | 6 | 0.87904 | 0.016 | 0.32 | 17.5808 | 0.01 | 0.5494 | 0 | 0 | 0 | 0 |  | 0 | 18.1302 |  | 26
[5 empty] | CURB FORMWORK | 164 | SF | 6 | 39.36 | 0.24 | 4.8 | 787.2 | 1 | 164 | 0 | 0 | 0 | 0 |  | 0 | 951.2 |  | 26
[5 empty] | PLACE INTERIOR CURBS | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 80 |  | 26
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 26
6
| new in 90% design |  |  | Precast Electrical Building 10" Foundation |  |  |  | 6
| new in 90% design |  |  |  | HAND PREP SUBGRADE-BUILDING | 241.22 | SF | 6 | 3.8595 | 0.016 | 0.32 | 77.1904 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 77.1904 |  | 26
| new in 90% design |  |  |  | POINT & PATCH | 97.02 | SF | 6 | 2.9106 | 0.03 | 0.6 | 58.212 | 0.01 | 0.9702 | 0 | 0 | 0 | 0 |  | 0 | 59.1822 |  | 26
| new in 90% design |  |  |  | FINISH CONCRETE | 241.22 | SF | 6 | 3.3771 | 0.014 | 0.28 | 67.5416 | 0.02 | 4.8244 | 0 | 0 | 0 | 0 |  | 0 | 72.366 |  | 26
| new in 90% design |  |  |  | SLAB EDGEFORM | 129.36 | SF | 6 | 31.0464 | 0.24 | 4.8 | 620.928 | 0.7 | 90.552 | 0 | 0 | 1 | 129.36 |  | 0 | 840.84 |  | 26
| new in 90% design |  |  |  | 10 MIL VISQUEEN | 2.65 | SQS | 6 | 1.9981 | 0.754 | 15.08 | 39.962 | 30 | 79.5 | 0 | 0 | 0 | 0 |  | 0 | 119.462 |  | 26
| new in 90% design |  |  |  | RESTEEL DOBIE SUPPORTS | 241.22 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 12.061 | 0 | 0 | 0 | 0 |  | 0 | 12.061 |  | 26
| new in 90% design |  |  |  | PLACE SLAB ON GRADE | 11 | CY | 6 | 11 | 1 | 20 | 220 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 26
| new in 90% design |  |  |  | PURCHASE: 4000 PSI CONCRETE | 11 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1210 | 0 | 0 | 0 | 0 |  | 0 | 1210 |  | 26
new in 90% design
| new in 90% design |  |  | Concrete Pads for Precast Electrical Building |  |  |  | 6
| new in 90% design |  |  |  | HAND PREP SUBGRADE-BUILDING | 136.01 | SF | 6 | 2.1762 | 0.016 | 0.32 | 43.5232 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 43.5232 |  | 26
| new in 90% design |  |  |  | POINT & PATCH | 23.19 | SF | 6 | 1.9943 | 0.086 | 1.72 | 39.8868 | 0.01 | 0.2319 | 0 | 0 | 0 | 0 |  | 0 | 40.1187 |  | 26
| new in 90% design |  |  |  | FINISH CONCRETE | 136.01 | SF | 6 | 2.0401 | 0.015 | 0.3 | 40.803 | 0.02 | 2.7202 | 0 | 0 | 0 | 0 |  | 0 | 43.5232 |  | 26
| new in 90% design |  |  |  | SLAB EDGEFORM | 49.67 | SF | 6 | 11.9208 | 0.24 | 4.8 | 238.416 | 0.7 | 34.769 | 0 | 0 | 1 | 49.67 |  | 0 | 322.855 |  | 26
| new in 90% design |  |  |  | 1/2" EXPANSION JOINT | 23.67 | SF | 6 | 2.012 | 0.085 | 1.7 | 40.239 | 1.5 | 35.505 | 0 | 0 | 0 | 0 |  | 0 | 75.744 |  | 26
| new in 90% design |  |  |  | 1/2" JOINT SEALANT | 23.67 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 59.175 | 0 | 0 |  | 0 | 59.175 |  | 26
| new in 90% design |  |  |  | RESTEEL DOBIE SUPPORTS | 136.01 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 6.8005 | 0 | 0 | 0 | 0 |  | 0 | 6.8005 |  | 26
| new in 90% design |  |  |  | PLACE SLAB ON GRADE | 3 | CY | 6 | 3 | 1 | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 60 |  | 26
| new in 90% design |  |  |  | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 26
6
6
|  |  | (119-E) MCC Building |  |  |  |  | 6
|  |  |  | 12" Continuous Footing |  |  |  | 6
[5 empty] | HAND EXCAV CONTINUOUS FTG | 4.84 | CY | 6 | 9.68 | 2 | 40 | 193.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 193.6 |  | 27
[5 empty] | FINISH TOP FTG/PILE CAP | 396 | SF | 8 | 11.088 | 0.028 | 0.56 | 221.76 | 0.02 | 7.92 | 0 | 0 | 0 | 0 |  | 0 | 229.68 |  | 27
[5 empty] | CONTINUOUS FTG EDGEFORM | 264 | SF | 6 | 63.36 | 0.24 | 4.8 | 1267.2 | 0.45 | 118.8 | 0 | 0 | 1 | 264 |  | 0 | 1650 |  | 27
[5 empty] | RESTEEL DOBIE SUPPORTS | 396 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 19.8 | 0 | 0 | 0 | 0 |  | 0 | 19.8 |  | 27
[5 empty] | PLACE CONTINUOUS FOOTING | 15 | CY | 8 | 15 | 1 | 20 | 300 | 0 | 0 |  | 0 |  | 0 |  | 0 | 300 |  | 27
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 15 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1650 | 0 | 0 | 0 | 0 |  | 0 | 1650 |  | 27
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 27
[5 empty] | HAND PREP SUBGRADE-BUILDING | 849.25 | SF | 6 | 13.588 | 0.016 | 0.32 | 271.76 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 271.76 |  | 27
[5 empty] | POINT & PATCH | 122 | SF | 8 | 3.66 | 0.03 | 0.6 | 73.2 | 0.01 | 1.22 | 0 | 0 | 0 | 0 |  | 0 | 74.42 |  | 27
[5 empty] | FINISH CONCRETE | 849.25 | SF | 8 | 11.8895 | 0.014 | 0.28 | 237.79 | 0.02 | 16.985 | 0 | 0 | 0 | 0 |  | 0 | 254.775 |  | 27
[5 empty] | SLAB EDGEFORM | 10 | SF | 6 | 2.4 | 0.24 | 4.8 | 48 | 0.7 | 7 | 0 | 0 | 1 | 10 |  | 0 | 65 |  | 27
[5 empty] | ZIP STRIP | 119 | LF | 6 | 3.451 | 0.029 | 0.58 | 69.02 | 1.125 | 133.875 |  | 0 |  | 0 |  | 0 | 202.895 |  | 27
[5 empty] | 1/2" EXPANSION JOINT | 119 | SF | 6 | 10.115 | 0.085 | 1.7 | 202.3 | 1.5 | 178.5 | 0 | 0 | 0 | 0 |  | 0 | 380.8 |  | 27
[5 empty] | 1/2" JOINT SEALANT | 139.7 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 349.25 |  | 0 | 349.25 |  | 27
[5 empty] | 10 MIL VISQUEEN | 9.34 | SQS | 6 | 2.1389 | 0.229 | 4.58 | 42.7772 | 30 | 280.2 | 0 | 0 | 0 | 0 |  | 0 | 322.9772 |  | 27
[5 empty] | SAW CUT CONCRETE | 20.67 | LF | 6 | 2.4804 | 0.12 | 2.4 | 49.608 | 0.18 | 3.7206 | 0 | 0 | 0.75 | 15.5025 |  | 0 | 68.8311 |  | 27
[5 empty] | RESTEEL DOBIE SUPPORTS | 849.25 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 42.4625 | 0 | 0 | 0 | 0 |  | 0 | 42.4625 |  | 27
[5 empty] | PLACE SLAB ON GRADE | 20 | CY | 8 | 16 | 0.8 | 16 | 320 | 0 | 0 |  | 0 |  | 0 |  | 0 | 320 |  | 27
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 20 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2200 | 0 | 0 | 0 | 0 |  | 0 | 2200 |  | 27
|  |  |  | Equipment Pads - 5 EA |  |  |  | 6 | [14 empty] | 27
[5 empty] | POINT & PATCH CONC PAD | 50.27 | SF | 8 | 2.0108 | 0.04 | 0.8 | 40.216 | 0.01 | 0.5027 | 0 | 0 | 0 | 0 |  | 0 | 40.7187 |  | 27
[5 empty] | TROWEL FINISH PADS | 193.47 | SF | 6 | 13.3494 | 0.069 | 1.38 | 266.9886 | 0.02 | 3.8694 | 0 | 0 | 0 | 0 |  | 0 | 270.858 |  | 27
[5 empty] | RUB CONC PAD | 50.27 | SF | 6 | 5.027 | 0.1 | 2 | 100.54 | 0.03 | 1.5081 | 0 | 0 | 0 | 0 |  | 0 | 102.0481 |  | 27
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 193.47 | SF | 6 | 3.0955 | 0.016 | 0.32 | 61.9104 | 0.01 | 1.9347 | 0 | 0 | 0 | 0 |  | 0 | 63.8451 |  | 27
[5 empty] | PAD EDGEFORM | 152.34 | SF | 6 | 36.5616 | 0.24 | 4.8 | 731.232 | 1 | 152.34 | 0 | 0 | 0 | 0 |  | 0 | 883.572 |  | 27
[5 empty] | PLACE PADS | 3 | CY | 8 | 5.001 | 1.667 | 33.34 | 100.02 | 0 | 0 |  | 0 |  | 0 |  | 0 | 100.02 |  | 27
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 27
|  |  |  | HVAC Pads |  |  |  | 6 | [14 empty] | 27
[5 empty] | HAND PREP SUBGRADE-BUILDING | 77.89 | SF | 6 | 2.0251 | 0.026 | 0.52 | 40.5028 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.5028 |  | 27
[5 empty] | POINT & PATCH | 29.84 | SF | 8 | 1.9993 | 0.067 | 1.34 | 39.9856 | 0.01 | 0.2984 | 0 | 0 | 0 | 0 |  | 0 | 40.284 |  | 27
[5 empty] | FINISH CONCRETE | 77.89 | SF | 6 | 2.0251 | 0.026 | 0.52 | 40.5028 | 0.02 | 1.5578 | 0 | 0 | 0 | 0 |  | 0 | 42.0606 |  | 27
[5 empty] | SLAB EDGEFORM | 70.32 | SF | 6 | 16.8768 | 0.24 | 4.8 | 337.536 | 0.7 | 49.224 | 0 | 0 | 1 | 70.32 |  | 0 | 457.08 |  | 27
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 27
[5 empty] | RESTEEL DOBIE SUPPORTS | 77.89 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 3.8945 | 0 | 0 | 0 | 0 |  | 0 | 3.8945 |  | 27
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 6 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 27
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 27
|  |  | (120-E) Generator / MCC Building |  |  |  |  | 6
|  |  |  | 12" Continuous Footing |  |  |  | 6
[5 empty] | HAND EXCAV CONTINUOUS FTG | 6.86 | CY | 6 | 13.72 | 2 | 40 | 274.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 274.4 |  | 28
[5 empty] | FINISH TOP FTG/PILE CAP | 568 | SF | 8 | 15.904 | 0.028 | 0.56 | 318.08 | 0.02 | 11.36 | 0 | 0 | 0 | 0 |  | 0 | 329.44 |  | 28
[5 empty] | CONTINUOUS FTG EDGEFORM | 378.68 | SF | 6 | 90.8832 | 0.24 | 4.8 | 1817.664 | 0.45 | 170.406 | 0 | 0 | 1 | 378.68 |  | 0 | 2366.75 |  | 28
[5 empty] | RESTEEL DOBIE SUPPORTS | 568 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 28.4 | 0 | 0 | 0 | 0 |  | 0 | 28.4 |  | 28
[5 empty] | PLACE CONTINUOUS FOOTING | 22 | CY | 8 | 17.6 | 0.8 | 16 | 352 | 0 | 0 |  | 0 |  | 0 |  | 0 | 352 |  | 28
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 22 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 2420 | 0 | 0 | 0 | 0 |  | 0 | 2420 |  | 28
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 28
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1976 | SF | 6 | 31.616 | 0.016 | 0.32 | 632.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 632.32 |  | 28
[5 empty] | POINT & PATCH | 177 | SF | 8 | 5.31 | 0.03 | 0.6 | 106.2 | 0.01 | 1.77 | 0 | 0 | 0 | 0 |  | 0 | 107.97 |  | 28
[5 empty] | FINISH CONCRETE | 1976 | SF | 8 | 27.664 | 0.014 | 0.28 | 553.28 | 0.02 | 39.52 | 0 | 0 | 0 | 0 |  | 0 | 592.8 |  | 28
[5 empty] | SLAB EDGEFORM | 12 | SF | 6 | 2.88 | 0.24 | 4.8 | 57.6 | 0.7 | 8.4 | 0 | 0 | 1 | 12 |  | 0 | 78 |  | 28
[5 empty] | ZIP STRIP | 173 | LF | 6 | 5.017 | 0.029 | 0.58 | 100.34 | 1.125 | 194.625 |  | 0 |  | 0 |  | 0 | 294.965 |  | 28
[5 empty] | 1/2" EXPANSION JOINT | 173 | SF | 6 | 14.705 | 0.085 | 1.7 | 294.1 | 1.5 | 259.5 | 0 | 0 | 0 | 0 |  | 0 | 553.6 |  | 28
[5 empty] | 1/2" JOINT SEALANT | 209 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 522.5 |  | 0 | 522.5 |  | 28
[5 empty] | 10 MIL VISQUEEN | 20.96 | SQS | 6 | 4.7998 | 0.229 | 4.58 | 95.9968 | 30 | 628.8 | 0 | 0 | 0 | 0 |  | 0 | 724.7968 |  | 28
[5 empty] | SAW CUT CONCRETE | 36 | LF | 6 | 4.32 | 0.12 | 2.4 | 86.4 | 0.18 | 6.48 | 0 | 0 | 0.75 | 27 |  | 0 | 119.88 |  | 28
[5 empty] | RESTEEL DOBIE SUPPORTS | 1976 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 98.8 | 0 | 0 | 0 | 0 |  | 0 | 98.8 |  | 28
[5 empty] | PLACE SLAB ON GRADE | 41 | CY | 8 | 28.7 | 0.7 | 14 | 574 | 0 | 0 |  | 0 |  | 0 |  | 0 | 574 |  | 28
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 41 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 4510 | 0 | 0 | 0 | 0 |  | 0 | 4510 |  | 28
|  |  |  | Equipment Pads - 6 EA |  |  |  | 6 | [14 empty] | 28
[5 empty] | POINT & PATCH CONC PAD | 81.51 | SF | 8 | 2.0378 | 0.025 | 0.5 | 40.755 | 0.01 | 0.8151 | 0 | 0 | 0 | 0 |  | 0 | 41.5701 |  | 28
[5 empty] | TROWEL FINISH PADS | 481.65 | SF | 6 | 33.2339 | 0.069 | 1.38 | 664.677 | 0.02 | 9.633 | 0 | 0 | 0 | 0 |  | 0 | 674.31 |  | 28
[5 empty] | RUB CONC PAD | 81.51 | SF | 6 | 8.151 | 0.1 | 2 | 163.02 | 0.03 | 2.4453 | 0 | 0 | 0 | 0 |  | 0 | 165.4653 |  | 28
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 481.65 | SF | 6 | 7.7064 | 0.016 | 0.32 | 154.128 | 0.01 | 4.8165 | 0 | 0 | 0 | 0 |  | 0 | 158.9445 |  | 28
[5 empty] | PAD EDGEFORM | 247 | SF | 6 | 59.28 | 0.24 | 4.8 | 1185.6 | 1 | 247 | 0 | 0 | 0 | 0 |  | 0 | 1432.6 |  | 28
[5 empty] | PLACE PADS | 6 | CY | 8 | 6 | 1 | 20 | 120 | 0 | 0 |  | 0 |  | 0 |  | 0 | 120 |  | 28
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 6 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 660 | 0 | 0 | 0 | 0 |  | 0 | 660 |  | 28
|  |  |  | HVAC Pads |  |  |  | 6 | [14 empty] | 28
[5 empty] | HAND PREP SUBGRADE-BUILDING | 294 | SF | 6 | 4.704 | 0.016 | 0.32 | 94.08 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 94.08 |  | 28
[5 empty] | POINT & PATCH | 61.62 | SF | 8 | 1.9718 | 0.032 | 0.64 | 39.4368 | 0.01 | 0.6162 | 0 | 0 | 0 | 0 |  | 0 | 40.053 |  | 28
[5 empty] | FINISH CONCRETE | 294 | SF | 8 | 4.116 | 0.014 | 0.28 | 82.32 | 0.02 | 5.88 | 0 | 0 | 0 | 0 |  | 0 | 88.2 |  | 28
[5 empty] | SLAB EDGEFORM | 145 | SF | 6 | 34.8 | 0.24 | 4.8 | 696 | 0.7 | 101.5 | 0 | 0 | 1 | 145 |  | 0 | 942.5 |  | 28
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 28
[5 empty] | RESTEEL DOBIE SUPPORTS | 294 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 14.7 | 0 | 0 | 0 | 0 |  | 0 | 14.7 |  | 28
[5 empty] | PLACE SLAB ON GRADE | 5 | CY | 8 | 10 | 2 | 40 | 200 | 0 | 0 |  | 0 |  | 0 |  | 0 | 200 |  | 28
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 5 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 550 | 0 | 0 | 0 | 0 |  | 0 | 550 |  | 28
|  |  |  | 2' Thick Generator Slab |  |  |  | 6 | [14 empty] | 28
[5 empty] | HAND PREP SUBGRADE-BUILDING | 981.86 | SF | 6 | 15.7098 | 0.016 | 0.32 | 314.1952 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 314.1952 |  | 28
[5 empty] | POINT & PATCH | 437.28 | SF | 8 | 13.1184 | 0.03 | 0.6 | 262.368 | 0.01 | 4.3728 | 0 | 0 | 0 | 0 |  | 0 | 266.7408 |  | 28
[5 empty] | FINISH CONCRETE | 981.86 | SF | 8 | 13.746 | 0.014 | 0.28 | 274.9208 | 0.02 | 19.6372 | 0 | 0 | 0 | 0 |  | 0 | 294.558 |  | 28
[5 empty] | SLAB EDGEFORM | 437.28 | SF | 6 | 104.9472 | 0.24 | 4.8 | 2098.944 | 0.7 | 306.096 | 0 | 0 | 1 | 437.28 |  | 0 | 2842.32 |  | 28
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 20 | EA | 6 | 12 | 0.6 | 12 | 240 | 1.5 | 30 | 0 | 0 | 0 | 0 |  | 0 | 270 |  | 28
[5 empty] | RESTEEL DOBIE SUPPORTS | 981.86 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 49.093 | 0 | 0 | 0 | 0 |  | 0 | 49.093 |  | 28
[5 empty] | PLACE SLAB ON GRADE | 73 | CY | 8 | 43.8 | 0.6 | 12 | 876 | 0 | 0 |  | 0 |  | 0 |  | 0 | 876 |  | 28
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 73 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 8030 | 0 | 0 | 0 | 0 |  | 0 | 8030 |  | 28
|  |  |  | Generator Slab on Grade |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 2093 | SF | 8 | 33.488 | 0.016 | 0.32 | 669.76 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 669.76 |  | 28
[5 empty] | POINT & PATCH | 111.75 | SF | 6 | 3.3525 | 0.03 | 0.6 | 67.05 | 0.01 | 1.1175 | 0 | 0 | 0 | 0 |  | 0 | 68.1675 |  | 28
[5 empty] | FINISH CONCRETE | 2093 | SF | 6 | 28.7787 | 0.01375 | 0.275 | 575.575 | 0.02 | 41.86 | 0 | 0 | 0 | 0 |  | 0 | 617.435 |  | 28
[5 empty] | SLAB EDGEFORM | 223.5 | SF | 6 | 53.64 | 0.24 | 4.8 | 1072.8 | 0.7 | 156.45 | 0 | 0 | 1 | 223.5 |  | 0 | 1452.75 |  | 28
[5 empty] | RESTEEL DOBIE SUPPORTS | 2093 | SF | 6 | 0 | 0 | 0 | 0 | 0.5 | 1046.5 | 0 | 0 | 0 | 0 |  | 0 | 1046.5 |  | 28
[5 empty] | PLACE SLAB ON GRADE | 49 | CY | 6 | 29.4 | 0.6 | 12 | 588 | 0 | 0 |  | 0 |  | 0 |  | 0 | 588 |  | 28
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 49 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 5390 | 0 | 0 | 0 | 0 |  | 0 | 5390 |  | 28
|  |  | (125-E) Air Compressor / MCC Building |  |  |  |  | 6
|  |  |  | 12" Continuous Footing |  |  |  | 6
[5 empty] | HAND EXCAV CONTINUOUS FTG | 5.77 | CY | 6 | 11.54 | 2 | 40 | 230.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 230.8 |  | 29
[5 empty] | FINISH TOP FTG/PILE CAP | 471.9 | SF | 8 | 13.2132 | 0.028 | 0.56 | 264.264 | 0.02 | 9.438 | 0 | 0 | 0 | 0 |  | 0 | 273.702 |  | 29
[5 empty] | CONTINUOUS FTG EDGEFORM | 314.6 | SF | 6 | 75.504 | 0.24 | 4.8 | 1510.08 | 0.45 | 141.57 | 0 | 0 | 1 | 314.6 |  | 0 | 1966.25 |  | 29
[5 empty] | RESTEEL DOBIE SUPPORTS | 471.9 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 23.595 | 0 | 0 | 0 | 0 |  | 0 | 23.595 |  | 29
[5 empty] | PLACE CONTINUOUS FOOTING | 18 | CY | 8 | 18 | 1 | 20 | 360 | 0 | 0 |  | 0 |  | 0 |  | 0 | 360 |  | 29
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 18 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 1980 | 0 | 0 | 0 | 0 |  | 0 | 1980 |  | 29
|  |  |  | 6" Slab on Grade |  |  |  | 6 | [14 empty] | 29
[5 empty] | HAND PREP SUBGRADE-BUILDING | 1422.25 | SF | 6 | 22.756 | 0.016 | 0.32 | 455.12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 455.12 |  | 29
[5 empty] | POINT & PATCH | 146 | SF | 8 | 4.38 | 0.03 | 0.6 | 87.6 | 0.01 | 1.46 | 0 | 0 | 0 | 0 |  | 0 | 89.06 |  | 29
[5 empty] | FINISH CONCRETE | 90 | SF | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 29
[5 empty] | FINISH CONCRETE | 1332.25 | SF | 8 | 18.6515 | 0.014 | 0.28 | 373.03 | 0.02 | 26.645 | 0 | 0 | 0 | 0 |  | 0 | 399.675 |  | 29
[5 empty] | SLAB EDGEFORM | 15 | SF | 6 | 3.6 | 0.24 | 4.8 | 72 | 0.7 | 10.5 | 0 | 0 | 1 | 15 |  | 0 | 97.5 |  | 29
[5 empty] | ZIP STRIP | 144 | LF | 6 | 4.176 | 0.029 | 0.58 | 83.52 | 1.125 | 162 |  | 0 |  | 0 |  | 0 | 245.52 |  | 29
[5 empty] | 1/2" EXPANSION JOINT | 144 | SF | 6 | 12.24 | 0.085 | 1.7 | 244.8 | 1.5 | 216 | 0 | 0 | 0 | 0 |  | 0 | 460.8 |  | 29
[5 empty] | 1/2" JOINT SEALANT | 170 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 425 |  | 0 | 425 |  | 29
[5 empty] | 10 MIL VISQUEEN | 14.65 | SQS | 6 | 3.3549 | 0.229 | 4.58 | 67.097 | 30 | 439.5 | 0 | 0 | 0 | 0 |  | 0 | 506.597 |  | 29
[5 empty] | SAW CUT CONCRETE | 26 | LF | 6 | 3.12 | 0.12 | 2.4 | 62.4 | 0.18 | 4.68 | 0 | 0 | 0.75 | 19.5 |  | 0 | 86.58 |  | 29
[5 empty] | RESTEEL DOBIE SUPPORTS | 1422.25 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 71.1125 | 0 | 0 | 0 | 0 |  | 0 | 71.1125 |  | 29
[5 empty] | PLACE SLAB ON GRADE | 32 | CY | 8 | 22.4 | 0.7 | 14 | 448 | 0 | 0 |  | 0 |  | 0 |  | 0 | 448 |  | 29
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 32 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 3520 | 0 | 0 | 0 | 0 |  | 0 | 3520 |  | 29
|  |  |  | Equipment Pads - 4 EA |  |  |  | 6 | [14 empty] | 29
[5 empty] | POINT & PATCH CONC PAD | 46.86 | SF | 8 | 2.015 | 0.043 | 0.86 | 40.2996 | 0.01 | 0.4686 | 0 | 0 | 0 | 0 |  | 0 | 40.7682 |  | 29
[5 empty] | TROWEL FINISH PADS | 142 | SF | 6 | 9.798 | 0.069 | 1.38 | 195.96 | 0.02 | 2.84 | 0 | 0 | 0 | 0 |  | 0 | 198.8 |  | 29
[5 empty] | RUB CONC PAD | 46.86 | SF | 6 | 4.686 | 0.1 | 2 | 93.72 | 0.03 | 1.4058 | 0 | 0 | 0 | 0 |  | 0 | 95.1258 |  | 29
[5 empty] | ROUGH/CLEAN NEW CONC-PAD | 142 | SF | 6 | 2.272 | 0.016 | 0.32 | 45.44 | 0.01 | 1.42 | 0 | 0 | 0 | 0 |  | 0 | 46.86 |  | 29
[5 empty] | PAD EDGEFORM | 142 | SF | 6 | 34.08 | 0.24 | 4.8 | 681.6 | 1 | 142 | 0 | 0 | 0 | 0 |  | 0 | 823.6 |  | 29
[5 empty] | PLACE PADS | 2 | CY | 8 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 29
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 29
|  |  |  | HVAC Pads |  |  |  | 6 | [14 empty] | 29
[5 empty] | HAND PREP SUBGRADE-BUILDING | 77.89 | SF | 6 | 2.0251 | 0.026 | 0.52 | 40.5028 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 40.5028 |  | 29
[5 empty] | POINT & PATCH | 29.84 | SF | 8 | 1.9993 | 0.067 | 1.34 | 39.9856 | 0.01 | 0.2984 | 0 | 0 | 0 | 0 |  | 0 | 40.284 |  | 29
[5 empty] | FINISH CONCRETE | 77.89 | SF | 8 | 2.0251 | 0.026 | 0.52 | 40.5028 | 0.02 | 1.5578 | 0 | 0 | 0 | 0 |  | 0 | 42.0606 |  | 29
[5 empty] | SLAB EDGEFORM | 70.32 | SF | 6 | 16.8768 | 0.24 | 4.8 | 337.536 | 0.7 | 49.224 | 0 | 0 | 1 | 70.32 |  | 0 | 457.08 |  | 29
[5 empty] | SET ANCHOR BOLTS/ S.O.G. | 16 | EA | 6 | 9.6 | 0.6 | 12 | 192 | 1.5 | 24 | 0 | 0 | 0 | 0 |  | 0 | 216 |  | 29
[5 empty] | RESTEEL DOBIE SUPPORTS | 77.89 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 3.8945 | 0 | 0 | 0 | 0 |  | 0 | 3.8945 |  | 29
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 8 | 4 | 2 | 40 | 80 | 0 | 0 |  | 0 |  | 0 |  | 0 | 80 |  | 29
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 29
|  |  | Vaults / Boxes/ Pits |  |  |  |  | 6
|  |  |  | Valve Boxes / Fire Hydrants - 94 EA |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 222 | SF | 6 | 3.552 | 0.016 | 0.32 | 71.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 71.04 |  | 31
[5 empty] | POINT & PATCH | 288 | SF | 8 | 8.64 | 0.03 | 0.6 | 172.8 | 0.01 | 2.88 | 0 | 0 | 0 | 0 |  | 0 | 175.68 |  | 31
[5 empty] | FINISH CONCRETE | 222 | SF | 8 | 3.108 | 0.014 | 0.28 | 62.16 | 0.02 | 4.44 | 0 | 0 | 0 | 0 |  | 0 | 66.6 |  | 31
[5 empty] | SLAB EDGEFORM | 576 | SF | 6 | 138.24 | 0.24 | 4.8 | 2764.8 | 0.7 | 403.2 | 0 | 0 | 1 | 576 |  | 0 | 3744 |  | 31
[5 empty] | RESTEEL DOBIE SUPPORTS | 222 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 11.1 | 0 | 0 | 0 | 0 |  | 0 | 11.1 |  | 31
[5 empty] | PLACE SLAB ON GRADE | 5 | CY | 8 | 10 | 2 | 40 | 200 | 0 | 0 |  | 0 |  | 0 |  | 0 | 200 |  | 31
[5 empty] | PURCHASE: 3000 PSI CONCRETE | 5 | CY | 6 | 0 | 0 | 0 | 0 | 100 | 500 | 0 | 0 | 0 | 0 |  | 0 | 500 |  | 31
|  |  | Misc Site Items |  |  |  |  | 6
|  |  |  | Valve Station / C-501 |  |  |  | 6
[5 empty] | HAND PREP SUBGRADE-BUILDING | 12 | SF | 6 | 2.4 | 0.2 | 4 | 48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 48 |  | 32
[5 empty] | POINT & PATCH | 24 | SF | 8 | 1.968 | 0.082 | 1.64 | 39.36 | 0.01 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 39.6 |  | 32
[5 empty] | FINISH CONCRETE | 12 | SF | 8 | 2.4 | 0.2 | 4 | 48 | 0.02 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 48.24 |  | 32
[5 empty] | SLAB EDGEFORM | 24 | SF | 6 | 5.76 | 0.24 | 4.8 | 115.2 | 0.7 | 16.8 | 0 | 0 | 1 | 24 |  | 0 | 156 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 12 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 0.6 | 0 | 0 | 0 | 0 |  | 0 | 0.6 |  | 32
[5 empty] | PLACE SLAB ON GRADE | 1 | CY | 8 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 32
|  |  |  | SRWR Flow Meter / C-502 |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND PREP SUBGRADE-BUILDING | 100 | SF | 6 | 1.7 | 0.017 | 0.34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 34 |  | 32
[5 empty] | POINT & PATCH | 50 | SF | 8 | 1.9 | 0.038 | 0.76 | 38 | 0.01 | 0.5 | 0 | 0 | 0 | 0 |  | 0 | 38.5 |  | 32
[5 empty] | FINISH CONCRETE | 100 | SF | 8 | 1.7 | 0.017 | 0.34 | 34 | 0.02 | 2 | 0 | 0 | 0 | 0 |  | 0 | 36 |  | 32
[5 empty] | SLAB EDGEFORM | 50 | SF | 6 | 12 | 0.24 | 4.8 | 240 | 0.7 | 35 | 0 | 0 | 1 | 50 |  | 0 | 325 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 100 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 5 | 0 | 0 | 0 | 0 |  | 0 | 5 |  | 32
[5 empty] | POINT & PATCH CONC PIPE SUPPRT | 24 | SF | 8 | 1.92 | 0.08 | 1.6 | 38.4 | 0.01 | 0.24 | 0 | 0 | 0 | 0 |  | 0 | 38.64 |  | 32
[5 empty] | TROWEL FINISH PIPE SUPPORTS | 1.78 | SF | 6 | 2.136 | 1.2 | 24 | 42.72 | 0.02 | 0.0356 | 0 | 0 | 0 | 0 |  | 0 | 42.7556 |  | 32
[5 empty] | RUB CONC PIPE SUPPORT | 24 | SF | 6 | 2.4 | 0.1 | 2 | 48 | 0.03 | 0.72 | 0 | 0 | 0 | 0 |  | 0 | 48.72 |  | 32
[5 empty] | ROUGH/CLEAN NEW CONC-PIPE SUPPORT | 1.8 | SF | 6 | 2.16 | 1.2 | 24 | 43.2 | 0.01 | 0.018 | 0 | 0 | 0 | 0 |  | 0 | 43.218 |  | 32
[5 empty] | PIPE SUPPORT FORMWORK | 14 | SF | 6 | 3.92 | 0.28 | 5.6 | 78.4 | 1 | 14 | 0 | 0 | 0 | 0 |  | 0 | 92.4 |  | 32
[5 empty] | FORM SMALL PIPE SADDLE | 2 | EA | 6 | 2 | 1 | 20 | 40 | 1.5 | 3 | 0 | 0 | 0 | 0 |  | 0 | 43 |  | 32
[5 empty] | PLACE SLAB ON GRADE | 4 | CY | 8 | 4 | 1 | 20 | 80 | 7.5 | 30 |  | 0 |  | 0 |  | 0 | 110 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 32
[5 empty] | PLACE PIPE SUPPORT | 1 | CY | 6 | 2 | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 |  | 0 | 40 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 1 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 |  | 0 | 110 |  | 32
|  |  |  | Implant P.S. Flow Meter / C-119 |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND PREP SUBGRADE-BUILDING | 144 | SF | 6 | 2.304 | 0.016 | 0.32 | 46.08 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 46.08 |  | 32
[5 empty] | POINT & PATCH | 52 | SF | 8 | 1.976 | 0.038 | 0.76 | 39.52 | 0.01 | 0.52 | 0 | 0 | 0 | 0 |  | 0 | 40.04 |  | 32
[5 empty] | FINISH CONCRETE | 144 | SF | 8 | 2.016 | 0.014 | 0.28 | 40.32 | 0.02 | 2.88 | 0 | 0 | 0 | 0 |  | 0 | 43.2 |  | 32
[5 empty] | SLAB EDGEFORM | 52 | SF | 6 | 12.48 | 0.24 | 4.8 | 249.6 | 0.7 | 36.4 | 0 | 0 | 1 | 52 |  | 0 | 338 |  | 32
[5 empty] | 1/2" JOINT SEALANT | 16 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 40 |  | 0 | 40 |  | 32
[5 empty] | SAW CUT CONCRETE | 16 | LF | 6 | 1.92 | 0.12 | 2.4 | 38.4 | 0.18 | 2.88 | 0 | 0 | 0.75 | 12 |  | 0 | 53.28 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 144 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 7.2 | 0 | 0 | 0 | 0 |  | 0 | 7.2 |  | 32
[5 empty] | PLACE SLAB ON GRADE | 5 | CY | 8 | 10 | 2 | 40 | 200 | 0 | 0 |  | 0 |  | 0 |  | 0 | 200 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 5 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 550 | 0 | 0 | 0 | 0 |  | 0 | 550 |  | 32
|  |  |  | BFP Feed Pump Flowmeter Station / D115-301E |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND PREP SUBGRADE-BUILDING | 102.69 | SF | 6 | 1.9511 | 0.019 | 0.38 | 39.0222 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39.0222 |  | 32
[5 empty] | POINT & PATCH | 43.34 | SF | 8 | 1.9936 | 0.046 | 0.92 | 39.8728 | 0.01 | 0.4334 | 0 | 0 | 0 | 0 |  | 0 | 40.3062 |  | 32
[5 empty] | FINISH CONCRETE | 102.69 | SF | 8 | 1.9511 | 0.019 | 0.38 | 39.0222 | 0.02 | 2.0538 | 0 | 0 | 0 | 0 |  | 0 | 41.076 |  | 32
[5 empty] | SLAB EDGEFORM | 43.34 | SF | 6 | 10.4016 | 0.24 | 4.8 | 208.032 | 0.7 | 30.338 | 0 | 0 | 1 | 43.34 |  | 0 | 281.71 |  | 32
[5 empty] | 1/2" JOINT SEALANT | 14 | LF | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 35 |  | 0 | 35 |  | 32
[5 empty] | SAW CUT CONCRETE | 14 | LF | 6 | 2.002 | 0.143 | 2.86 | 40.04 | 0.18 | 2.52 | 0 | 0 | 0.75 | 10.5 |  | 0 | 53.06 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 102.69 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 5.1345 | 0 | 0 | 0 | 0 |  | 0 | 5.1345 |  | 32
[5 empty] | PLACE SLAB ON GRADE | 4 | CY | 8 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 32
|  |  |  | Yard Pipe Support Footings - 20 EA Detail 1/S507 |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND EXCAV COLUMN FTG | 1.956 | CY | 6 | 3.912 | 2 | 40 | 78.24 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 78.24 |  | 32
[5 empty] | FINISH TOP FTG/PILE CAP | 160 | SF | 8 | 4.48 | 0.028 | 0.56 | 89.6 | 0.02 | 3.2 | 0 | 0 | 0 | 0 |  | 0 | 92.8 |  | 32
[5 empty] | COLUMN FTG EDGEFORM | 360 | SF | 6 | 86.4 | 0.24 | 4.8 | 1728 | 0.45 | 162 | 0 | 0 | 1 | 360 |  | 0 | 2250 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 160 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 8 | 0 | 0 | 0 | 0 |  | 0 | 8 |  | 32
[5 empty] | PLACE COLUMN FOOTING | 9 | CY | 8 | 7.2 | 0.8 | 16 | 144 | 0 | 0 |  | 0 |  | 0 |  | 0 | 144 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 9 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 990 | 0 | 0 | 0 | 0 |  | 0 | 990 |  | 32
|  |  |  | Yard Pipe Support Columns - 20 EA Detail 1/S507 |  |  |  | 6 | [14 empty] | 32
[5 empty] | POINT & PATCH | 280.8 | SF | 8 | 8.424 | 0.03 | 0.6 | 168.48 | 0.01 | 2.808 | 0 | 0 | 0 | 0 |  | 0 | 171.288 |  | 32
[5 empty] | RUB CONC COLUMN/PIER | 280.8 | SF | 6 | 28.08 | 0.1 | 2 | 561.6 | 0.03 | 8.424 | 0 | 0 | 0 | 0 |  | 0 | 570.024 |  | 32
[5 empty] | PIER FORM: 4'-6' PERIM | 280.8 | SF | 6 | 73.8504 | 0.263 | 5.26 | 1477.008 | 0.818 | 229.6944 | 0 | 0 | 1 | 280.8 |  | 0 | 1987.5024 |  | 32
[5 empty] | SET ANCHOR BOLTS/ PIER | 80 | EA | 6 | 48 | 0.6 | 12 | 960 | 1.5 | 120 | 0 | 0 | 0 | 0 |  | 0 | 1080 |  | 32
[5 empty] | PLACE PIERS | 4 | CY | 8 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 32
|  |  |  | Misc Pads |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND PREP SUBGRADE-STEPS/GRADE | 150 | SF | 6 | 6 | 0.04 | 0.8 | 120 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 120 |  | 32
[5 empty] | BROOM FINISH STEPS ON GRADE | 150 | SF | 6 | 12.45 | 0.083 | 1.66 | 249 | 0.02 | 3 | 0 | 0 | 0 | 0 |  | 0 | 252 |  | 32
[5 empty] | LANDING ON-GRADE EDGEFORM | 120 | SF | 6 | 28.8 | 0.24 | 4.8 | 576 | 2 | 240 | 0 | 0 | 0 | 0 |  | 0 | 816 |  | 32
[5 empty] | PLACE STEPS & LANDING ON GRADE | 4 | CY | 8 | 8 | 2 | 40 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 4 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 440 | 0 | 0 | 0 | 0 |  | 0 | 440 |  | 32
|  |  |  | Pipe Bollards - 31 EA |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND EXCAV @ BOLLARDS | 42 | CY | 6 | 84 | 2 | 40 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1680 |  | 32
[5 empty] | SET PIPE BOLLARD | 42 | EA | 6 | 63 | 1.5 | 30 | 1260 | 3.5 | 147 | 0 | 0 | 0 | 0 |  | 0 | 1407 |  | 32
[5 empty] | GROUT PIPE BOLLARDS | 42 | EA | 6 | 63 | 1.5 | 30 | 1260 | 15 | 630 | 0 | 0 | 0 | 0 |  | 0 | 1890 |  | 32
[5 empty] | CONCRETE @ BOLLARD BASE | 42 | EA | 6 | 42 | 1 | 20 | 840 | 25 | 1050 | 0 | 0 | 0 | 0 |  | 0 | 1890 |  | 32
|  |  |  | Mitered End Section - 4 EA (7/C-503) |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND PREP SUBGRADE-BUILDING | 201 | SF | 6 | 3.216 | 0.016 | 0.32 | 64.32 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 64.32 |  | 32
[5 empty] | POINT & PATCH | 28 | SF | 8 | 1.988 | 0.071 | 1.42 | 39.76 | 0.01 | 0.28 | 0 | 0 | 0 | 0 |  | 0 | 40.04 |  | 32
[5 empty] | FINISH CONCRETE | 201 | SF | 8 | 2.814 | 0.014 | 0.28 | 56.28 | 0.02 | 4.02 | 0 | 0 | 0 | 0 |  | 0 | 60.3 |  | 32
[5 empty] | SLAB EDGEFORM | 112 | SF | 6 | 26.88 | 0.24 | 4.8 | 537.6 | 0.7 | 78.4 | 0 | 0 | 1 | 112 |  | 0 | 728 |  | 32
[5 empty] | 6X6-10/10 MESH 21# W1.4XW1.4 | 2.26 | SQS | 6 | 2.0001 | 0.885 | 17.7 | 40.002 | 18 | 40.68 | 0 | 0 | 0 | 0 |  | 0 | 80.682 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 201 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 10.05 | 0 | 0 | 0 | 0 |  | 0 | 10.05 |  | 32
[5 empty] | PLACE SLAB ON GRADE | 2 | CY | 8 | 8 | 4 | 80 | 160 | 0 | 0 |  | 0 |  | 0 |  | 0 | 160 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 2 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 220 | 0 | 0 | 0 | 0 |  | 0 | 220 |  | 32
6
|  |  |  | Pipe Collar - 3 EA (1/C-502) |  |  |  | 6 | [14 empty] | 32
[5 empty] | HAND PREP SUBGRADE-BUILDING | 147 | SF | 6 | 2.352 | 0.016 | 0.32 | 47.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 47.04 |  | 32
[5 empty] | POINT & PATCH | 84 | SF | 8 | 5.964 | 0.071 | 1.42 | 119.28 | 0.01 | 0.84 | 0 | 0 | 0 | 0 |  | 0 | 120.12 |  | 32
[5 empty] | FINISH CONCRETE | 135 | SF | 8 | 1.89 | 0.014 | 0.28 | 37.8 | 0.02 | 2.7 | 0 | 0 | 0 | 0 |  | 0 | 40.5 |  | 32
[5 empty] | SLAB EDGEFORM | 84 | SF | 6 | 20.16 | 0.24 | 4.8 | 403.2 | 0.7 | 58.8 | 0 | 0 | 1 | 84 |  | 0 | 546 |  | 32
[5 empty] | RESTEEL DOBIE SUPPORTS | 147 | SF | 6 | 0 | 0 | 0 | 0 | 0.05 | 7.35 | 0 | 0 | 0 | 0 |  | 0 | 7.35 |  | 32
[5 empty] | PLACE SLAB ON GRADE | 3 | CY | 8 | 12 | 4 | 80 | 240 | 0 | 0 |  | 0 |  | 0 |  | 0 | 240 |  | 32
[5 empty] | PURCHASE: 4000 PSI CONCRETE | 3 | CY | 6 | 0 | 0 | 0 | 0 | 110 | 330 | 0 | 0 | 0 | 0 |  | 0 | 330 |  | 32
6
6
6
[9 empty] | 83616.1199 |  |  | 1672112.398 |  | 3163348.667 |  | 911242.55 |  | 319696.5685 |  | 169130 | 6235530.1835
[5 empty] | BID TOTALS: |  |  |  | MHS |  |  | Labor |  | Materials |  | Subcontract |  | Equipment |  | Other | TOTAL
6235530.1835
Note on Q17: Eric Wagner: quote for Schneider / Lakeland was $12.73 for 2686 for 8" hollowcore, assuming that using $15/sf here for less quantity but thinner system should be OK.