## 6 Week Sch
OWP - AWWTF GMP 2C | [8 empty] | Night Work |  |  |  |  | X | Subs |  |  |  | County Holiday
Schedule | [8 empty] | Critical Path |  |  |  |  | P | Pour
2026-01-12 | [8 empty] | Holiday |  |  |  |  | I | Inspection
8 | [8 empty] | Shutdown Activity |  |  |  |  | X | Garney FC
Activity ID | Crew | Work Description 12-07-22 | Notes | Responsility | Budget | MH Burn Rate | Delta | Days | 2026-01-01 | [20 empty] | 2026-02-01 | [27 empty] | 2026-03-01 | [30 empty] | 2026-04-01 | [29 empty] | 2026-05-01 | [30 empty] | 2026-06-01 | [29 empty] | 2026-07-01 | [30 empty] | 2026-08-01 | [30 empty] | 2026-09-01 | [29 empty] | 2026-10-01 | [30 empty] | 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2026-02-01 | [11 empty] | Notes
[9 empty] | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | M | Tu | W | Th | F | S
 | time axis 2026-01-11 to 2027-02-12
|  | GENERAL CONDITIONS | [405 empty] | *
| 1 | CREW TOTALS | [7 empty] | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 0 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 13 | 13 | 13 | 13 | 13 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 13 | 13 | 13 | 13 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 3 | 3 | 3 | 8 |  |  | 8 | 13 | 13 | 13 | 13 |  |  | 18 | 18 | 18 | 18 | 18 |  |  | 3 | 13 | 13 | 13 | 18 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 10 |  |  | 10 | 10 | 10 | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 10 |  |  | 10 | 10 | 10 | 10 | 0 |  |  | 10 | 10 | 10 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 20 | 20 | 20 | 15 | 15 |  |  | 15 | 10 | 5 | 5 | 5 |  |  | 5 | 5 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 20 | 20 |  |  | 15 | 10 | 10 | 10 | 5 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 0 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 20 | 20 |  |  | 25 | 30 | 30 | 30 | 30 |  |  | 35 | 30 | 25 | 20 | 20 |  |  | 15 | 20 | 20 | 20 | 25 |  |  | 20 | 20 | 20 | 25 | 30 |  |  | 25 | 25 | 25 | 25 | 30 |  |  | 30 | 30 | 25 | 20 | 20 |  |  | 20 | 20 | 0 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 20 | 0 | 0 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 10 | 5 |  |  | 10 | 10 | 10 | 10 | 5 |  |  | 10 | 10 | 10 | 10 | 10 |  |  | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | EQUIPMENT | [405 empty] | *
|  | Mini Excavator |  | Rental |  |  |  | 0 | bar: 2026-01-30
|  | Walk Behind Roller/Tamp |  | Rental |  |  |  | 0 | bar: 2026-01-30
|  | 544 Loader |  | Rental |  |  |  | 0 | bar: 2026-01-30
|  | CAT 315 |  | Rental |  |  |  | 1 | bar: 2026-02-24
|  | 48kw Generator |  | Rental |  |  |  | 1 | bar: 2026-03-02
|  | 10K Lull |  | Rental |  |  |  | 0 | bar: 2026-03-26
|  | 20' Scissor Lift |  | Rental |  |  |  | 0 | bar: 2026-03-26
|  | 40' Boom Lift |  | Rental |  |  |  | 0 | bar: 2026-03-26
|  | PRECON | [405 empty] | *
|  | Expected GMP-02 NTP |  | Hillsborough County |  |  |  | 1 | bar: 2026-02-02
|  | Pre-Con Photos & Video |  | Hines |  |  |  | 4 | bar: 2026-02-03 to 2026-02-06
|  | Site Surveying |  | Hyatt Survey |  |  |  | 9 | bar: 2026-02-03 to 2026-02-06; 2026-02-09 to 2026-02-13
|  | Install Erosion Control |  | KCI |  |  |  | 9 | bar: 2026-02-03 to 2026-02-06; 2026-02-09 to 2026-02-13
0
|  | FENCING | [405 empty] | *
|  | Demo Existing Fence |  | TSS? |  |  |  | 14 | bar: 2026-02-02 to 2026-02-06; 2026-02-09 to 2026-02-13; 2026-02-16 to 2026-02-20
|  | Install Temp Fencing around Construction Staging Area |  | Fence 4 U |  |  |  | 10 | bar: 2026-03-16 to 2026-03-20; 2026-03-23 to 2026-03-27
|  | Install Permanent Fencing around Site |  | Big Jerry's |  |  |  | 15 | bar: 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22
0
SITEWORK
|  | West Construction Entrance with Soil Tracking Provisions |  | TSS Civil |  |  |  | 5 | bar: 2026-02-02 to 2026-02-06
|  | Site Prep, Clearing, and Grading for Gravel Road & Parking Area |  | TSS Civil |  |  |  | 5 | bar: 2026-02-09 to 2026-02-13
|  | Clear/Fill West Existing Ag. Ditch |  | TSS Civil |  |  |  | 9 | bar: 2026-02-16 to 2026-02-20; 2026-02-23 to 2026-02-27
|  | Place/Grade Gravel Road & Parking Area |  | TSS Civil |  |  |  | 5 | bar: 2026-03-02 to 2026-03-06
|  | Temporary Berms and/or Swales (Sedimentation Basin) |  | TSS Civil |  |  |  | 5 | bar: 2026-03-09 to 2026-03-13
|  | Clear/Fill Remaining NW Existing Ag. Ditch |  | TSS Civil |  |  |  | 15 | bar: 2026-03-16 to 2026-03-20; 2026-03-23 to 2026-03-27; 2026-03-30 to 2026-04-03
|  | F/R/P ADA Parking Spaces and Sidewalk |  | TSS Civil |  |  |  | 5 | bar: 2026-04-06 to 2026-04-10
|  | Install Parking Bumpers and Bollards |  | TSS Civil |  |  |  | 2 | bar: 2026-04-06 to 2026-04-07
|  | Parking Area Signage and Striping |  | TSS Civil |  |  |  | 2 | bar: 2026-04-08 to 2026-04-09
|  | Place Fill Material (Elev. 131.11 & 132.0) |  | TSS Civil |  |  |  | 15 | bar: 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01
|  | Clearing and Tree Removal along SR672 |  | TSS Civil |  |  |  | 10 | bar: 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01
|  | Clear/Fill Remaining Exisitng Ag. Ditches |  | TSS Civil |  |  |  | 15 | bar: 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22
|  | Remaining Site Prep, Clearing, and Grading |  | TSS Civil |  |  |  | 15 | bar: 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15
|  | South Construction Entrance with Soil Tracking Provisions |  | TSS Civil |  |  |  | 5 | bar: 2026-06-24 to 2026-06-26; 2026-06-29 to 2026-06-30
|  | Remaining Gravel Road |  | TSS Civil |  |  |  | 5 | bar: 2026-07-01 to 2026-07-03; 2026-07-06 to 2026-07-08
0
CONTRACTOR STAGING AREA
|  | Paint Conex and build office tables |  | Garney |  |  |  | 0 | 2026-01-12: 3; 2026-01-13: 3; 2026-01-14: 3; 2026-01-15: 3; 2026-01-16: 3; 2026-01-19: 3; 2026-01-20: 3; 2026-01-21: 3; 2026-01-22: 3; 2026-01-23: 3; 2026-01-26: 3; 2026-01-27: 3; 2026-01-28: 3; 2026-01-29: 3; 2026-01-30: 3
|  | Install Water Wells |  | Custom Drilling |  |  |  | 19 | bar: 2026-01-11 to 2027-02-12
|  | Run Contractor Staging Area Power |  | Cogburn |  |  |  | 14 | bar: 2026-02-09 to 2026-02-13; 2026-02-16 to 2026-02-20; 2026-02-23 to 2026-02-27
|  | Deliver/Setup Office Trailers |  | MBSI |  |  |  | 5 | bar: 2026-02-23 to 2026-02-27
| GS CREW #1 | Install Water and Sewer Lines to Trailers |  | Garney | 200 | 72 | 128 | 3 | 2026-02-25: 3; 2026-02-26: 3; 2026-02-27: 3
| GS CREW #2 | Build\ Office Trailer Deck/Steps - 446'X6' Deck (Includes Railing) |  | Garney | 1400 | 800 | 600 | 20 | 2026-03-02: 5; 2026-03-03: 5; 2026-03-04: 5; 2026-03-05: 5; 2026-03-06: 5; 2026-03-09: 5; 2026-03-10: 5; 2026-03-11: 5; 2026-03-12: 5; 2026-03-13: 5; 2026-03-16: 5; 2026-03-17: 5; 2026-03-18: 5; 2026-03-19: 5; 2026-03-20: 5; 2026-03-23: 5; 2026-03-24: 5; 2026-03-25: 5; 2026-03-26: 5; 2026-03-27: 5
| GS CREW #2 | Set Up Connexes (Changed from CPM) |  | Garney | 200 | 200 | 0 | 5 | 2026-03-30: 5; 2026-03-31: 5; 2026-04-01: 5; 2026-04-02: 5; 2026-04-03: 5
WAREHOUSE
| GS CREW #1 | D/L/B 2" SCH80 Conduit For Fiber |  | Garney | 450 | 384 | 66 | 16 | 2026-02-02: 3; 2026-02-03: 3; 2026-02-04: 3; 2026-02-05: 3; 2026-02-06: 3; 2026-02-09: 3; 2026-02-10: 3; 2026-02-11: 3; 2026-02-12: 3; 2026-02-13: 3; 2026-02-17: 3; 2026-02-18: 3; 2026-02-19: 3; 2026-02-20: 3; 2026-02-23: 3; 2026-02-24: 3
| GS CREW #2 | Clear Area and Prep Subgrade |  | Garney | 62 | 80 | -18 | 2 | 2026-03-16: 5; 2026-03-17: 5
| GS CREW #2 | F/R/P Slab |  | Garney | 380 | 240 | 140 | 6 | 2026-03-18: 5; 2026-03-19: 5; 2026-03-20: 5; 2026-03-23: 5; 2026-03-24: 5; 2026-03-25: 5
| GS CREW #2 | Assemble Warehouse Structure + Bollards |  | Garney | 680 | 480 | 200 | 12 | 2026-03-26: 5; 2026-03-27: 5; 2026-03-30: 5; 2026-03-31: 5; 2026-04-01: 5; 2026-04-02: 5; 2026-04-03: 5; 2026-04-06: 5; 2026-04-07: 5; 2026-04-08: 5; 2026-04-09: 5; 2026-04-10: 5
| GS CREW #2 | Install Electrcial, Lighting, HVAC, etc |  | Garney/Cogburn | 170 | 200 | -30 | 5 | 2026-04-13: 5; 2026-04-14: 5; 2026-04-15: 5; 2026-04-16: 5; 2026-04-17: 5
| GS CREW #2 | Install Shelves |  | Garney | 80 | 80 | 0 | 2 | 2026-04-20: 5; 2026-04-21: 5
| GS CREW #2 | Build Out Small Office |  | Garney | 150 | 120 | 30 | 3 | 2026-04-22: 5; 2026-04-23: 5; 2026-04-24: 5
0
|  | UNDERSLAB PIPING & ENCASEMENT | [405 empty] | *
112 | YP CREW #2 | 12" Drain - Under Reclaim Tanks 1-4 Slab | Not broken up in LSE, MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 404 | 400 | 4 | 10 | 2026-04-21: 5; 2026-04-22: 5; 2026-04-23: 5; 2026-04-24: 5; 2026-04-27: 5; 2026-04-28: 5; 2026-04-29: 5; 2026-04-30: 5; 2026-05-01: 5; 2026-05-04: 5
104Ua |  | 30" Mixed Liquor - Under BNR Basins 1 & 2 Slabs | Combined 1&2 per GMP-2C LSE, includes encasement MH's for both | Garney | 650 | 600 | 50 | 15 | 2026-05-08: 5; 2026-05-11: 5; 2026-05-12: 5; 2026-05-13: 5; 2026-05-14: 5; 2026-05-15: 5; 2026-05-18: 5; 2026-05-19: 5; 2026-05-20: 5; 2026-05-21: 5; 2026-05-22: 5; 2026-05-26: 5; 2026-05-27: 5; 2026-05-28: 5; 2026-05-29: 5
116.1U |  | 12" Drain - BNR Train 1&2 Drains Under Slab | LSE carries all 8, divded MH's by 4, includes pipe encasement | Garney | 529 | 520 | 9 | 13 | 2026-06-01: 5; 2026-06-02: 5; 2026-06-03: 5; 2026-06-04: 5; 2026-06-05: 5; 2026-06-08: 5; 2026-06-09: 5; 2026-06-10: 5; 2026-06-11: 5; 2026-06-12: 5; 2026-06-15: 5; 2026-06-16: 5; 2026-06-17: 5
107.3Ua |  | 48" Reclaim Water - Under SlabTank 1 | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 305 | 240 | 65 | 6 | 2026-06-26: 5; 2026-06-29: 5; 2026-06-30: 5; 2026-07-01: 5; 2026-07-02: 5; 2026-07-06: 5
107.3Ub |  | 48" Reclaim Water - Under SlabTank 2 | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 215 | 240 | -25 | 6 | 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-13: 5; 2026-07-14: 5
107.3Uc |  | 48" Reclaim Water - Under SlabTank 3 | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 215 | 240 | -25 | 6 | 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5
118U |  | 12" Sludge - Under WAS Storage Tanks | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 451 | 440 | 11 | 11 | 2026-07-01: 5; 2026-07-02: 5; 2026-07-06: 5; 2026-07-07: 5; 2026-07-08: 5; 2026-07-09: 5; 2026-07-10: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5
110.1a |  | 24" RAS - Under RAS PS 1 plus encasement | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 380 | 360 | 20 | 9 | 2026-07-09: 5; 2026-07-10: 5; 2026-07-13: 5; 2026-07-14: 5; 2026-07-15: 5; 2026-07-16: 5; 2026-07-17: 5; 2026-07-20: 5; 2026-07-21: 5
110.1b |  | 24" RAS - Under RAS PS 2 plus encasement | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 328 | 320 | 8 | 8 | 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-27: 5; 2026-07-28: 5; 2026-07-29: 5; 2026-07-30: 5; 2026-07-31: 5
108Ua |  | 54" Reclaim Water - Effluent Under Tank 1 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 245 | 240 | 5 | 6 | 2026-08-03: 5; 2026-08-04: 5; 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-10: 5
108Ub |  | 54" Reclaim Water - Effluent Under Tank 2 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 245 | 240 | 5 | 6 | 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5; 2026-08-17: 5; 2026-08-18: 5
108Uc |  | 54" Reclaim Water - Effluent Under Tank 3 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 245 | 240 | 5 | 6 | 2026-08-19: 5; 2026-08-20: 5; 2026-08-21: 5; 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5
118HU |  | 12" Sludge - Under Dewatering Feed PS Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 363 | 320 | 43 | 8 | 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5; 2026-08-14: 5
102.1U |  | 30" EQ Effluent- EQ Pump Station to EQ Tanks 1 - Under EQ Tanks | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 581 | 560 | 21 | 14 | 2026-08-27: 5; 2026-08-28: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5
102.1U |  | 30" EQ Effluent- EQ Pump Station to EQ Tanks 2 - Under EQ Tanks | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 581 | 560 | 21 | 14 | 2026-09-17: 5; 2026-09-18: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5; 2026-10-05: 5; 2026-10-06: 5
104Ua2 |  | 30" Mixed Liquor - Under Clarifier 1 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 360 | 360 | 0 | 9 | 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5
104Ua2 |  | 30" Mixed Liquor - Under Clarifier 2 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 360 | 360 | 0 | 9 | 2026-10-05: 5; 2026-10-06: 5; 2026-10-07: 5; 2026-10-08: 5; 2026-10-09: 5; 2026-10-13: 5; 2026-10-14: 5; 2026-10-15: 5; 2026-10-16: 5
103U |  | 36" EQ Influent - EQ Tank 1 to EQ Pump Station - Under EQ Tanks | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 210 | 160 | 50 | 4 | 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5
103U |  | 36" EQ Influent - EQ Tank 2 to EQ Pump Station - Under EQ Tanks | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 210 | 160 | 50 | 4 | 2026-10-02: 5; 2026-10-05: 5; 2026-10-06: 5; 2026-10-07: 5
110Ua |  | 16" RAS - Under Clarifier 1 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 305 | 280 | 25 | 7 | 2026-10-22: 5; 2026-10-23: 5; 2026-10-26: 5; 2026-10-27: 5; 2026-10-28: 5; 2026-10-29: 5; 2026-10-30: 5
110Ua |  | 16" RAS - Under Clarifier 2 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 305 | 280 | 25 | 7 | 2026-11-02: 5; 2026-11-03: 5; 2026-11-04: 5; 2026-11-05: 5; 2026-11-06: 5; 2026-11-09: 5; 2026-11-10: 5
116.3Ua |  | 10" Drain - Under Clarifier 1 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 315 | 280 | 35 | 7 | 2026-11-12: 5; 2026-11-13: 5; 2026-11-16: 5; 2026-11-17: 5; 2026-11-18: 5; 2026-11-19: 5; 2026-11-20: 5
116.3Ua |  | 10" Drain - Under Clarifier 2 Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 315 | 280 | 35 | 7 | 2026-11-23: 5; 2026-11-24: 5; 2026-11-25: 5; 2026-11-30: 5; 2026-12-01: 5; 2026-12-02: 5; 2026-12-03: 5
101U |  | 48" Force Main Plant Influent - Under Headworks | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 620 | 400 | 220 | 10 | 2026-12-04: 5; 2026-12-07: 5; 2026-12-08: 5; 2026-12-09: 5; 2026-12-10: 5; 2026-12-11: 5; 2026-12-14: 5; 2026-12-15: 5; 2026-12-16: 5; 2026-12-17: 5
115.4U |  | 18" Drain - Under Dewatering Facility Slab | MH's Include Pipe Encasement, DOES NOT include MH's for pipe testing | Garney | 650 | 600 | 50 | 15 | 2026-12-18: 5; 2026-12-21: 5; 2026-12-22: 5; 2026-12-23: 5; 2026-12-28: 5; 2026-12-29: 5; 2026-12-30: 5; 2026-12-31: 5; 2027-01-04: 5; 2027-01-05: 5; 2027-01-06: 5; 2027-01-07: 5; 2027-01-08: 5; 2027-01-11: 5; 2027-01-12: 5
4/2027 | 4/2027 | 6" Drain - Under Disk Filter Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 8" Drain - Under BNR Influent Train 3&4 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under BNR Basin 3 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under BNR Basin 4 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 24" Reject Return - Under Disk Filter Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 12" Drain - BNR Train 3&4 Drains Under Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 30" Secondary Effluent - Under Filter Slab (TYP 5) |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 8" Drain - Under BNR Influent Train 5&6 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under BNR Basin 5 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under BNR Basin 6 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 12" Drain - BNR Train 5&6 Drains Under Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 10" & 18" Drain - Under Chlorine Contact Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 16" RAS - Under Clarifier 3&4 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 48" Filter Effluent - Under Chlorine Contact Slab (TYP 2) |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 16" RAS - Under Clarifier 5&6 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under Clarifier 3 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under Clarifier 4 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under Clarifier 5 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 36" Mixed Liquor - Under Clarifier 6 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 10" Drain - Under Clarifier 3&4 Slab |  | Garney |  | 0 | 0 | 0
2027 | 2027 | 10" Drain - Under Clarifier 5&6 Slab |  | Garney |  | 0 | 0 | 0
2028 | 2028 | 24" RAS - Under RAS PS 3 |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  | YARD PIPE | [405 empty] | *
|  | Trench Testing For Dewatering System |  | Mid-State |  |  |  | 1 | bar: 2026-01-13
| GS CREW #1 | 6" Temp Water Line - Perimeter of Plant |  | Garney | 2500 | 1560 | 940 | 65 | 2026-03-02: 3; 2026-03-03: 3; 2026-03-04: 3; 2026-03-05: 3; 2026-03-06: 3; 2026-03-09: 3; 2026-03-10: 3; 2026-03-11: 3; 2026-03-12: 3; 2026-03-13: 3; 2026-03-16: 3; 2026-03-17: 3; 2026-03-18: 3; 2026-03-19: 3; 2026-03-20: 3; 2026-03-23: 3; 2026-03-24: 3; 2026-03-25: 3; 2026-03-26: 3; 2026-03-27: 3; 2026-03-30: 3; 2026-03-31: 3; 2026-04-01: 3; 2026-04-02: 3; 2026-04-03: 3; 2026-04-06: 3; 2026-04-07: 3; 2026-04-08: 3; 2026-04-09: 3; 2026-04-10: 3; 2026-04-13: 3; 2026-04-14: 3; 2026-04-15: 3; 2026-04-16: 3; 2026-04-17: 3; 2026-04-20: 3; 2026-04-21: 3; 2026-04-22: 3; 2026-04-23: 3; 2026-04-24: 3; 2026-04-27: 3; 2026-04-28: 3; 2026-04-29: 3; 2026-04-30: 3; 2026-05-01: 3; 2026-05-04: 3; 2026-05-05: 3; 2026-05-06: 3; 2026-05-07: 3; 2026-05-08: 3; 2026-05-11: 3; 2026-05-12: 3; 2026-05-13: 3; 2026-05-14: 3; 2026-05-15: 3; 2026-05-18: 3; 2026-05-19: 3; 2026-05-20: 3; 2026-05-21: 3; 2026-05-22: 3; 2026-05-25: 3; 2026-05-26: 3; 2026-05-27: 3; 2026-05-28: 3; 2026-05-29: 3
|  | Install Dewateringing System |  | Mid-State |  |  |  | 21 | bar: 2026-03-30 to 2026-04-03; 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27
115.1 |  | 8" Drain - BNR Influent Channel to Plant Lift Station 1 (w/ 1 Manhole) | MH's Include 1 Manhole | Garney | 390 | 360 | 30 | 9 | 2026-05-12: 5; 2026-05-13: 5; 2026-05-14: 5; 2026-05-15: 5; 2026-05-18: 5; 2026-05-19: 5; 2026-05-20: 5; 2026-05-21: 5; 2026-05-22: 5
112 |  | 12" Drain - Reclaim Tank 1 to Reject Pump Station (w/ 1 Valve Vault) | MH's Include VV | Garney | 229 | 200 | 29 | 5 | 2026-05-18: 5; 2026-05-19: 5; 2026-05-20: 5; 2026-05-21: 5; 2026-05-22: 5
112 |  | 12" Drain - Reclaim Tank 2 to Reject Pump Station (w/ 1 Valve Vault) | MH's Include VV | Garney | 157 | 160 | -3 | 4 | 2026-05-26: 5; 2026-05-27: 5; 2026-05-28: 5; 2026-05-29: 5
112 |  | 12" Drain - Reclaim Tank 3 to Reject Pump Station (w/ 1 Valve Vault) | MH's Include VV | Garney | 373 | 360 | 13 | 9 | 2026-06-01: 5; 2026-06-02: 5; 2026-06-03: 5; 2026-06-04: 5; 2026-06-05: 5; 2026-06-08: 5; 2026-06-09: 5; 2026-06-10: 5; 2026-06-11: 5
LS1 |  | Install Plant Lift Station 1 | MH's Includes Inv Grouting | Garney | 270 | 240 | 30 | 6 | 2026-05-29: 5; 2026-06-01: 5; 2026-06-02: 5; 2026-06-03: 5; 2026-06-04: 5; 2026-06-05: 5
113 |  | 16" Force Main - Plant Lift Station 1 to Headworks |  | Garney | 200 | 200 | 0 | 5 | 2026-06-08: 5; 2026-06-09: 5; 2026-06-10: 5; 2026-06-11: 5; 2026-06-12: 5
115.6 |  | 12" Drain - WAS Tank Drains to MH5&6 |  | Garney | 450 | 440 | 10 | 11 | 2026-06-15: 5; 2026-06-16: 5; 2026-06-17: 5; 2026-06-18: 5; 2026-06-22: 5; 2026-06-23: 5; 2026-06-24: 5; 2026-06-25: 5; 2026-06-26: 5; 2026-06-29: 5; 2026-06-30: 5
N/A |  | 12" Drain - Reclaim Tank 4 to Reject Pump Station (w/ 1 Valve Vault) | Tank 4 will be delted from scope? | Garney |  | 0 | 0 | 0
118 |  | 12" Sludge - WAS Tanks to Dewatering Feed PS |  | Garney | 340 | 320 | 20 | 8 | 2026-07-17: 5; 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-27: 5; 2026-07-28: 5
110.1a |  | 24" RAS - RAS PS Effluent up to 36" Tee |  | Garney | 260 | 240 | 20 | 6 | 2026-07-20: 5; 2026-07-21: 5; 2026-07-22: 5; 2026-07-23: 5; 2026-07-24: 5; 2026-07-27: 5
110.2 |  | 36" RAS - RAS PS 1-2 Effluent up to 48" (South to North) |  | Garney | 280 | 280 | 0 | 7 | 2026-08-05: 5; 2026-08-06: 5; 2026-08-07: 5; 2026-08-10: 5; 2026-08-11: 5; 2026-08-12: 5; 2026-08-13: 5
103 |  | 36" EQ Influent - Headworks to EQ Pump Station |  | Garney | 145 | 120 | 25 | 3 | 2026-08-13: 5; 2026-08-14: 5; 2026-08-17: 5
116.4 |  | 6" Scum Drain - RAS Pump Station 1 to 10" Drain Line |  | Garney | 115 | 120 | -5 | 3 | 2026-08-18: 5; 2026-08-19: 5; 2026-08-20: 5
108a |  | 54" Reclaim Water - Reclaim Tanks to Reclaim Pump Station |  | Garney | 650 | 640 | 10 | 16 | 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5; 2026-09-03: 5; 2026-09-04: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-14: 5; 2026-09-15: 5
108b |  | 54" Reclaim Water - Reclaim Tanks to Reclaim Pump Station |  | Garney | 540 | 520 | 20 | 13 | 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5
104.1 |  | 30" Mixed Liquor - BNR Basin 1 to Clarifier 1 |  | Garney | 350 | 320 | 30 | 8 | 2026-08-24: 5; 2026-08-25: 5; 2026-08-26: 5; 2026-08-27: 5; 2026-08-28: 5; 2026-08-31: 5; 2026-09-01: 5; 2026-09-02: 5
104.2 |  | 30" Mixed Liquor - BNR Basin 2 to Clarifier 2 |  | Garney | 550 | 480 | 70 | 12 | 2026-09-03: 5; 2026-09-04: 5; 2026-09-08: 5; 2026-09-09: 5; 2026-09-10: 5; 2026-09-11: 5; 2026-09-14: 5; 2026-09-15: 5; 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-21: 5
110.3 |  | 48" RAS - To Preliminary Treatment JB |  | Garney | 1700 | 1560 | 140 | 39 | 2026-09-16: 5; 2026-09-17: 5; 2026-09-18: 5; 2026-09-21: 5; 2026-09-22: 5; 2026-09-23: 5; 2026-09-24: 5; 2026-09-25: 5; 2026-09-28: 5; 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5; 2026-10-05: 5; 2026-10-06: 5; 2026-10-07: 5; 2026-10-08: 5; 2026-10-09: 5; 2026-10-12: 5; 2026-10-13: 5; 2026-10-14: 5; 2026-10-15: 5; 2026-10-16: 5; 2026-10-19: 5; 2026-10-20: 5; 2026-10-21: 5; 2026-10-22: 5; 2026-10-23: 5; 2026-10-26: 5; 2026-10-27: 5; 2026-10-28: 5; 2026-10-29: 5; 2026-10-30: 5; 2026-11-02: 5; 2026-11-03: 5; 2026-11-04: 5; 2026-11-05: 5; 2026-11-06: 5; 2026-11-09: 5
108H |  | 54" Reclaim Water - Reclaim Water Pump Station Header |  | Garney | 910 | 880 | 30 | 22 | 2026-10-05: 5; 2026-10-06: 5; 2026-10-07: 5; 2026-10-08: 5; 2026-10-09: 5; 2026-10-12: 5; 2026-10-13: 5; 2026-10-14: 5; 2026-10-15: 5; 2026-10-16: 5; 2026-10-19: 5; 2026-10-20: 5; 2026-10-21: 5; 2026-10-22: 5; 2026-10-23: 5; 2026-10-26: 5; 2026-10-27: 5; 2026-10-28: 5; 2026-10-29: 5; 2026-10-30: 5; 2026-11-02: 5; 2026-11-03: 5
115.2 |  | 10" Drain - From BOTH EQ Tanks to MH2 | MH's Include MH2 | Garney | 230 | 200 | 30 | 5 | 2026-09-29: 5; 2026-09-30: 5; 2026-10-01: 5; 2026-10-02: 5; 2026-10-05: 5
103 |  | 36" EQ Influent- EQ Pump Station to EQ Tanks |  | Garney | 600 | 600 | 0 | 15 | 2026-10-05: 5; 2026-10-06: 5; 2026-10-07: 5; 2026-10-08: 5; 2026-10-09: 5; 2026-10-12: 5; 2026-10-13: 5; 2026-10-14: 5; 2026-10-15: 5; 2026-10-16: 5; 2026-10-19: 5; 2026-10-20: 5; 2026-10-21: 5; 2026-10-22: 5; 2026-10-23: 5
109 |  | 48" Reclaim Water - Reclaim Water Pump Station to Distribution (PS to 45) | Add 1-20' Stick w/ plug past 45 | Garney | 575 | 560 | 15 | 14 | 2026-10-16: 5; 2026-10-19: 5; 2026-10-20: 5; 2026-10-21: 5; 2026-10-22: 5; 2026-10-23: 5; 2026-10-26: 5; 2026-10-27: 5; 2026-10-28: 5; 2026-10-29: 5; 2026-10-30: 5; 2026-11-02: 5; 2026-11-03: 5; 2026-11-04: 5
102.1 |  | 30" EQ Effluent - EQ Tanks to EQ Pump Station |  | Garney | 520 | 520 | 0 | 13 | 2026-10-23: 5; 2026-10-26: 5; 2026-10-27: 5; 2026-10-28: 5; 2026-10-29: 5; 2026-10-30: 5; 2026-11-02: 5; 2026-11-03: 5; 2026-11-04: 5; 2026-11-05: 5; 2026-11-06: 5; 2026-11-09: 5; 2026-11-10: 5
109 |  | 48" Reclaim Water - Reclaim Water Pump Station to Distribution (45 to N 90) |  | Garney | 1940 | 1920 | 20 | 49 | 2026-10-30: 5; 2026-11-02: 5; 2026-11-03: 5; 2026-11-04: 5; 2026-11-05: 5; 2026-11-06: 5; 2026-11-09: 5; 2026-11-10: 5; 2026-11-12: 5; 2026-11-13: 5; 2026-11-16: 5; 2026-11-17: 5; 2026-11-18: 5; 2026-11-19: 5; 2026-11-20: 5; 2026-11-23: 5; 2026-11-24: 5; 2026-11-25: 5; 2026-11-30: 5; 2026-12-01: 5; 2026-12-02: 5; 2026-12-03: 5; 2026-12-04: 5; 2026-12-07: 5; 2026-12-08: 5; 2026-12-09: 5; 2026-12-10: 5; 2026-12-11: 5; 2026-12-14: 5; 2026-12-15: 5; 2026-12-16: 5; 2026-12-17: 5; 2026-12-18: 5; 2026-12-21: 5; 2026-12-22: 5; 2026-12-23: 5; 2026-12-24: 5; 2026-12-25: 5; 2026-12-28: 5; 2026-12-29: 5; 2026-12-30: 5; 2026-12-31: 5; 2027-01-01: 5; 2027-01-04: 5; 2027-01-05: 5; 2027-01-06: 5; 2027-01-07: 5; 2027-01-08: 5
115 |  | 8" Drain - BNR Influent Channel on East Side (w/ 1 Manhole) |  | Garney | 230 | 200 | 30 | 5 | 2026-11-10: 5; 2026-11-12: 5; 2026-11-13: 5; 2026-11-16: 5; 2026-11-17: 5
102 |  | 30" EQ Effluent - EQ Pump Station to BNR Splitter Box |  | Garney | 260 | 240 | 20 | 6 | 2026-11-18: 5; 2026-11-19: 5; 2026-11-20: 5; 2026-11-23: 5; 2026-11-24: 5; 2026-11-25: 5
115.1 |  | 18" Drain - From BNR Between EQ Tanks to MH2 |  | Garney | 217 | 200 | 17 | 5 | 2026-11-25: 5; 2026-11-30: 5; 2026-12-01: 5; 2026-12-02: 5; 2026-12-03: 5
MH 111 |  | Install Scum Manhole1 (#111) |  | Garney | 100 | 80 | 20 | 2 | 2026-08-14: 5; 2026-08-17: 5
111 |  | 6" Scum - Clarifier 1&2 Scum Lines and (1) PC Manhole | MH's Include Manhole Install | Garney | 160 | 160 | 0 | 4 | 2026-12-04: 5; 2026-12-07: 5; 2026-12-08: 5; 2026-12-09: 5
110Ha |  | 16" RAS - Clarifier 1&2 to RAS PS 1 | NOT ENOUGH IN ESTIMATE! | Garney | 100 | 120 | -20 | 3 | 2026-12-10: 5; 2026-12-11: 5; 2026-12-14: 5
116.3a |  | 10" Drain - Clarifier 1 to MH3 |  | Garney | 80 | 80 | 0 | 2 | 2026-12-15: 5; 2026-12-16: 5
116.3a |  | 18" Drain - Clarifier 2 to 10" Drain |  | Garney | 50 | 40 | 10 | 1 | 2026-12-17: 5
105a |  | 30" Secondary Effluent - Clarifiers 1 to Disk Filters (to 48"SE) |  | Garney | 100 | 100 | 0 | 3 | 2026-12-18: 5; 2026-12-21: 5; 2026-12-22: 2.5
105a |  | 30" Secondary Effluent - Clarifiers 2 to Disk Filters (to 48"SE) |  | Garney | 100 | 100 | 0 | 3 | 2026-12-22: 2.5; 2026-12-23: 5; 2026-12-24: 5
|  | 48" Force Main Plant Influent | Goes into 2027 | Garney |  | 0 | 0 | 0
|  | 48" Reclaim Water - Reclaim Water Pump Station to Distribution (N 90 to Landfill Road) | Goes into 2027 | Garney |  | 0 | 0 | 0
BNR FOUNDATION IMPROVEMENTS
|  | BNR Foundation Improvements |  | Menard |  |  |  | 20 | bar: 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01
|  | F/R/P Train 1&2 Foundation - Pour #1 |  | Baker |  |  |  | 6 | bar: 2026-05-29; 2026-06-01 to 2026-06-05
|  | F/R/P Train 1&2 Foundation - Pour #2 |  | Baker |  |  |  | 6 | bar: 2026-06-08 to 2026-06-12; 2026-06-15
|  | F/R/P Train 1&2 Foundation - Pour #3 |  | Baker |  |  |  | 6 | bar: 2026-06-16 to 2026-06-19; 2026-06-22 to 2026-06-24
|  | F/R/P Train 1&2 Foundation - Pour #4 |  | Baker |  |  |  | 6 | bar: 2026-06-25 to 2026-06-26; 2026-06-29 to 2026-07-03
|  | F/R/P Train 1&2 Foundation - Pour #5 |  | Baker |  |  |  | 6 | bar: 2026-07-06 to 2026-07-10; 2026-07-13
|  | F/R/P Train 1&2 Foundation - Pour #6 |  | Baker |  |  |  | 6 | bar: 2026-07-14 to 2026-07-17; 2026-07-20 to 2026-07-21
|  | F/R/P Train 1&2 Foundation - Pour #7 |  | Baker |  |  |  | 6 | bar: 2026-07-22 to 2026-07-24; 2026-07-27 to 2026-07-29
|  | F/R/P Train 1&2 Foundation - Pour #8 |  | Baker |  |  |  | 6 | bar: 2026-07-30 to 2026-07-31; 2026-08-03 to 2026-08-06
|  | F/R/P Train 1&2 Foundation - Pour #9 |  | Baker |  |  |  | 6 | bar: 2026-08-07; 2026-08-10 to 2026-08-14
|  | F/R/P Train 1&2 Foundation - Pour #10 |  | Baker |  |  |  | 6 | bar: 2026-08-17 to 2026-08-21; 2026-08-24
|  | F/R/P Train 1&2 Foundation - Pour #11 |  | Baker |  |  |  | 6 | bar: 2026-08-25 to 2026-08-28; 2026-08-31 to 2026-09-01
|  | F/R/P Train 1&2 Foundation - Pour #12 |  | Baker |  |  |  | 6 | bar: 2026-09-02 to 2026-09-04; 2026-09-07 to 2026-09-10
|  | F/R/P Train 1&2 Foundation - Pour #13 |  | Baker |  |  |  | 6 | bar: 2026-09-11; 2026-09-14 to 2026-09-18
|  | F/R/P Train 1&2 Foundation - Pour #14 |  | Baker |  |  |  | 6 | bar: 2026-09-21 to 2026-09-25; 2026-09-28
|  | F/R/P Train 1&2 Foundation - Pour #15 |  | Baker |  |  |  | 6 | bar: 2026-09-29 to 2026-10-02; 2026-10-05 to 2026-10-06
|  | F/R/P Train 1&2 Foundation - Pour #16 |  | Baker |  |  |  | 3 | bar: 2026-10-07 to 2026-10-09; 2026-10-12 to 2026-10-14
|  | Remaining Concrete Work for Trains 1&2 - April 9, 2027 Completion | To Be Continued | Baker |  |  |  | 12 | [398 empty] | To Be Continued | bar: 2026-10-15 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30
0
WIDENING TURN LANE EDITION
|  | Relocate Existing Ditch |  | ??? |  |  |  | 10 | bar: 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15
|  | Widen SR 672 |  | ??? |  |  |  | 15 | bar: 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08
|  | Milling and Resurfacing of SR 672 |  | ??? |  |  |  | 5 | bar: 2026-06-09 to 2026-06-12; 2026-06-15
|  | Asphalt Striping |  | ??? |  |  |  | 5 | bar: 2026-06-16 to 2026-06-19; 2026-06-22 to 2026-06-23
0
|  | SITE ELECTRICAL |  |  |  |  | Cogburn
|  | Temp 480V Construction Power Loop |  | Cogburn | 5995 |  | 150 | 150 | bar: 2026-03-02 to 2026-03-06; 2026-03-09 to 2026-03-13; 2026-03-16 to 2026-03-20; 2026-03-23 to 2026-03-27; 2026-03-30 to 2026-04-03; 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01; 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-19; 2026-06-22 to 2026-06-26; 2026-06-29 to 2026-07-03; 2026-07-06 to 2026-07-10; 2026-07-13 to 2026-07-17; 2026-07-20 to 2026-07-24; 2026-07-27 to 2026-07-31; 2026-08-03 to 2026-08-07; 2026-08-10 to 2026-08-14; 2026-08-17 to 2026-08-21; 2026-08-24 to 2026-08-28; 2026-08-31 to 2026-09-04; 2026-09-07 to 2026-09-11; 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-09-29
|  | Install MV Ductbank 11 |  | Cogburn | 3241 |  | 81 | 81 | bar: 2026-03-02 to 2026-03-06; 2026-03-09 to 2026-03-13; 2026-03-16 to 2026-03-20; 2026-03-23 to 2026-03-27; 2026-03-30 to 2026-04-03; 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01; 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-12; 2026-06-15 to 2026-06-19; 2026-06-22 to 2026-06-24
|  | Dewatering Pumps |  | Cogburn | 2806 |  | 70 | 69 | bar: 2026-03-02 to 2026-03-06; 2026-03-09 to 2026-03-13; 2026-03-16 to 2026-03-20; 2026-03-23 to 2026-03-27; 2026-03-30 to 2026-04-03; 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01; 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05
|  | Well Pumps | TECO Primary DB | Cogburn | 3370 |  | 52 | 52 | bar: 2026-03-31 to 2026-04-03; 2026-04-06 to 2026-04-10; 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01; 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-11
|  | Tower Cranes |  | Cogburn | 1555 |  | 39 | 39 | bar: 2026-04-13 to 2026-04-17; 2026-04-20 to 2026-04-24; 2026-04-27 to 2026-05-01; 2026-05-04 to 2026-05-08; 2026-05-11 to 2026-05-15; 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05
|  | Install MV Ductbank 10 | EB1 480V DB | Cogburn | 989 |  | 15 | 18 | bar: 2026-06-09 to 2026-06-12; 2026-06-15 to 2026-06-19; 2026-06-22 to 2026-06-26; 2026-06-29 to 2026-07-03; 2026-07-06
|  | Install MV Ductbank 8 (Complete 26-Apr-27) | Generator DB | Cogburn | 990 |  | 15 | 19 | bar: 2026-05-18 to 2026-05-22; 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05; 2026-06-08 to 2026-06-11
|  | Install MV Ductbank 16 | MV Loop | Cogburn | 868 |  | 14 | 14 | bar: 2026-07-30 to 2026-07-31; 2026-08-03 to 2026-08-07; 2026-08-10 to 2026-08-14; 2026-08-17 to 2026-08-18; 2026-09-07
|  | Install MV Ductbank 17 | MV Loop | Cogburn | 1898 |  | 30 | 16 | bar: 2026-08-19 to 2026-08-21; 2026-08-24 to 2026-08-28; 2026-08-31 to 2026-09-04; 2026-09-08 to 2026-09-10
|  | Install MV Ductbank 19 | Blower Building DB | Cogburn | 660 |  | 11 | 18 | bar: 2026-09-11; 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02; 2026-10-05 to 2026-10-06; 2026-11-11
|  | Install MV Ductbank 6 | MV Loop | Cogburn | 1194 |  | 19 | 30 | bar: 2026-10-07 to 2026-10-09; 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-10; 2026-11-12 to 2026-11-13; 2026-11-16 to 2026-11-18; 2026-11-26 to 2026-11-27; 2026-12-24 to 2026-12-25
|  | Install MV Ductbank 5 | Dewatering DB | Cogburn | 497 |  | 8 | 14 | bar: 2026-11-19 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-08; 2026-12-24 to 2026-12-25
|  | Install MV Ductbank 1/2 | MV Loop | Cogburn | 1157 |  | 18 | 43 | bar: 2026-12-09 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05
|  | Install MV Ductbank 7 | MV Loop | Cogburn | 4192 |  | 66 | 26 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-10; 2026-11-12 to 2026-11-13; 2026-11-16 to 2026-11-17; 2027-02-07 to 2027-02-11
|  | Install MV Ductbank 3 |  | Cogburn |  |  | 0 | 0
|  | Install MV Ductbank 12 |  | Cogburn |  |  | 0 | 0
|  | Install MV Ductbank 18 |  | Cogburn |  |  | 0 | 0
|  | Install MV Ductbank 15 |  | Cogburn |  |  | 0 | 0
|  | Install MV Ductbank 13 |  | Cogburn |  |  | 0 | 0
|  | Install MV Ductbank 14 |  | Cogburn |  |  | 0 | 0
|  | Install MV Ductbank 4 | EB4 DB | Cogburn | 695 |  | 11 | 0
|  | Install MV Ductbank 9 | OPS Building DB | Cogburn | 721 |  | 12 | 25 | bar: 2026-11-18 to 2026-11-20; 2026-11-23 to 2026-11-25; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-23; 2026-12-28
|  | Install MV Ductbank 12 | OPS Building DB | Cogburn | 547 |  | 9 | 0
|  | Install MV Ductbank 13 | OPS Building DB | Cogburn | 520 |  | 9 | 0
|  | Install MV Ductbank 14 | MV Loop | Cogburn | 850 |  | 14 | 0
|  | Install MV Ductbank 15 | MV Loop | Cogburn | 1046 |  | 16 | 0
|  | Install TECO Primary Ductbank | EB3 DB | Cogburn | 251 |  | 4 | 0
|  | Install MV Ductbank 16 | MV Loop | Cogburn | 1163 |  | 18 | 0
|  | Install MV Ductbank 21 | Comms DB From the World | Cogburn | 1523 |  | 24 | 0
|  | Install MV Ductbank 20 (may be VE out of scope) | Comms DB From the World | Cogburn | 1077 |  | 17 | 0
|  |  |  | Cogburn |  |  |  | 0
*
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
|  |  |  | Garney |  | 0 | 0 | 0
0
*
0
0
*
0
0
0
0
0
0
0
0
0
*
*
*
Note on C125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to wait on these until we confirm we are building tanks.
Note on C126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to wait on these until we confirm we are building tanks.
Note on C127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to wait on these until we confirm we are building tanks.